{"text_format":"1","workbook":"xlsx","n_sheets":5,"sheets":["Map","Schedule","Graphic Overview","Help","Data"],"not_rendered":{"charts":0,"images":3,"macros":1,"external_links":7,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Map","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Schedule","index":1,"n_rows":1617,"n_cols":32,"rows_kept":1617,"cut":false,"hidden":false,"merged":[[1,23,1,27],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]]}
[null,10000]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination","In yearly timetable","IM\nProject ID\n(Optional)"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other"]
[null,"DB Netz AG","301106.01","Berlin - Frankurt (O)","< >","Erkner","Bln-Köpenick",2018,2018,10,10,"10.03.2018","22:00:00","11.03.2018","04:00:00","6 h","abends, nachts/\nat night, evening","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C385E85A296A.01"]
[null,"DB Netz AG","301106.02","Berlin - Frankurt (O)","< >","Bln-Köpenick","Erkner",2018,2018,10,16,"11.03.2018","22:55:00","19.04.2018","05:05:00","7 d, 11 h","nachts/\nat night","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,"So-Do/MTWThSu, jeweils/each 22:55-05:05 ",null,"X","1C385E85A296A.02"]
[null,"DB Netz AG","201145.01","Berlin - Frankurt (O)","< >","Bln-Köpenick","Bln-Köpenick",2018,2018,15,16,"13.04.2018","22:00:00","19.04.2018","22:00:00","6 d","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C6856E330DCA.01"]
[null,"DB Netz AG","301126.01","Berlin - Frankurt (O)","< >","Erkner","Rahnsdorf    Üst",2018,2018,16,17,"19.04.2018","22:00:00","29.04.2018","22:00:00","10 d","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C6CD8592DC0A.01"]
[null,"DB Netz AG","301234.01","Berlin - Frankurt (O)","< >","Bln-Köpenick","Bln-Köpenick",2018,2018,16,18,"19.04.2018","22:00:00","30.04.2018","04:00:00","10 d, 06 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C6B7A4D4456A.01"]
[null,"DB Netz AG","10310","Berlin - Frankurt (O)","<","Rahnsdorf    Üst","Bln-Köpenick",2018,2018,17,18,"27.04.2018","22:00:00","30.04.2018","04:00:00","2 d, 06 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C75B06198EEA.01"]
[null,"DB Netz AG","301126.02","Berlin - Frankurt (O)","< >","Erkner","Stadtforst",2018,2018,17,18,"29.04.2018","22:00:00","30.04.2018","04:00:00","6 h","abends, nachts/\nat night, evening","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C6CD8592DC0A.02"]
[null,"DB Netz AG","301133.01","Berlin - Frankurt (O)","<","Erkner","Rahnsdorf    Üst",2018,2018,18,48,"30.04.2018","04:00:00","30.11.2018","22:00:00","214 d, 18 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C6CF224CD182.01"]
[null,"DB Netz AG","301134.03","Berlin - Frankurt (O)","<","Oderbrücke","Frankfurt (O)",2018,2018,21,23,"21.05.2018","06:00:00","04.06.2018","06:00:00","14 d","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C959768C784A.03"]
[null,"DB Netz AG","1C8482E66CD22.01","Berlin - Frankurt (O)","<","Stadtforst","Bln-Rummels Rgo",2018,2018,27,28,"06.07.2018","23:40:00","09.07.2018","04:20:00","2 d, 05 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C8482E66CD22.01"]
[null,"DB Netz AG","1C8482E66CD22.02","Berlin - Frankurt (O)","< >","Bln-Rummels Rgo","Stadtforst",2018,2018,27,28,"07.07.2018","18:20:00","09.07.2018","04:20:00","20 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 18:20-04:20 ",null,null,"1C8482E66CD22.02"]
[null,"DB Netz AG","201140.01","Berlin - Frankurt (O)","<","Stadtforst","Bln-Rummels Rgo",2018,2018,28,29,"13.07.2018","23:40:00","16.07.2018","04:20:00","2 d, 05 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C8488F54A4E2.01"]
[null,"DB Netz AG","201140.02","Berlin - Frankurt (O)","< >","Bln-Rummels Rgo","Stadtforst",2018,2018,28,29,"14.07.2018","18:20:00","16.07.2018","04:20:00","20 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 18:20-04:20 ",null,null,"1C8488F54A4E2.02"]
[null,"DB Netz AG","304095.01","Magdeburg - Berlin","<","Biederitz","Werder (Havel)",2018,2018,14,16,"02.04.2018","21:00:00","16.04.2018","05:00:00","4 d, 16 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 21:00-05:00 ",null,null,"1C8B5D51E9F3F.01"]
[null,"DB Netz AG","40329","Magdeburg - Berlin","<","Magdeburg Hbf","Mg-Neustadt",2018,2018,18,18,"05.05.2018","09:15:00","06.05.2018","15:45:00","1 d, 07 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C6C8A1BA245F.01"]
[null,"DB Netz AG","1C62AC38E0023.03","Magdeburg - Berlin","< >","Lu Wittenberg","Lu Wittenberg",2018,2018,24,25,"15.06.2018","22:10:00","22.06.2018","04:20:00","1 d, 19 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:10-04:20 ",null,null,"1C62AC38E0023.03"]
[null,"DB Netz AG","1C8482E66CD22.04","Magdeburg - Berlin","<","Eichgestell","Ostendgestell",2018,2018,27,28,"06.07.2018","23:40:00","09.07.2018","04:20:00","2 d, 05 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C8482E66CD22.04"]
[null,"DB Netz AG","1C8482E66CD22.03","Magdeburg - Berlin","< >","Ostendgestell","Eichgestell",2018,2018,27,28,"07.07.2018","18:20:00","09.07.2018","04:20:00","20 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 18:20-04:20 ",null,null,"1C8482E66CD22.03"]
[null,"DB Netz AG","201140.04","Magdeburg - Berlin","<","Eichgestell","Ostendgestell",2018,2018,28,29,"13.07.2018","23:40:00","16.07.2018","04:20:00","2 d, 05 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C8488F54A4E2.04"]
[null,"DB Netz AG","201140.03","Magdeburg - Berlin","< >","Ostendgestell","Eichgestell",2018,2018,28,29,"14.07.2018","18:20:00","16.07.2018","04:20:00","20 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 18:20-04:20 ",null,null,"1C8488F54A4E2.03"]
[null,"DB Netz AG","301108.02","Magdeburg - Berlin",">","Wilhelmsh   Abzw","Michendorf",2018,2018,11,13,"16.03.2018","04:00:00","26.03.2018","04:00:00","10 d","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C3FA7D619D5F.02"]
[null,"DB Netz AG","201049.01","Magdeburg - Berlin","< >","Bad Belzig","Brück (Mark)",2018,2018,14,15,"05.04.2018","22:00:00","10.04.2018","22:00:00","5 d","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C76D73C89BBF.01"]
[null,"DB Netz AG","10170","Magdeburg - Berlin",">","Brück (Mark)","Bad Belzig",2018,2018,15,15,"13.04.2018","22:00:00","15.04.2018","06:00:00","16 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"1C76D73C89BBF.05"]
[null,"DB Netz AG","201050.01","Magdeburg - Berlin","<","Bad Belzig","Brück (Mark)",2018,2018,16,17,"20.04.2018","22:00:00","23.04.2018","06:00:00","2 d, 08 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C76DEEE295DF.01"]
[null,"DB Netz AG","10229","Magdeburg - Berlin","<","Brück (Mark)","Brück (Mark)",2018,2018,16,17,"20.04.2018","22:00:00","23.04.2018","06:00:00","2 d, 08 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C76DEEE295DF.04"]
[null,"DB Netz AG","201050.02","Magdeburg - Berlin","< >","Brück (Mark)","Bad Belzig",2018,2018,17,17,"23.04.2018","00:00:00","23.04.2018","06:00:00","6 h","nachts/\nat night","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C76DEEE295DF.02"]
[null,"DB Netz AG","1C745F729E723.04","Magdeburg - Berlin",">","Meinsdorf","Dessau Gbf",2018,2018,23,25,"04.06.2018","23:00:00","22.06.2018","05:00:00","4 d, 12 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1C745F729E723.04"]
[null,"DB Netz AG","301186.01","Magdeburg - Berlin","< >","Bad Belzig","Bad Belzig",2018,2018,36,38,"08.09.2018","09:00:00","22.09.2018","09:00:00","14 d","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C5CB1149E9BF.01"]
[null,"DB Netz AG","301186.02","Magdeburg - Berlin",">","Brück (Mark)","Bad Belzig",2018,2018,36,38,"08.09.2018","09:00:00","22.09.2018","09:00:00","14 d","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C5CB1149E9BF.02"]
[null,"DB Netz AG","40329","Hamburg - Magdeburg","< >","Mg-Neustadt","Magdeburg Hbf",2018,2018,18,18,"05.05.2018","09:15:00","06.05.2018","15:45:00","1 d, 07 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C6C8A1BA245F.02"]
[null,"DB Netz AG","201087.01","Magdeburg - Berlin","<","Michendorf","Saarmund",2018,2018,28,28,"09.07.2018","08:00:00","09.07.2018","22:00:00","14 h","tagsüber/\nduring the day","Durcharbeitung von Gleisen/\ntrackage maintenance",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C5E040CE049F.01"]
[null,"DB Netz AG","201087.02","Magdeburg - Berlin",">","Saarmund","Michendorf",2018,2018,28,28,"10.07.2018","08:00:00","10.07.2018","22:00:00","14 h","tagsüber/\nduring the day","Durcharbeitung von Gleisen/\ntrackage maintenance",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C5E040CE049F.02"]
[null,"DB Netz AG","201087.03","Magdeburg - Berlin","<","Michendorf","Saarmund",2018,2018,28,28,"11.07.2018","08:00:00","11.07.2018","20:00:00","12 h","tagsüber/\nduring the day","Durcharbeitung von Gleisen/\ntrackage maintenance",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C5E040CE049F.03"]
[null,"DB Netz AG","201087.04","Magdeburg - Berlin",">","Saarmund","Michendorf",2018,2018,28,28,"12.07.2018","08:00:00","12.07.2018","20:00:00","12 h","tagsüber/\nduring the day","Durcharbeitung von Gleisen/\ntrackage maintenance",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C5E040CE049F.04"]
[null,"DB Netz AG","1C6889558FEB4.01","Hamburg - Magdeburg","< >","Hannover Hbf","Hannover Hbf",2018,2018,24,24,"11.06.2018","23:00:00","13.06.2018","05:00:00","12 h","nachts/\nat night","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1C6889558FEB4.01"]
[null,"DB Netz AG","302015.02","Hamburg - Magdeburg","<","Stelle","Meckelfeld",2018,2018,27,35,"06.07.2018","23:00:00","27.08.2018","05:00:00","51 d, 06 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C9C817B216F3.02"]
[null,"DB Netz AG","302016.01","Hamburg - Magdeburg","< >","Meckelfeld","Maschen Pbf",2018,2018,28,28,"09.07.2018","23:30:00","12.07.2018","04:30:00","15 h","nachts/\nat night","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:30-04:30 ",null,null,"1C9C824397CB3.01"]
[null,"DB Netz AG","1C5554A245E33.01","Hamburg - Magdeburg",">","Deutsch Evern","Bienenbüttel",2018,2018,42,42,"17.10.2018","00:00:00","19.10.2018","05:00:00","15 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:00-05:00 ",null,null,"1C5554A245E33.01"]
[null,"DB Netz AG","1C555D8D5E8B3.01","Hamburg - Magdeburg","<","Klein Süstedt","Uelzen Gbf",2018,2018,47,47,"19.11.2018","23:50:00","22.11.2018","05:30:00","17 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:50-05:30 ",null,null,"1C555D8D5E8B3.01"]
[null,"DB Netz AG","20248","Bremerhaven - Bremen","<","Stubben","Brh-Wulsdorf",2018,2018,14,15,"07.04.2018","00:00:00","09.04.2018","05:00:00","15 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:00-05:00 ",null,null,"1C5E2F36B967C.02"]
[null,"DB Netz AG","20248","Bremerhaven - Bremen","<","Brh-L Abstellbf","Brh-Speckenbütt",2018,2018,15,15,"13.04.2018","00:00:00","15.04.2018","05:00:00","15 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:00-05:00 ",null,null,"1C5E2F36B967C.04"]
[null,"DB Netz AG","20363","Bremerhaven - Bremen",">","Brh-Speckenbütt","Brh-Lehe Pbf",2018,2018,16,16,"17.04.2018","00:00:00","21.04.2018","05:00:00","1 d, 01 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:00-05:00 ",null,null,"1C5E2FA389D9C.01"]
[null,"DB Netz AG","20363","Bremerhaven - Bremen","<","Brh-L Abstellbf","Brh-Speckenbütt",2018,2018,17,17,"24.04.2018","00:00:00","26.04.2018","05:00:00","15 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:00-05:00 ",null,null,"1C5E2FA389D9C.03"]
[null,"DB Netz AG","20383","Bremerhaven - Bremen",">","Bremen-Burg","Bremen Hbf",2018,2018,17,18,"27.04.2018","22:00:00","02.05.2018","05:00:00","4 d, 07 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C8712C06995A.05"]
[null,"DB Netz AG","20382","Bremerhaven - Bremen","<","Bremen Hbf","Osterholz-Scharm",2018,2018,17,18,"28.04.2018","20:00:00","02.05.2018","04:00:00","3 d, 08 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1B4C9370F9151.01"]
[null,"DB Netz AG","20382","Bremerhaven - Bremen","<","Brm Rbf Abzw","Osterholz-Scharm",2018,2018,17,18,"28.04.2018","20:00:00","02.05.2018","04:00:00","3 d, 08 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1B4C9370F9151.02"]
[null,"DB Netz AG","20434","Bremerhaven - Bremen",">","Brh-Wulsdorf","Stubben",2018,2018,18,18,"02.05.2018","22:30:00","04.05.2018","05:00:00","13 h","nachts/\nat night","Durcharbeitung von Gleisen/\ntrackage maintenance",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:30-05:00 ",null,null,"1C2F7A1225F9C.03"]
[null,"DB Netz AG","202457.01","Bremerhaven - Bremen",">","Brh-Speckenbütt","Brh-Lehe Pbf",2018,2018,20,21,"19.05.2018","23:30:00","22.05.2018","05:00:00","17 h","nachts/\nat night","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:30-05:00 ",null,null,"1C5E2FE03131C.01"]
[null,"DB Netz AG","202476.02","Bremerhaven - Bremen","< >","Brm Rbf Abzw","Brm Rbf Abzw",2018,2018,22,23,"28.05.2018","12:00:00","05.06.2018","12:00:00","8 d","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1CB3E35F58A9C.02"]
[null,"DB Netz AG","302201.01","Bremerhaven - Bremen","<","Bremen Hbf","Brhv-Seehf DB-Gr",2018,2018,22,24,"28.05.2018","23:00:00","11.06.2018","05:00:00","3 d","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"(Sa)/MTWThFSu, jeweils/each 23:00-05:00 ",null,null,"1CB3D440C385C.01"]
[null,"DB Netz AG","302201.02","Bremerhaven - Bremen","<","Bremen Hbf","Brhv-Seehf DB-Gr",2018,2018,22,23,"02.06.2018","23:00:00","10.06.2018","06:30:00","15 h","nachts, morgens/\nat night, morning","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 23:00-06:30 ",null,null,"1CB3D440C385C.02"]
[null,"DB Netz AG","202464.03","Bremerhaven - Bremen","< >","Bremerhaven Hbf","Brh-Lehe Pbf",2018,2018,33,33,"18.08.2018","22:00:00","19.08.2018","05:45:00","8 h","abends, nachts/\nat night, evening","Inbetriebnahme/\nstartup operations","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C5E3090E873C.03"]
[null,"DB Netz AG","202464.01","Bremerhaven - Bremen","< >","Brh-L Abstellbf","Brh-Speckenbütt",2018,2018,33,33,"18.08.2018","22:00:00","19.08.2018","08:00:00","10 h","abends, nachts, morgens/\nat night, morning, evening","Inbetriebnahme/\nstartup operations","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C5E3090E873C.01"]
[null,"DB Netz AG","1C9E441B7DCDC.01","Bremerhaven - Bremen","< >","Brh-Wulsdorf","Brh-Wulsdorf",2018,2018,45,49,"10.11.2018","00:00:00","08.12.2018","23:59:00","17 d","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"Sa-Di/MTSSu",null,null,"1C9E441B7DCDC.01"]
[null,"DB Netz AG","302082.01","Bremen - Hannover","<","Wunstorf","Bremen Hbf",2018,2018,3,13,"19.01.2018","23:00:00","30.03.2018","05:00:00","17 d, 12 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,"X","1C2C9967E875A.01"]
[null,"DB Netz AG","20136","Bremen - Hannover","< >","Langwedel","Verden (Aller)",2018,2018,7,9,"12.02.2018","01:30:00","27.02.2018","04:30:00","2 d","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:30-04:30 ",null,null,"1C29A4A1D59BA.01"]
[null,"DB Netz AG","20146","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2018,2018,9,9,"27.02.2018","01:15:00","03.03.2018","04:45:00","17 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:15-04:45 ",null,null,"1C2CB231C097A.01"]
[null,"DB Netz AG","302104.02","Bremen - Hannover","<","Verden (Aller)","Langwedel",2018,2018,9,11,"27.02.2018","22:00:00","13.03.2018","05:00:00","13 d, 07 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1C33D2FB93A5A.02"]
[null,"DB Netz AG","302103.02","Bremen - Hannover","<","Dörverden","Langwedel",2018,2018,9,11,"28.02.2018","01:00:00","12.03.2018","05:00:00","2 d, 04 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 01:00-05:00 ",null,"X","1C33D7B2A46FA.02"]
[null,"DB Netz AG","302105.01","Bremen - Hannover","<","Verden (Aller)","Etelsen",2018,2018,9,11,"01.03.2018","01:00:00","13.03.2018","05:00:00","2 d, 04 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 01:00-05:00 ",null,"X","1C33D82A2341A.01"]
[null,"DB Netz AG","20165","Bremen - Hannover","< >","Rohrsen/Nienburg","Rohrsen/Nienburg",2018,2018,10,10,"06.03.2018","01:15:00","07.03.2018","04:45:00","7 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:15-04:45 ",null,null,"1C3E05D2F935A.01"]
[null,"DB Netz AG","20165","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2018,2018,10,10,"06.03.2018","01:15:00","07.03.2018","04:45:00","7 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:15-04:45 ",null,null,"1C2CC5E5D4C5A.01"]
[null,"DB Netz AG","302108.01","Bremen - Hannover","< >","Rohrsen/Nienburg","Rohrsen/Nienburg",2018,2018,10,10,"07.03.2018","07:00:00","09.03.2018","17:00:00","1 d, 06 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,"Mi-Fr/WThF, jeweils/each 07:00-17:00 ",null,"X","1C2DF01ACAE7A.01"]
[null,"DB Netz AG","20165","Bremen - Hannover","< >","Rohrsen/Nienburg","Rohrsen/Nienburg",2018,2018,10,10,"08.03.2018","01:15:00","09.03.2018","04:45:00","7 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:15-04:45 ",null,null,"1C3E061C8073A.01"]
[null,"DB Netz AG","302108.02","Bremen - Hannover","<","Nienburg (Weser)","Eystrup",2018,2018,10,11,"10.03.2018","01:00:00","12.03.2018","04:45:00","2 d, 04 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1C2DF01ACAE7A.02"]
[null,"DB Netz AG","302111.01","Bremen - Hannover","<","Etelsen","Etelsen",2018,2018,11,12,"13.03.2018","22:00:00","23.03.2018","05:00:00","9 d, 07 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1C2C91517B29A.01"]
[null,"DB Netz AG","302111.03","Bremen - Hannover","< >","Etelsen","Etelsen",2018,2018,11,12,"14.03.2018","01:30:00","23.03.2018","04:30:00","1 d, 06 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung mit BR, PSS und TE/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:30-04:30 ",null,null,"1C2C91517B29A.03"]
[null,"DB Netz AG","20198","Bremen - Hannover","< >","Langwedel","Verden (Aller)",2018,2018,11,13,"14.03.2018","01:30:00","26.03.2018","04:30:00","1 d, 15 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:30-04:30 ",null,null,"1C33ED110379A.01"]
[null,"DB Netz AG","20198","Bremen - Hannover",">","Rohrsen/Nienburg","Nienburg (Weser)",2018,2018,11,11,"15.03.2018","07:00:00","16.03.2018","17:00:00","20 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Vegetationsarbeiten/\nvegetation work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-17:00 ",null,"X","19C671990F1AC.03"]
[null,"DB Netz AG","20198","Bremen - Hannover","<","Eystrup","Dörverden",2018,2018,11,12,"18.03.2018","07:00:00","20.03.2018","17:00:00","1 d, 06 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Vegetationsarbeiten/\nvegetation work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-17:00 ",null,null,"19C671990F1AC.05"]
[null,"DB Netz AG","302112.01","Bremen - Hannover","< >","Bremen-Mahndorf","Bremen-Mahndorf",2018,2018,12,12,"19.03.2018","07:00:00","23.03.2018","18:00:00","2 d, 07 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,"Mo-Fr/MTWThF, jeweils/each 07:00-18:00 ",null,"X","1C4B34077E63A.01"]
[null,"DB Netz AG","20198","Bremen - Hannover","<","Achim","Achim",2018,2018,12,12,"20.03.2018","08:00:00","23.03.2018","17:00:00","1 d, 12 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 08:00-17:00 ",null,null,"1C4B40AF6955A.01"]
[null,"DB Netz AG","20198","Bremen - Hannover",">","Dörverden","Eystrup",2018,2018,12,12,"21.03.2018","07:00:00","23.03.2018","17:00:00","1 d, 06 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Vegetationsarbeiten/\nvegetation work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-17:00 ",null,null,"1C4B8B9B9D2BA.04"]
[null,"DB Netz AG","302118.01","Bremen - Hannover",">","Eystrup","Eystrup",2018,2018,12,13,"23.03.2018","22:00:00","30.03.2018","05:00:00","6 d, 07 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1C4B35169F91A.01"]
[null,"DB Netz AG","302112.02","Bremen - Hannover","<","Baden /Kr Verden","Bremen-Mahndorf",2018,2018,12,13,"23.03.2018","23:00:00","26.03.2018","05:00:00","2 d, 06 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1C4B34077E63A.02"]
[null,"DB Netz AG","20198","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2018,2018,12,13,"24.03.2018","01:15:00","28.03.2018","04:30:00","16 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 01:15-04:30 ",null,null,"1C2CCA631AA3A.02"]
[null,"DB Netz AG","302119.03","Bremen - Hannover","< >","Eystrup","Eystrup",2018,2018,12,13,"25.03.2018","01:15:00","29.03.2018","04:45:00","17 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung mit BR, PSS und TE/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:15-04:45 ",null,null,"1C4B3595149DA.03"]
[null,"DB Netz AG","20290","Hannover - Magdeburg",">","Frellstedt","Königslutter",2018,2018,14,15,"06.04.2018","18:00:00","09.04.2018","10:00:00","2 d, 16 h","ganztags/\nfull day","Einbau Planumsschutzschicht/\nplanum protective layer",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BBFB33675085.01"]
[null,"DB Netz AG","202167.01","Oberhausen - Hannover","< >","Löhne(Westf) Pbf","Löhne(Westf) Pbf",2018,2018,21,24,"22.05.2018","07:00:00","11.06.2018","16:00:00","20 d, 09 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1CA6AD2BAB1FA.01"]
[null,"DB Netz AG","302208.01","Oberhausen - Hannover","< >","Löhne(Westf) Gbf","Herford",2018,2018,24,24,"11.06.2018","01:00:00","14.06.2018","23:59:00","3 d, 23 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CA713C28623A.01"]
[null,"DB Netz AG","302210.01","Oberhausen - Hannover",">","Oeynhausen Abzw","Löhne(Westf) Pbf",2018,2018,24,25,"16.06.2018","01:00:00","18.06.2018","04:00:00","2 d, 03 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1CA8381558FBA.01"]
[null,"DB Netz AG","1C6889E6854B4.01","Oberhausen - Hannover","< >","Hannover Hbf","Hannover Hbf",2018,2018,25,25,"18.06.2018","23:00:00","20.06.2018","05:00:00","12 h","nachts/\nat night","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1C6889E6854B4.01"]
[null,"DB Netz AG","202280.02","Oberhausen - Hannover","< >","Oeynhausen Abzw","Oeynhausen Abzw",2018,2018,26,26,"30.06.2018","00:15:00","30.06.2018","06:15:00","6 h","nachts, morgens/\nat night, morning","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CAE08CC9685A.02"]
[null,"DB Netz AG","202281.02","Oberhausen - Hannover","< >","Oeynhausen Abzw","Oeynhausen Abzw",2018,2018,27,27,"07.07.2018","00:15:00","07.07.2018","06:15:00","6 h","nachts, morgens/\nat night, morning","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CAE09DAF463A.02"]
[null,"DB Netz AG","202282.02","Oberhausen - Hannover","< >","Oeynhausen Abzw","Oeynhausen Abzw",2018,2018,28,28,"14.07.2018","00:15:00","14.07.2018","06:15:00","6 h","nachts, morgens/\nat night, morning","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CAE0C059C93A.02"]
[null,"DB Netz AG","202284.02","Oberhausen - Hannover","< >","Oeynhausen Abzw","Oeynhausen Abzw",2018,2018,29,29,"21.07.2018","00:15:00","21.07.2018","06:15:00","6 h","nachts, morgens/\nat night, morning","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CAE0D85A801A.02"]
[null,"DB Netz AG","202285.02","Oberhausen - Hannover","< >","Oeynhausen Abzw","Oeynhausen Abzw",2018,2018,32,32,"11.08.2018","00:15:00","11.08.2018","06:15:00","6 h","nachts, morgens/\nat night, morning","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CAE0E53BECBA.02"]
[null,"DB Netz AG","202286.02","Oberhausen - Hannover","< >","Oeynhausen Abzw","Oeynhausen Abzw",2018,2018,34,34,"26.08.2018","00:15:00","26.08.2018","06:15:00","6 h","nachts, morgens/\nat night, morning","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CAE10238461A.02"]
[null,"DB Netz AG","1C688A584B454.01","Hannover - Magdeburg","< >","Hannover Hbf","Hannover Hbf",2018,2018,25,25,"21.06.2018","23:00:00","23.06.2018","05:00:00","12 h","nachts/\nat night","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1C688A584B454.01"]
[null,"DB Netz AG","1C99AD80D2FF4.01","Hannover - Magdeburg","< >","Hannover Hbf","Hannover Hbf",2018,2018,29,29,"16.07.2018","23:00:00","18.07.2018","05:00:00","12 h","nachts/\nat night","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1C99AD80D2FF4.01"]
[null,"DB Netz AG","302125.01","Oberhausen - Hannover","< >","Ahlem","Han-Linden Hafen",2018,2018,13,14,"29.03.2018","21:00:00","03.04.2018","12:00:00","4 d, 15 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C5F570954274.01"]
[null,"DB Netz AG","302125.02","Oberhausen - Hannover",">","Hannover-Linden","Seelze Ost",2018,2018,13,14,"29.03.2018","21:00:00","03.04.2018","17:00:00","4 d, 20 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C5F570954274.02"]
[null,"DB Netz AG","202182.01","Oberhausen - Hannover","< >","Hannover-Linden","Hannover-Linden",2018,2018,17,24,"27.04.2018","07:00:00","12.06.2018","18:00:00","46 d, 11 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C8B3AF274C74.01"]
[null,"DB Netz AG","20423","Oberhausen - Hannover","< >","Hannover-Linden","Hannover-Linden",2018,2018,17,24,"27.04.2018","07:00:00","12.06.2018","18:00:00","46 d, 11 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C8B3AF274C74.02"]
[null,"DB Netz AG","20476","Oberhausen - Hannover","< >","Hannover-Linden","Hannover-Linden",2018,2018,19,21,"09.05.2018","08:00:00","24.05.2018","18:00:00","15 d, 10 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C9B36452FDB4.02"]
[null,"DB Netz AG","20476","Oberhausen - Hannover","< >","Hannover-Linden","Hannover-Linden",2018,2018,19,21,"09.05.2018","08:00:00","24.05.2018","18:00:00","15 d, 10 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C9B36452FDB4.03"]
[null,"DB Netz AG","302127.04","Löhne - Bad Bentheim","< >","Rheine","Rheine",2018,2018,13,13,"29.03.2018","22:00:00","31.03.2018","06:00:00","1 d, 08 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2AFD3748C61.04"]
[null,"DB Netz AG","302129.02","Löhne - Bad Bentheim","< >","Rheine","Rheine",2018,2018,13,14,"31.03.2018","06:00:00","03.04.2018","01:00:00","2 d, 19 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2AFD8B04521.02"]
[null,"DB Netz AG","202330.01","Löhne - Bad Bentheim","< >","Bünde (Westf)","Bruchmühlen",2018,2018,13,13,"01.04.2018","00:30:00","01.04.2018","06:30:00","6 h","nachts, morgens/\nat night, morning","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C4E09F4F549A.01"]
[null,"DB Netz AG","302129.04","Löhne - Bad Bentheim","< >","Rheine","Ibbenbüren-Esch",2018,2018,14,15,"03.04.2018","01:00:00","09.04.2018","05:00:00","6 d, 04 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C2AFD8B04521.04"]
[null,"DB Netz AG","20257","Löhne - Bad Bentheim","<","Ibbenbüren-Esch","Ibbenbüren",2018,2018,15,25,"09.04.2018","23:00:00","23.06.2018","23:00:00","75 d","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,null,null,"X",null,null,null,null,null,null,null,null,null,"1C4E3D251C5FA.01"]
[null,"DB Netz AG","20368","Löhne - Bad Bentheim","< >","Osn-Eversburg","Osnabrück Hbf Pu",2018,2018,17,18,"27.04.2018","23:00:00","02.05.2018","04:00:00","4 d, 05 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,null,null,"X",null,null,null,null,null,null,null,null,null,"1C69E8B7C0B1A.01"]
[null,"DB Netz AG","202406.01","Löhne - Bad Bentheim",">","Osnabrück Hbf Pu","Osn-Eversburg",2018,2018,17,18,"27.04.2018","23:00:00","02.05.2018","04:00:00","4 d, 05 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C69EC25CCF7A.01"]
[null,"DB Netz AG","20410","Löhne - Bad Bentheim","< >","Osn-Eversburg","Velpe (Westf)",2018,2018,18,18,"06.05.2018","00:05:00","06.05.2018","06:45:00","7 h","nachts, morgens/\nat night, morning","Durcharbeitung von Gleisen/\ntrackage maintenance","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C5CA917C189A.02"]
[null,"DB Netz AG","202337.01","Löhne - Bad Bentheim",">","Ibbenbüren-Esch","Rheine",2018,2018,22,22,"28.05.2018","23:50:00","31.05.2018","05:30:00","17 h","nachts/\nat night","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:50-05:30 ",null,null,"1C9DF978E987A.01"]
[null,"DB Netz AG","202337.02","Löhne - Bad Bentheim","< >","Rheine","Ibbenbüren-Esch",2018,2018,22,22,"29.05.2018","01:30:00","30.05.2018","04:30:00","6 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:30-04:30 ",null,null,"1C9DF978E987A.02"]
[null,"DB Netz AG","302203.02","Löhne - Bad Bentheim","<","Löhne(Westf) Gbf","Löhne(Westf) Pbf",2018,2018,22,23,"31.05.2018","01:00:00","10.06.2018","05:00:00","10 d, 04 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1CA6B504DE97A.02"]
[null,"DB Netz AG","302204.01","Löhne - Bad Bentheim","<","Wissingen","Melle",2018,2018,22,23,"02.06.2018","00:00:00","04.06.2018","06:00:00","2 d, 06 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C9F75F77D83A.01"]
[null,"DB Netz AG","302207.01","Löhne - Bad Bentheim",">","Melle","Wissingen",2018,2018,23,24,"09.06.2018","00:00:00","11.06.2018","06:00:00","2 d, 06 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C9F7C55FCBDA.01"]
[null,"DB Netz AG","202359.01","Löhne - Bad Bentheim",">","Ibbenbüren","Ibbenbüren-Esch",2018,2018,23,24,"10.06.2018","23:00:00","13.06.2018","05:20:00","19 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:20 ",null,null,"1CAE3D06A003A.01"]
[null,"DB Netz AG","302210.02","Löhne - Bad Bentheim",">","Löhne(Westf) Pbf","Löhne(Westf) Gbf",2018,2018,24,25,"16.06.2018","01:00:00","18.06.2018","04:00:00","2 d, 03 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1CA8381558FBA.02"]
[null,"DB Netz AG","302210.05","Löhne - Bad Bentheim",">","Löhne(Westf) Pbf","Kirchlengern",2018,2018,24,25,"16.06.2018","01:00:00","18.06.2018","04:00:00","2 d, 03 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1CA8381558FBA.05"]
[null,"DB Netz AG","202319.01","Löhne - Bad Bentheim","< >","Ibbenbüren","Ibbenbüren-Esch",2018,2018,27,27,"07.07.2018","23:50:00","08.07.2018","06:40:00","7 h","night time, morgens/\nmorning","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C4E40FEBBB5A.01"]
[null,"DB Netz AG","202320.01","Löhne - Bad Bentheim","< >","Ibbenbüren","Ibbenbüren-Esch",2018,2018,28,28,"14.07.2018","23:50:00","15.07.2018","06:40:00","7 h","night time, morgens/\nmorning","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C4E4237D313A.01"]
[null,"DB Netz AG","202321.01","Löhne - Bad Bentheim","< >","Ibbenbüren","Ibbenbüren-Esch",2018,2018,44,44,"03.11.2018","23:50:00","04.11.2018","06:40:00","7 h","night time, morgens/\nmorning","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C4E428F15F1A.01"]
[null,"DB Netz AG","202338.01","Löhne - Bad Bentheim","<","Rheine","Ibbenbüren-Esch",2018,2018,46,46,"12.11.2018","23:40:00","14.11.2018","05:40:00","12 h","nachts/\nat night","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:40-05:40 ",null,null,"1C9DFD215335A.01"]
[null,"DB Netz AG","102082.02","Löhne - Bad Bentheim","< >","Bad Bentheim","Bad Bentheim",2018,2018,12,13,"24.03.2018","22:00:00","26.03.2018","06:00:00","16 h","abends, nachts/\nat night, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"1C2E0D20C7AA1.02"]
[null,"DB Netz AG","302133.01","Löhne - Bad Bentheim","< >","Salzbergen","Schüttorf",2018,2018,14,15,"03.04.2018","01:00:00","09.04.2018","08:00:00","6 d, 07 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C2C716436541.01"]
[null,"DB Netz AG","202411.01","Löhne - Bad Bentheim","< >","Bad Bentheim","Bad Bentheim Gr",2018,2018,14,15,"03.04.2018","22:00:00","09.04.2018","08:00:00","2 d, 12 h","abends, nachts, morgens/\nat night, morning, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 22:00-08:00 ",null,null,"1C60F43B13521.01"]
[null,"DB Netz AG","20178","Löhne - Bad Bentheim",">","Schüttorf","Bad Bentheim",2018,2018,14,15,"03.04.2018","22:00:00","09.04.2018","08:00:00","2 d, 12 h","abends, nachts, morgens/\nat night, morning, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-08:00 ",null,null,"1C60F43B13521.02"]
[null,"DB Netz AG","202412.01","Löhne - Bad Bentheim","< >","Bad Bentheim","Bad Bentheim Gr",2018,2018,16,16,"21.04.2018","23:30:00","22.04.2018","07:20:00","8 h","night time, morgens/\nmorning","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C60F5E0FB221.01"]
[null,"DB Netz AG","1CAFA1D5D6A21.01","Löhne - Bad Bentheim","< >","Bad Bentheim Gr","Bad Bentheim",2018,2018,22,22,"02.06.2018","23:30:00","03.06.2018","05:20:00","6 h","night time","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CAFA1D5D6A21.01"]
[null,"DB Netz AG","202415.01","Löhne - Bad Bentheim","< >","Bad Bentheim Gr","Bad Bentheim",2018,2018,27,27,"07.07.2018","23:30:00","08.07.2018","05:20:00","6 h","night time","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CAFAA94C7941.01"]
[null,"DB Netz AG","303110.02","Oberhausen - Hannover","<","Brackwede Gbf","Brake (b Bielef)",2018,2018,4,10,"26.01.2018","22:30:00","05.03.2018","05:20:00","13 d, 17 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"Fr-So/FSSu",null,null,"1C48003D11D9F.02"]
[null,"DB Netz AG","303141.03","Oberhausen - Hannover","< >","Brackwede","Herford",2018,2018,10,11,"09.03.2018","22:00:00","12.03.2018","06:00:00","1 d","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"Fr-So/FSSu, jeweils/each 22:00-06:00 ",null,null,"1C49B02DFC47F.03"]
[null,"DB Netz AG","103054.04","Oberhausen - Hannover","< >","Gütersloh Hbf","Brackwede",2018,2018,11,11,"12.03.2018","02:00:00","12.03.2018","10:00:00","8 h","nachts, morgens/\nat night, morning","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C4A088A482DF.04"]
[null,"DB Netz AG","303146.03","Oberhausen - Hannover","< >","Brackwede Gbf","Herford",2018,2018,11,13,"17.03.2018","22:00:00","26.03.2018","06:00:00","1 d, 08 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"Sa+So/SSu, jeweils/each 22:00-06:00 ",null,null,"1C49B3078BDBF.03"]
[null,"DB Netz AG","20508","Oberhausen - Hannover","< >","Löhne(Westf) Gbf","Löhne(Westf) Gbf",2018,2018,21,29,"22.05.2018","07:00:00","20.07.2018","16:00:00","59 d, 09 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1CA6AC70A725A.01"]
[null,"DB Netz AG","202276.01","Oberhausen - Hannover",">","Vennebeck","Gohfeld",2018,2018,22,23,"02.06.2018","22:00:00","04.06.2018","06:00:00","16 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"1CAE0657D49BA.01"]
[null,"DB Netz AG","202277.01","Oberhausen - Hannover",">","Vennebeck","Gohfeld",2018,2018,23,24,"09.06.2018","22:00:00","11.06.2018","06:00:00","16 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"1CAE071321D3A.01"]
[null,"DB Netz AG","302209.02","Oberhausen - Hannover","< >","Löhne(Westf) Gbf","Löhne(Westf) Gbf",2018,2018,24,27,"14.06.2018","23:59:00","04.07.2018","05:00:00","19 d, 05 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1CA82B107253A.02"]
[null,"DB Netz AG","302209.04","Oberhausen - Hannover","< >","Löhne(Westf) Pbf","Herford",2018,2018,24,27,"14.06.2018","23:59:00","04.07.2018","05:00:00","19 d, 05 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CA82B107253A.04"]
[null,"DB Netz AG","202278.01","Oberhausen - Hannover",">","Vennebeck","Gohfeld",2018,2018,24,26,"15.06.2018","12:00:00","27.06.2018","12:00:00","12 d","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1CAE07CEB849A.01"]
[null,"DB Netz AG","202180.01","Oberhausen - Hannover","< >","Löhne(Westf) Gbf","Löhne(Westf) Gbf",2018,2018,25,27,"24.06.2018","00:00:00","02.07.2018","04:00:00","1 d, 08 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung mit BR und PSS/\n","X",null,null,null,null,null,null,null,null,null,"(Sa)/MTWThFSu, jeweils/each 00:00-04:00 ",null,null,"1CA81E25AD1FA.01"]
[null,"DB Netz AG","302212.02","Oberhausen - Hannover","< >","Löhne(Westf) Pbf","Löhne(Westf) Pbf",2018,2018,25,27,"24.06.2018","00:00:00","02.07.2018","04:00:00","1 d, 08 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung mit BR, PSS und TE/\n","X",null,null,null,null,null,null,null,null,null,"(Sa)/MTWThFSu, jeweils/each 00:00-04:00 ",null,null,"1CA8233B27D5A.02"]
[null,"DB Netz AG","202280.01","Oberhausen - Hannover","< >","Bad Oeynhsn Gbf","Bad Oeynhsn Gbf",2018,2018,26,26,"29.06.2018","22:00:00","30.06.2018","06:15:00","8 h","abends, nachts, morgens/\nat night, morning, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CAE08CC9685A.01"]
[null,"DB Netz AG","202281.01","Oberhausen - Hannover","< >","Bad Oeynhsn Gbf","Bad Oeynhsn Gbf",2018,2018,27,27,"06.07.2018","22:00:00","08.07.2018","05:00:00","1 d, 07 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CAE09DAF463A.01"]
[null,"DB Netz AG","202282.01","Oberhausen - Hannover","< >","Bad Oeynhsn Gbf","Bad Oeynhsn Gbf",2018,2018,28,28,"13.07.2018","22:00:00","15.07.2018","05:00:00","1 d, 07 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CAE0C059C93A.01"]
[null,"DB Netz AG","202284.01","Oberhausen - Hannover","< >","Bad Oeynhsn Gbf","Bad Oeynhsn Gbf",2018,2018,29,29,"20.07.2018","15:50:00","21.07.2018","22:50:00","1 d, 07 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CAE0D85A801A.01"]
[null,"DB Netz AG","202285.01","Oberhausen - Hannover","< >","Bad Oeynhsn Gbf","Bad Oeynhsn Gbf",2018,2018,32,32,"10.08.2018","22:00:00","11.08.2018","15:00:00","17 h","abends, nachts, morgens, nachmittags/\nat night, morning, afternoon, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CAE0E53BECBA.01"]
[null,"DB Netz AG","202286.01","Oberhausen - Hannover","< >","Bad Oeynhsn Gbf","Bad Oeynhsn Gbf",2018,2018,34,34,"26.08.2018","05:00:00","26.08.2018","21:00:00","16 h","tagsüber/\nduring the day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CAE10238461A.01"]
[null,"DB Netz AG","102031.02","Wilhelmshaven - Bremen","< >","Brm Hbf ehem Bwn","Bremen Hbf",2018,2018,13,14,"29.03.2018","22:00:00","03.04.2018","05:00:00","4 d, 07 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n","X",null,null,null,null,null,null,null,null,null,null,null,null,"19EF7E78D059A.02"]
[null,"DB Netz AG","20432","Wilhelmshaven - Bremen","< >","Bremen Hbf","Brm Hbf ehem Bwn",2018,2018,18,18,"05.05.2018","00:20:00","06.05.2018","05:20:00","10 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung mit PSS/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:20-05:20 ",null,null,"1C99F79365FBA.01"]
[null,"DB Netz AG","1C4DD330FE461.01","Wilhelmshaven - Bremen","< >","Delmenhorst Df","Delmenhorst Df",2018,2018,34,34,"20.08.2018","07:00:00","23.08.2018","15:00:00","1 d, 08 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-15:00 ",null,null,"1C4DD330FE461.01"]
[null,"DB Netz AG","20177, 20178","Löhne - Bad Bentheim","< >","Rheine","Rheine",2018,2018,11,15,"12.03.2018","07:00:00","09.04.2018","16:00:00","28 d, 09 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2AFC9697141.01"]
[null,"DB Netz AG","20178","Löhne - Bad Bentheim","< >","Salzbergen","Salzbergen",2018,2018,13,15,"26.03.2018","07:00:00","09.04.2018","08:00:00","14 d, 01 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2C7D3E22E61.04"]
[null,"DB Netz AG","302127.01","Löhne - Bad Bentheim","< >","Rheine","Rheine",2018,2018,13,15,"29.03.2018","07:00:00","13.04.2018","14:00:00","15 d, 07 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2AFD3748C61.01"]
[null,"DB Netz AG","302127.02","Löhne - Bad Bentheim","< >","Rheine","Rheine",2018,2018,13,15,"29.03.2018","07:00:00","13.04.2018","14:00:00","15 d, 07 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2AFD3748C61.02"]
[null,"DB Netz AG","302127.03","Löhne - Bad Bentheim","< >","Rheine","Rheine",2018,2018,13,13,"29.03.2018","22:00:00","31.03.2018","06:00:00","1 d, 08 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2AFD3748C61.03"]
[null,"DB Netz AG","302129.01","Löhne - Bad Bentheim","< >","Rheine","Rheine",2018,2018,13,14,"31.03.2018","06:00:00","03.04.2018","01:00:00","2 d, 19 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2AFD8B04521.01"]
[null,"DB Netz AG","20178","Löhne - Bad Bentheim","< >","Salzbergen","Salzbergen",2018,2018,14,15,"02.04.2018","07:00:00","09.04.2018","16:00:00","7 d, 09 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2C7D3E22E61.03"]
[null,"DB Netz AG","20178","Löhne - Bad Bentheim","< >","Salzbergen","Salzbergen",2018,2018,14,15,"03.04.2018","01:00:00","09.04.2018","08:00:00","6 d, 07 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2C7D3E22E61.05"]
[null,"DB Netz AG","302133.02","Löhne - Bad Bentheim","< >","Salzbergen","Salzbergen",2018,2018,14,15,"03.04.2018","01:00:00","09.04.2018","08:00:00","6 d, 07 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2C716436541.02"]
[null,"DB Netz AG","202169.01","Löhne - Bad Bentheim","< >","Rheine","Rheine",2018,2018,15,15,"09.04.2018","07:00:00","11.04.2018","19:00:00","2 d, 12 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2AFFF4E7081.01"]
[null,"DB Netz AG","20178","Löhne - Bad Bentheim","< >","Rheine","Rheine",2018,2018,15,15,"11.04.2018","19:00:00","13.04.2018","14:00:00","1 d, 19 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2AFFF4E7081.02"]
[null,"DB Netz AG","1CAFADC350161.01","Löhne - Bad Bentheim","< >","Rheine","Rheine",2018,2018,26,26,"25.06.2018","08:00:00","27.06.2018","16:00:00","1 d","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 08:00-16:00 ",null,null,"1CAFADC350161.01"]
[null,"DB Netz AG","202382.01","Löhne - Bad Bentheim","<","Emsdetten","Rheine",2018,2018,44,45,"04.11.2018","22:45:00","09.11.2018","05:20:00","1 d, 09 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:45-05:20 ",null,null,"1CB0C618ED281.01"]
[null,"DB Netz AG","202382.02","Löhne - Bad Bentheim","<","Emsdetten","Rheine",2018,2018,45,46,"11.11.2018","22:45:00","13.11.2018","05:20:00","13 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:45-05:20 ",null,null,"1CB0C618ED281.02"]
[null,"DB Netz AG","202314.01","Wilhelmshaven - Bremen","<","Rastede","Oldb (Oldb) Hbf",2018,2018,14,17,"07.04.2018","05:00:00","29.04.2018","23:59:00","7 d, 04 h","ganztags/\nfull day","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,null,null,null,null,null,"Sa+So/SSu",null,null,"1C2C8FEA248A1.01"]
[null,"DB Netz AG","20365","Wilhelmshaven - Bremen","< >","Rastede","Jaderberg",2018,2018,17,17,"23.04.2018","23:00:00","27.04.2018","05:00:00","1 d","nachts/\nat night","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1C812DD5AF95C.02"]
[null,"DB Netz AG","20365","Wilhelmshaven - Bremen","<","Jaderberg","Rastede",2018,2018,17,17,"27.04.2018","05:00:00","28.04.2018","05:00:00","1 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C8558100DF1C.05"]
[null,"DB Netz AG","202512.01","Wilhelmshaven - Bremen","< >","Varel (Oldb)","Sande",2018,2018,17,18,"28.04.2018","05:00:00","01.05.2018","09:00:00","3 d, 04 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C86FCFCAB4DC.01"]
[null,"DB Netz AG","20365","Wilhelmshaven - Bremen","< >","Rastede","Jaderberg",2018,2018,17,18,"28.04.2018","05:00:00","01.05.2018","23:00:00","3 d, 18 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C8558100DF1C.01"]
[null,"DB Netz AG","1C99AEF660E14.02","Hannover - Magdeburg","< >","Hannover Hbf","Hannover Hbf",2018,2018,29,30,"21.07.2018","16:40:00","23.07.2018","04:40:00","1 d, 12 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C99AEF660E14.02"]
[null,"DB Netz AG","20308","Wilhelmshaven - Bremen","< >","Weißer Floh","Wilhhv Ölweiche",2018,2018,16,16,"22.04.2018","05:00:00","22.04.2018","23:50:00","19 h","ganztags/\nfull day","Schleifen von Schienen/\nrail grinding","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C55843B78AE1.01"]
[null,"DB Netz AG","202486.01","Wilhelmshaven - Bremen","< >","Weißer Floh","Wilhhv Ölweiche",2018,2018,17,18,"28.04.2018","05:00:00","02.05.2018","04:00:00","3 d, 23 h","ganztags/\nfull day","Durchlassarbeiten/\npassage work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C70D8453F141.01"]
[null,"DB Netz AG","303418.01","Emmerich - Oberhausen","<","Mehrhoog","Empel-Rees",2017,2017,50,50,"11.12.2017","04:10:00","17.12.2017","23:45:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1C7C899C4C20D.01"]
[null,"DB Netz AG","303418.02","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2017,2017,50,50,"16.12.2017","23:45:00","17.12.2017","06:05:00","6 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,"X","1C7C899C4C20D.02"]
[null,"DB Netz AG","30136","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,11,12,"16.03.2018","23:45:00","19.03.2018","04:10:00","2 d, 04 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BF70B87C498D.01"]
[null,"DB Netz AG","303142.01","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,11,12,"16.03.2018","23:45:00","19.03.2018","04:10:00","2 d, 04 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,"X","1C7C9FE9C138D.01"]
[null,"DB Netz AG","303218.01","Emmerich - Oberhausen","<","Mehrhoog","Empel-Rees",2018,2018,21,21,"21.05.2018","08:30:00","25.05.2018","14:00:00","1 d, 04 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 08:30-14:00 ",null,"X","1C7CA6B0C642D.01"]
[null,"DB Netz AG","303218.02","Emmerich - Oberhausen","<","Mehrhoog","Empel-Rees",2018,2018,21,21,"21.05.2018","23:30:00","25.05.2018","04:30:00","20 h","nachts/\nat night","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:30-04:30 ",null,"X","1C7CA6B0C642D.02"]
[null,"DB Netz AG","303298.01","Emmerich - Oberhausen",">","Empel-Rees","Mehrhoog",2018,2018,30,30,"23.07.2018","08:30:00","27.07.2018","14:00:00","1 d, 04 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 08:30-14:00 ",null,"X","1C7CEA95F738D.01"]
[null,"DB Netz AG","30734","Emmerich - Oberhausen",">","Empel-Rees","Mehrhoog",2018,2018,30,30,"23.07.2018","23:30:00","27.07.2018","04:30:00","20 h","nachts/\nat night","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:30-04:30 ",null,null,"1C7CEA95F738D.04"]
[null,"DB Netz AG","203161.01","Emmerich - Oberhausen","< >","Dinslaken","Ob-Sterkrade",2018,2018,37,37,"15.09.2018","00:20:00","16.09.2018","00:20:00","1 d","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C3881B5309CD.01"]
[null,"DB Netz AG","30492","Aachen - Oberhausen","<","Rheydt Gbf","Baal Gbf",2018,2018,21,23,"27.05.2018","23:30:00","08.06.2018","04:30:00","2 d, 12 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:30-04:30 ",null,null,"1C2B0D67C2437.01"]
[null,"DB Netz AG","303282.01","Aachen - Oberhausen","< >","Baal Gbf","Rheydt Gbf",2018,2018,28,35,"13.07.2018","23:30:00","27.08.2018","04:30:00","9 d, 09 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:30-04:30 ",null,null,"1C2B2D5BB5A57.01"]
[null,"DB Netz AG","303282.02","Aachen - Oberhausen",">","Baal Gbf","Rheydt Gbf",2018,2018,28,32,"14.07.2018","04:30:00","10.08.2018","23:30:00","27 d, 19 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2B2D5BB5A57.02"]
[null,"DB Netz AG","303282.04","Aachen - Oberhausen","<","Rheydt Gbf","Baal Gbf",2018,2018,32,36,"11.08.2018","04:30:00","03.09.2018","04:30:00","23 d","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2B2D5BB5A57.04"]
[null,"DB Netz AG","303305.01","Aachen - Oberhausen","<","Rheydt Gbf","Baal Gbf",2018,2018,32,36,"11.08.2018","04:30:00","03.09.2018","04:30:00","23 d","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2B2E986CBF7.01"]
[null,"DB Netz AG","203131.05","Oberhausen - Hannover",">","Oberaden","Bergkamen",2018,2018,14,14,"03.04.2018","20:00:00","06.04.2018","06:00:00","1 d, 06 h","abends, nachts/\nat night, evening","Arbeiten am Bahnübergang/\nrailroad crossing work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 20:00-06:00 ",null,null,"1C68860007423.05"]
[null,"DB Netz AG","203131.02","Oberhausen - Hannover","<","Bergkamen","Oberaden",2018,2018,14,15,"07.04.2018","20:00:00","10.04.2018","06:00:00","1 d, 06 h","abends, nachts/\nat night, evening","Arbeiten am Bahnübergang/\nrailroad crossing work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 20:00-06:00 ",null,null,"1C68860007423.02"]
[null,"DB Netz AG","203131.03","Oberhausen - Hannover",">","Oberaden","Bergkamen",2018,2018,15,16,"14.04.2018","20:00:00","19.04.2018","06:00:00","2 d, 02 h","abends, nachts/\nat night, evening","Arbeiten am Bahnübergang/\nrailroad crossing work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 20:00-06:00 ",null,null,"1C68860007423.03"]
[null,"DB Netz AG","203131.04","Oberhausen - Hannover","<","Bergkamen","Oberaden",2018,2018,16,17,"21.04.2018","20:00:00","26.04.2018","06:00:00","2 d, 02 h","abends, nachts/\nat night, evening","Arbeiten am Bahnübergang/\nrailroad crossing work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 20:00-06:00 ",null,null,"1C68860007423.04"]
[null,"DB Netz AG","303196.01","Oberhausen - Hannover","< >","Gladbeck West","Gladbeck West",2018,2018,17,21,"28.04.2018","07:00:00","22.05.2018","10:00:00","24 d, 03 h","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C6873AA3B454.01"]
[null,"DB Netz AG","303196.02","Oberhausen - Hannover","< >","Recklinghsn Ost","Recklinghsn Ost",2018,2018,17,21,"28.04.2018","07:00:00","22.05.2018","10:00:00","24 d, 03 h","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C6873AA3B454.02"]
[null,"DB Netz AG","203316.01","Oberhausen - Hannover","< >","Westerholt","Blumenthal",2018,2018,17,19,"29.04.2018","00:30:00","07.05.2018","00:30:00","8 d","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C3DCBCFC9694.01"]
[null,"DB Netz AG","303198.01","Oberhausen - Hannover","< >","Gladbeck West","Gladbeck West",2018,2018,17,21,"29.04.2018","00:30:00","22.05.2018","04:30:00","23 d, 04 h","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C687641CC514.01"]
[null,"DB Netz AG","303198.05","Oberhausen - Hannover","< >","Gladbeck West","Recklinghsn Ost",2018,2018,17,21,"29.04.2018","00:30:00","22.05.2018","04:30:00","23 d, 04 h","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C687641CC514.05"]
[null,"DB Netz AG","203182.01","Oberhausen - Hannover","< >","Westerholt","Blumenthal",2018,2018,20,21,"16.05.2018","23:30:00","22.05.2018","04:30:00","5 d, 05 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CA5350C9B114.01"]
[null,"DB Netz AG","203183.01","Oberhausen - Hannover","< >","Westerholt","Blumenthal",2018,2018,27,27,"07.07.2018","14:00:00","07.07.2018","22:00:00","8 h","nachmittags, abends/\nafternoon, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CA5359DD9AF4.01"]
[null,"DB Netz AG","203302.01","Oberhausen - Hannover","< >","Westerholt","Blumenthal",2018,2018,34,35,"25.08.2018","22:30:00","29.08.2018","04:30:00","3 d, 06 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C3DCC2247934.01"]
[null,"DB Netz AG","203184.01","Oberhausen - Hannover","< >","Westerholt","Blumenthal",2018,2018,37,39,"15.09.2018","14:00:00","24.09.2018","04:00:00","4 d, 04 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"Sa-Mo/MSSu",null,null,"1CA535F0A1174.01"]
[null,"DB Netz AG","31040","Oberhausen - Hannover",">","Ruhrtal","Mathilde",2018,2018,40,41,"07.10.2018","22:00:00","14.10.2018","05:00:00","2 d, 01 h","abends, nachts/\nat night, evening","Schienenerneuerung/\nrail renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1CA6D6696A3C3.01"]
[null,"DB Netz AG","31040","Oberhausen - Hannover",">","Ruhrtal","Mathilde",2018,2018,41,41,"11.10.2018","22:00:00","14.10.2018","05:00:00","21 h","abends, nachts/\nat night, evening","Schienenerneuerung/\nrail renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1CA6D6696A3C3.02"]
[null,"DB Netz AG","203318.03","Oberhausen - Hannover",">","Ruhrtal","Mathilde",2018,2018,41,42,"14.10.2018","22:00:00","21.10.2018","22:00:00","7 d","ganztags/\nfull day","Schienenerneuerung/\nrail renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1CA6D6696A3C3.03"]
[null,"DB Netz AG","31040","Oberhausen - Hannover",">","Ruhrtal","Mathilde",2018,2018,42,42,"20.10.2018","22:00:00","21.10.2018","22:00:00","1 d","ganztags/\nfull day","Schienenerneuerung/\nrail renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1CA6D6696A3C3.04"]
[null,"DB Netz AG","31040","Oberhausen - Hannover",">","Ruhrtal","Mathilde",2018,2018,42,43,"21.10.2018","22:00:00","24.10.2018","05:00:00","21 h","abends, nachts/\nat night, evening","Schienenerneuerung/\nrail renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1CA6D68EFD603.02"]
[null,"DB Netz AG","31040","Oberhausen - Hannover",">","Ruhrtal","Mathilde",2018,2018,42,43,"21.10.2018","22:00:00","28.10.2018","05:00:00","2 d, 01 h","abends, nachts/\nat night, evening","Schienenerneuerung/\nrail renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1CA6D68EFD603.03"]
[null,"DB Netz AG","103093.01","Aachen - Oberhausen","< >","Viersen","Krefeld Hbf",2018,2018,10,11,"09.03.2018","12:00:00","12.03.2018","04:40:00","2 d, 17 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C370E009CEB7.01"]
[null,"DB Netz AG","30924","Aachen - Oberhausen",">","Viersen","Krefeld Hbf",2018,2018,13,14,"31.03.2018","22:00:00","08.04.2018","05:20:00","1 d, 05 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"Do+Sa+So/ThSSu, jeweils/each 22:00-05:20 ",null,null,"1C38810AF4D37.01"]
[null,"DB Netz AG","30924","Aachen - Oberhausen",">","Viersen","Krefeld Hbf",2018,2018,16,16,"19.04.2018","22:00:00","21.04.2018","05:20:00","15 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:20 ",null,null,"1C38810AF4D37.02"]
[null,"DB Netz AG","30924","Aachen - Oberhausen","<","Krefeld Hbf","Viersen",2018,2018,16,17,"21.04.2018","22:00:00","23.04.2018","05:20:00","15 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:20 ",null,null,"1C38810AF4D37.03"]
[null,"DB Netz AG","30924","Aachen - Oberhausen","<","Krefeld Hbf","Viersen",2018,2018,18,18,"30.04.2018","22:00:00","04.05.2018","05:20:00","1 d, 05 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:20 ",null,null,"1C38810AF4D37.04"]
[null,"DB Netz AG","31136","Aachen - Oberhausen",">","Viersen","Krefeld Hbf",2018,2018,21,22,"27.05.2018","22:00:00","30.05.2018","05:20:00","22 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:20 ",null,null,"1C388322BB077.01"]
[null,"DB Netz AG","31136","Aachen - Oberhausen","<","Krefeld Hbf","Viersen",2018,2018,22,22,"30.05.2018","22:00:00","02.06.2018","05:20:00","22 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:20 ",null,null,"1C388322BB077.03"]
[null,"DB Netz AG","203197.01","Aachen - Oberhausen","< >","Viersen","Krefeld Hbf",2018,2018,44,45,"02.11.2018","12:00:00","05.11.2018","04:40:00","2 d, 17 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C388014560F7.01"]
[null,"DB Netz AG","30606","Oberhausen - Hannover","< >","Bottrop Süd","Bottrop Süd",2018,2018,25,25,"24.06.2018","06:00:00","24.06.2018","18:00:00","12 h","nachts, morgens, nachmittags/\nat night, morning, afternoon","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2F73A4ACE54.01"]
[null,"DB Netz AG","30057","Aachen - Oberhausen","< >","Oberh West Stw 1","Du-Meiderich Ost",2018,2018,5,7,"29.01.2018","20:00:00","17.02.2018","05:00:00","5 d, 15 h","abends, nachts/\nat night, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work","X",null,null,null,null,null,null,null,null,null,"Mo-Fr/MTWThF, jeweils/each 20:00-05:00 ",null,null,"1BDE25A30A2CD.02"]
[null,"DB Netz AG","304055.01","Falkenberg - Horka","< >","Bad Schandau Ost","Bad Schandau Ost",2018,2018,6,49,"09.02.2018","05:00:00","05.12.2018","10:00:00","199 d, 11 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,"unterbr./discontinuous",null,null,"1C2B784D595C7.01"]
[null,"DB Netz AG","304055.02","Falkenberg - Horka","< >","Bad Schandau","Bad Schandau",2018,2018,6,49,"09.02.2018","05:00:00","05.12.2018","10:00:00","299 d, 05 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2B784D595C7.03"]
[null,"DB Netz AG","304055.03","Falkenberg - Horka","< >","Pirna Gbf","Pirna Gbf",2018,2018,6,49,"09.02.2018","05:00:00","05.12.2018","10:00:00","299 d, 05 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2B784D595C7.04"]
[null,"DB Netz AG","304053.03","Falkenberg - Horka","< >","Pirna","Bad Schandau",2018,2018,6,6,"09.02.2018","23:50:00","11.02.2018","23:50:00","2 d","ganztags/\nfull day","Gleisumbau ohne Schienenwechsel/\n","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C2B6454FCB67.03"]
[null,"DB Netz AG","104004.01","Falkenberg - Horka","< >","Cossebaude","Dre Freibg Str",2018,2018,9,10,"03.03.2018","20:00:00","05.03.2018","04:00:00","1 d, 08 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C33F17EA6707.01"]
[null,"DB Netz AG","104006.01","Falkenberg - Horka","< >","Dre-Friedrichst","Dre Freibg Str",2018,2018,10,10,"08.03.2018","20:00:00","09.03.2018","16:00:00","20 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C341A8652DE7.01"]
[null,"DB Netz AG","40067","Falkenberg - Horka","<","Kurort Rathen","Obervogelgesang",2018,2018,12,12,"20.03.2018","22:05:00","23.03.2018","05:05:00","21 h","nachts/\nat night","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:05-05:05 ",null,null,"1C3416FEB72ED.01"]
[null,"DB Netz AG","40067","Falkenberg - Horka",">","Obervogelgesang","Kurort Rathen",2018,2018,13,13,"26.03.2018","22:05:00","29.03.2018","05:05:00","21 h","nachts/\nat night","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:05-05:05 ",null,null,"1C3416FEB72ED.02"]
[null,"DB Netz AG","40068","Falkenberg - Horka","<","Kurort Rathen","Kurort Rathen",2018,2018,14,19,"03.04.2018","01:00:00","10.05.2018","04:00:00","37 d, 03 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C34134678C4D.05"]
[null,"DB Netz AG","40273","Falkenberg - Horka","< >","Dre-Reick Abstbf","Dre-Friedrichst",2018,2018,15,15,"14.04.2018","20:00:00","15.04.2018","04:00:00","8 h","abends, nachts/\nat night, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C7B31166570C.02"]
[null,"DB Netz AG","40069, 40068","Falkenberg - Horka","< >","Bad Schandau","Pirna",2018,2018,19,19,"09.05.2018","22:00:00","10.05.2018","04:00:00","6 h","abends, nachts/\nat night, evening","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C341D7BD352D.02"]
[null,"DB Netz AG","40346","Falkenberg - Horka",">","Pirna","Obervogelgesang",2018,2018,20,20,"14.05.2018","22:00:00","17.05.2018","05:00:00","21 h","abends, nachts/\nat night, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1C7B10610A10D.01"]
[null,"DB Netz AG","40346","Falkenberg - Horka","<","Obervogelgesang","Pirna",2018,2018,20,20,"17.05.2018","22:00:00","19.05.2018","05:00:00","14 h","abends, nachts/\nat night, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1C7B1195BE62D.01"]
[null,"DB Netz AG","304147.01","Falkenberg - Horka","<","Obervogelgesang","Pirna",2018,2018,21,25,"22.05.2018","04:00:00","24.06.2018","01:00:00","32 d, 21 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1C7B1E09AFAAD.01"]
[null,"DB Netz AG","304147.03","Falkenberg - Horka","< >","Pirna","Obervogelgesang",2018,2018,22,23,"29.05.2018","00:00:00","08.06.2018","04:00:00","1 d, 20 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung mit BR, PSS und TE/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:00 ",null,null,"1C7B1E09AFAAD.03"]
[null,"DB Netz AG","40348","Falkenberg - Horka",">","Pirna","Obervogelgesang",2018,2018,25,26,"24.06.2018","22:00:00","27.06.2018","05:00:00","21 h","abends, nachts/\nat night, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1C7B295EAB08D.01"]
[null,"DB Netz AG","204114.01","Falkenberg - Horka","<","Kurort Rathen","Pirna",2018,2018,37,37,"12.09.2018","22:00:00","14.09.2018","05:00:00","14 h","abends, nachts/\nat night, evening","Durcharbeitung von Gleisen/\ntrackage maintenance",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1C7B2B6D7A50D.01"]
[null,"DB Netz AG","304239.01","Hannover - Magdeburg",">","Magdeburg Hbf","Helmstedt",2018,2018,40,42,"01.10.2018","22:00:00","15.10.2018","05:00:00","4 d, 02 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1C8B5949C08DF.01"]
[null,"DB Netz AG","304112.04","Magdeburg - Falkenberg","< >","Königsborn","Königsborn",2018,2018,15,16,"12.04.2018","04:30:00","21.04.2018","22:00:00","9 d, 17 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,null,null,"X",null,null,null,null,null,null,null,null,null,"1C61015FBA4BF.04"]
[null,"DB Netz AG","304112.02","Magdeburg - Falkenberg","< >","Königsborn","Königsborn",2018,2018,15,20,"12.04.2018","04:30:00","19.05.2018","22:00:00","37 d, 17 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C61015FBA4BF.02"]
[null,"DB Netz AG","204170.02","Magdeburg - Falkenberg","< >","Königsborn","Königsborn",2018,2018,15,16,"12.04.2018","06:30:00","21.04.2018","21:30:00","6 d, 06 h","tagsüber/\nduring the day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 06:30-21:30 ",null,null,"1C610034F109F.02"]
[null,"DB Netz AG","204170.03","Magdeburg - Falkenberg","< >","Königsborn","Königsborn",2018,2018,16,16,"21.04.2018","23:55:00","22.04.2018","06:00:00","6 h","night time","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C610034F109F.03"]
[null,"DB Netz AG","304112.05","Magdeburg - Falkenberg","< >","Königsborn","Königsborn",2018,2018,16,18,"22.04.2018","06:00:00","02.05.2018","00:10:00","9 d, 18 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,null,null,"X",null,null,null,null,null,null,null,null,null,"1C61015FBA4BF.05"]
[null,"DB Netz AG","304131.01","Magdeburg - Falkenberg","< >","Biederitz","Biederitz",2018,2018,18,20,"30.04.2018","08:00:00","19.05.2018","22:00:00","19 d, 14 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C610615EF5BF.01"]
[null,"DB Netz AG","304131.02","Magdeburg - Falkenberg","< >","Biederitz","Königsborn",2018,2018,18,20,"02.05.2018","00:10:00","19.05.2018","22:00:00","17 d, 22 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C610615EF5BF.02"]
[null,"DB Netz AG","304132.01","Magdeburg - Falkenberg","< >","Biederitz","Rodleben",2018,2018,18,25,"02.05.2018","00:10:00","22.06.2018","22:00:00","51 d, 22 h","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C610B82DDC3F.01"]
[null,"DB Netz AG","1C745F729E723.01","Magdeburg - Falkenberg","<","Roßlau (Elbe)","Rodleben",2018,2018,18,25,"02.05.2018","08:00:00","22.06.2018","18:00:00","51 d, 10 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C745F729E723.01"]
[null,"DB Netz AG","1C7F7E608DB3F.01","Magdeburg - Falkenberg","< >","Biederitz","Güterglück",2018,2018,32,33,"10.08.2018","08:00:00","19.08.2018","20:00:00","5 d","ganztags/\nfull day","Durcharbeitung von Weichen/\nswitch maintenance",null,"X",null,null,null,null,null,null,null,null,"Fr-So/FSSu",null,null,"1C7F7E608DB3F.01"]
[null,"DB Netz AG","204172.04","Magdeburg - Falkenberg","< >","Biederitz","Rodleben",2018,2018,32,33,"11.08.2018","04:30:00","19.08.2018","17:00:00","3 d, 01 h","ganztags/\nfull day","Durcharbeitung von Weichen/\nswitch maintenance","X",null,null,null,null,null,null,null,null,null,"Sa+So/SSu",null,null,"1C7F7E608DB3F.04"]
[null,"DB Netz AG","204163.03","Falkenberg - Bad Schandau","< >","Dresden Hbf","Dre-Neustadt",2018,2018,15,15,"14.04.2018","20:00:00","15.04.2018","04:00:00","8 h","abends, nachts/\nat night, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C7B31166570C.03"]
[null,"DB Netz AG","1C745F729E723.02","Magdeburg - Falkenberg","< >","Rodleben","Roßlau(Elbe) Gbf",2018,2018,18,25,"02.05.2018","08:00:00","22.06.2018","18:00:00","51 d, 10 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C745F729E723.02"]
[null,"DB Netz AG","304101.01","Falkenberg - Horka","< >","Horka Gbf","Horka Gbf",2018,2018,14,26,"03.04.2018","07:00:00","30.06.2018","17:00:00","88 d, 10 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1C76F2114902C.01"]
[null,"DB Netz AG","304101.02","Falkenberg - Horka",">","Horka Grenze","Horka Gbf",2018,2018,14,26,"03.04.2018","07:00:00","30.06.2018","17:00:00","88 d, 10 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1C76F2114902C.02"]
[null,"DB Netz AG","304130.01","Falkenberg - Horka","< >","Horka Gbf","Horka Gbf",2018,2018,18,20,"30.04.2018","07:00:00","18.05.2018","17:00:00","6 d, 06 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"Mo-Fr/MTWThF, jeweils/each 07:00-17:00 ",null,null,"1C76F3966262C.01"]
[null,"DB Netz AG","304146.01","Falkenberg - Horka","< >","Horka Gbf","Horka Gbf",2018,2018,21,22,"22.05.2018","07:00:00","01.06.2018","17:00:00","3 d, 18 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"Mo-Fr/MTWThF, jeweils/each 07:00-17:00 ",null,null,"1CA870CC5EAEC.01"]
[null,"DB Netz AG","304158.01","Falkenberg - Horka","< >","Horka Gbf","Horka Gbf",2018,2018,23,23,"04.06.2018","07:00:00","10.06.2018","17:00:00","2 d, 22 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-17:00 ",null,null,"1CA87322E556C.01"]
[null,"DB Netz AG","1C745F729E723.03","Magdeburg - Falkenberg",">","Meinsdorf","Roßlau Stw Rwa",2018,2018,23,25,"04.06.2018","08:00:00","22.06.2018","18:00:00","18 d, 10 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C745F729E723.03"]
[null,"DB Netz AG","1C62AC38E0023.01","Magdeburg - Falkenberg","< >","Lu Wittenberg","Lu Wittenberg",2018,2018,24,25,"15.06.2018","22:10:00","22.06.2018","04:20:00","1 d, 19 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 22:10-04:20 ",null,null,"1C62AC38E0023.01"]
[null,"DB Netz AG","1C62AC38E0023.02","Magdeburg - Falkenberg","<","Lu Wittenberg","Elster (Elbe)",2018,2018,24,25,"15.06.2018","22:10:00","22.06.2018","04:20:00","1 d, 19 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:10-04:20 ",null,null,"1C62AC38E0023.02"]
[null,"DB Netz AG","301312.01","Berlin - Frankurt (O)","< >","Ostendgestell","Erkner",2019,2019,28,30,"12.07.2019","22:40:00","25.07.2019","04:50:00","12 d, 06 h","ganztags/\nfull day","Weicheneinbau/\nswitch mounting","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C0C90FA15911.01"]
[null,"DB Netz AG","1BD3F36778D8C.02","Magdeburg - Berlin","<","Gensh Heide Ost","Eichgestell",2019,2019,8,10,"18.02.2019","21:00:00","04.03.2019","05:00:00","4 d, 16 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 21:00-05:00 ",null,null,"1BD3F36778D8C.02"]
[null,"DB Netz AG","1BD3F3BDC792C.02","Magdeburg - Berlin","<","Gensh Heide Ost","Eichgestell",2019,2019,38,40,"16.09.2019","21:00:00","30.09.2019","05:00:00","4 d, 16 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 21:00-05:00 ",null,null,"1BD3F3BDC792C.02"]
[null,"DB Netz AG","301041.01","Magdeburg - Berlin","<","Saarmund","Gensh Heide Ost",2019,2019,8,10,"18.02.2019","21:00:00","04.03.2019","05:00:00","4 d, 16 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 21:00-05:00 ",null,null,"1BD3F36778D8C.01"]
[null,"DB Netz AG","303585.03","Emmerich - Oberhausen","< >","Oberhausen Hbf","Oberhsn Hbf Obn",2019,2019,14,14,"05.04.2019","02:00:00","07.04.2019","08:00:00","2 d, 06 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BCF879390F6A.03"]
[null,"DB Netz AG","301259.01","Berlin - Frankurt (O)",">","Rahnsdorf    Üst","Erkner",2017,2018,49,16,"10.12.2017","00:01:00","19.04.2018","22:00:00","130 d, 22 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BB2CF5FF132A.01"]
[null,"DB Netz AG","301083.01","Berlin - Frankurt (O)","< >","Bln-Köpenick","Bln-Köpenick",2017,2018,49,49,"10.12.2017","00:01:00","08.12.2018","23:59:00","364 d","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BB2D4D15B10A.01"]
[null,"DB Netz AG","301083.02","Berlin - Frankurt (O)","< >","Erkner","Erkner",2017,2018,49,49,"10.12.2017","00:01:00","08.12.2018","23:59:00","364 d","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BB2D4D15B10A.02"]
[null,"DB Netz AG","301074.01","Berlin - Frankurt (O)","< >","Erkner","Bln-Köpenick",2017,2018,49,10,"10.12.2017","22:55:00","09.03.2018","05:05:00","16 d, 17 h","nachts/\nat night","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,"So-Do/MTWThSu, jeweils/each 22:55-05:05 ",null,"X","1BB2DAD929E8A.01"]
[null,"DB Netz AG","10002","Berlin - Frankurt (O)","< >","Bln-Köpenick","Rahnsdorf    Üst",2017,2018,49,10,"10.12.2017","22:55:00","09.03.2018","05:05:00","16 d, 17 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"So-Do/MTWThSu, jeweils/each 22:55-05:05 ",null,null,"1BB3E2EF9CE2A.01"]
[null,"DB Netz AG","301088.01","Berlin - Frankurt (O)",">","Stadtforst","Frankfurt (O)",2017,2018,50,49,"13.12.2017","22:55:00","07.12.2018","05:05:00","26 d, 17 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"Mi+Do/WTh, jeweils/each 22:55-05:05 ",null,"X","1BB422DCAA02A.01"]
[null,"DB Netz AG","10053","Berlin - Frankurt (O)","< >","Bln-Köpenick","Bln-Köpenick",2018,2018,8,9,"25.02.2018","22:55:00","28.02.2018","03:55:00","15 h","nachts/\nat night","Durcharbeitung von Weichen/\nswitch maintenance","X",null,null,null,null,null,null,null,null,null,"jeweils/each 22:55-03:55 ",null,null,"1C05828CA1E0A.01"]
[null,"DB Netz AG","10061","Berlin - Frankurt (O)","<","Bln-Köpenick","Bln-Köpenick",2018,2018,9,9,"01.03.2018","06:00:00","03.03.2018","18:00:00","1 d, 12 h","nachts, nachmittags, abends/\nnachts, at night, afternoon, evening","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 06:00-18:00 ",null,null,"1C3442B0EE80A.01"]
[null,"DB Netz AG","10065\nDeleted","Berlin - Frankurt (O)","< >","Erkner","Bln-Köpenick",2018,2018,10,16,"11.03.2018","22:55:00","19.04.2018","05:05:00","10 d, 01 h","nachts/\nat night","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 22:55-05:05 ",null,null,"1C385E85A296A.03"]
[null,"DB Netz AG","10279\nDeleted","Berlin - Frankurt (O)","< >","Erkner","Rahnsdorf    Üst",2018,2018,16,17,"19.04.2018","22:00:00","29.04.2018","22:00:00","10 d","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C6CF7C16A88A.01"]
[null,"DB Netz AG","10256\nDeleted","Berlin - Frankurt (O)","< >","Berkenbrück","Berkenbrück",2018,2018,16,17,"22.04.2018","22:40:00","24.04.2018","04:40:00","12 h","nachts/\nat night","Durcharbeitung von Gleisen/\ntrackage maintenance",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:40-04:40 ",null,null,"1C74409EAD9AA.02"]
[null,"DB Netz AG","10279","Berlin - Frankurt (O)","< >","Erkner","Erkner",2018,2018,17,18,"29.04.2018","22:00:00","30.04.2018","04:00:00","6 h","abends, nachts/\nat night, evening","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,null,null,"X","1C6CF7C16A88A.02"]
[null,"DB Netz AG","10279","Berlin - Frankurt (O)","< >","Bln-Köpenick","Bln-Köpenick",2018,2018,17,18,"29.04.2018","22:00:00","30.04.2018","04:00:00","6 h","abends, nachts/\nat night, evening","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,null,null,"X","1C6CF7C16A88A.03"]
[null,"DB Netz AG","1C6CE5D86FA6A.01\nDeleted","Berlin - Frankurt (O)","<","Erkner","Rahnsdorf    Üst",2018,2018,18,48,"30.04.2018","04:00:00","30.11.2018","22:00:00","214 d, 18 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C6CE5D86FA6A.01"]
[null,"DB Netz AG","1C6CE9F68848A.01\nDeleted","Berlin - Frankurt (O)","<","Erkner","Rahnsdorf    Üst",2018,2018,18,48,"30.04.2018","04:00:00","30.11.2018","22:00:00","214 d, 18 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C6CE9F68848A.01"]
[null,"DB Netz AG","1C6CEE17F768A.01\nDeleted","Berlin - Frankurt (O)","<","Erkner","Rahnsdorf    Üst",2018,2018,18,48,"30.04.2018","04:00:00","30.11.2018","22:00:00","214 d, 18 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C6CEE17F768A.01"]
[null,"DB Netz AG","301135.01","Berlin - Frankurt (O)","< >","Bln-Köpenick","Erkner",2018,2018,18,18,"02.05.2018","20:00:00","03.05.2018","04:00:00","8 h","abends, nachts/\nat night, evening","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,"X",null,"X",null,null,null,null,"19C66FA96F38C.01"]
[null,"DB Netz AG","10303\nDeleted","Berlin - Frankurt (O)","< >","Bln-Köpenick","Erkner",2018,2018,18,18,"02.05.2018","20:00:00","03.05.2018","04:00:00","8 h","abends, nachts/\nat night, evening","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C88A1E439D0A.01"]
[null,"DB Netz AG","301135.02","Berlin - Frankurt (O)","<","Rahnsdorf    Üst","Bln-Köpenick",2018,2018,18,19,"03.05.2018","04:00:00","07.05.2018","20:00:00","4 d, 16 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,"X",null,"X",null,null,null,null,"19C66FA96F38C.02"]
[null,"DB Netz AG","10303\nDeleted","Berlin - Frankurt (O)","<","Rahnsdorf    Üst","Bln-Köpenick",2018,2018,18,19,"03.05.2018","04:00:00","07.05.2018","20:00:00","4 d, 16 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C88A1E439D0A.02"]
[null,"DB Netz AG","301135.03","Berlin - Frankurt (O)","< >","Rahnsdorf    Üst","Erkner",2018,2018,18,48,"03.05.2018","22:55:00","30.11.2018","05:05:00","38 d, 19 h","nachts/\nat night","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,"X",null,"X",null,"So-Do/MTWThSu, jeweils/each 22:55-05:05 ",null,"X","19C66FA96F38C.03"]
[null,"DB Netz AG","10303","Berlin - Frankurt (O)","< >","Rahnsdorf    Üst","Erkner",2018,2018,18,48,"03.05.2018","22:55:00","30.11.2018","05:05:00","38 d, 19 h","nachts/\nat night","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,"So-Do/MTWThSu, jeweils/each 22:55-05:05 ",null,null,"1C88A1E439D0A.03"]
[null,"DB Netz AG","301139.01","Berlin - Frankurt (O)","< >","Bln-Köpenick","Erkner",2018,2018,19,19,"07.05.2018","20:00:00","08.05.2018","04:00:00","8 h","abends, nachts/\nat night, evening","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,"X",null,"X",null,null,null,null,"19C66FAD8906C.01"]
[null,"DB Netz AG","301145.01","Berlin - Frankurt (O)","< >","Erkner","Erkner",2018,2018,20,20,"17.05.2018","06:00:00","18.05.2018","18:00:00","1 d, 12 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C66FB24DBAC.01"]
[null,"DB Netz AG","301145.02","Berlin - Frankurt (O)","<","Erkner","Bln-Köpenick",2018,2018,20,20,"17.05.2018","06:00:00","18.05.2018","18:00:00","1 d, 12 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,"X",null,"X",null,null,null,null,"19C66FB24DBAC.02"]
[null,"DB Netz AG","301257.05","Berlin - Frankurt (O)",">","Frankfurt (O)","Oderbrücke",2018,2018,23,23,"04.06.2018","06:00:00","05.06.2018","01:00:00","19 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,"X",null,null,null,null,"19F25D2F9C9D1.05"]
[null,"DB Netz AG","1C56E44C44C0A.01","Berlin - Frankurt (O)","< >","Pillgram","Frankfurt (O)",2018,2018,25,26,"24.06.2018","22:55:00","29.06.2018","05:05:00","1 d, 07 h","nachts/\nat night","Arbeiten am Bahnübergang/\nrailroad crossing work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 22:55-05:05 ",null,null,"1C56E44C44C0A.01"]
[null,"DB Netz AG","301256.03","Berlin - Frankurt (O)","<","Oderbrücke","Frankfurt (O)",2018,2018,37,37,"14.09.2018","22:00:00","16.09.2018","06:00:00","1 d, 08 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,"X",null,null,null,null,"19F2523B551B1.03"]
[null,"DB Netz AG","301256.05","Berlin - Frankurt (O)",">","Frankfurt (O)","Oderbrücke",2018,2018,37,38,"16.09.2018","06:00:00","17.09.2018","04:00:00","22 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,"X",null,null,null,null,"19F2523B551B1.05"]
[null,"DB Netz AG","301223.01","Berlin - Frankurt (O)","< >","Erkner","Stadtforst",2018,2018,48,49,"30.11.2018","22:00:00","03.12.2018","04:00:00","2 d, 06 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,"X",null,"X",null,null,null,null,"19C66FEEDCA8C.01"]
[null,"DB Netz AG","201037.01","Berlin - Frankurt (O)","< >","Erkner","Fangschleuse",2018,2018,48,48,"01.12.2018","20:00:00","02.12.2018","08:00:00","12 h","abends, nachts, morgens/\nat night, morning, evening","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,null,"X",null,"X",null,null,null,null,"19B7DA032A8B1.01"]
[null,"DB Netz AG","304038.01","Magdeburg - Berlin","<","Biederitz","Werder (Havel)",2017,2018,50,49,"12.12.2017","22:00:00","05.12.2018","05:00:00","15 d, 04 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"Di/T, jeweils/each 22:00-05:00 ",null,"X","1BD864C2B8AE3.01"]
[null,"DB Netz AG","304039.01","Magdeburg - Berlin",">","Werder (Havel)","Biederitz",2017,2018,50,49,"12.12.2017","22:00:00","05.12.2018","05:00:00","15 d, 04 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"Di/T, jeweils/each 22:00-05:00 ",null,"X","1BD864FAB3BC3.01"]
[null,"DB Netz AG","40023","Magdeburg - Berlin","< >","Mg-Neustadt","Magdeburg Hbf",2018,2018,3,4,"17.01.2018","23:45:00","22.01.2018","03:45:00","20 h","nachts/\nat night","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:45-03:45 ",null,null,"1BBB1A7A6275F.01"]
[null,"DB Netz AG","40035","Magdeburg - Berlin","< >","Mg-Neustadt","Magdeburg Hbf",2018,2018,6,6,"05.02.2018","23:45:00","10.02.2018","03:45:00","20 h","nachts/\nat night","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:45-03:45 ",null,null,"1BE6F9D311FDF.01"]
[null,"DB Netz AG","304067.01","Magdeburg - Berlin","< >","Mg-Neustadt","Magdeburg Hbf",2018,2018,9,9,"03.03.2018","00:30:00","04.03.2018","12:45:00","1 d, 12 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BF9918E25CFF.01"]
[null,"DB Netz AG","10131","Magdeburg - Berlin","<","Bln Wendenh","Eichgestell",2018,2018,14,14,"04.04.2018","15:30:00","05.04.2018","09:20:00","18 h","nachmittags, abends, nachts, morgens/\nat night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C5E1588F24FD.05"]
[null,"DB Netz AG","10131\nDeleted","Magdeburg - Berlin","<","Bln Wendenh","Eichgestell",2018,2018,14,14,"04.04.2018","15:30:00","05.04.2018","09:20:00","18 h","nachmittags, abends, nachts, morgens/\nat night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C5E27155323D.05"]
[null,"DB Netz AG","10271","Magdeburg - Berlin","<","Grün Kreuz Nord","Bln Wendenh",2018,2018,16,17,"20.04.2018","20:00:00","23.04.2018","04:00:00","2 d, 08 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C7F6F14ABDFD.03"]
[null,"DB Netz AG","201063.01","Magdeburg - Berlin","<","Gensh Heide Ost","Diedersdorf",2018,2018,25,25,"22.06.2018","22:00:00","24.06.2018","22:00:00","2 d","ganztags/\nfull day","Schienenerneuerung/\nrail renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19CC458AD8CB1.01"]
[null,"DB Netz AG","1C8486F035422.04\nDeleted","Magdeburg - Berlin","<","Eichgestell","Ostendgestell",2018,2018,28,29,"13.07.2018","23:40:00","16.07.2018","04:20:00","2 d, 05 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C8486F035422.04"]
[null,"DB Netz AG","1C84849193682.04\nDeleted","Magdeburg - Berlin","<","Eichgestell","Ostendgestell",2018,2018,28,29,"13.07.2018","23:40:00","16.07.2018","04:20:00","2 d, 05 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C84849193682.04"]
[null,"DB Netz AG","201083.01","Magdeburg - Berlin","< >","Grün Kreuz Süd","Glasow Damm Ost",2018,2018,33,33,"17.08.2018","22:00:00","18.08.2018","06:00:00","8 h","abends, nachts/\nat night, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1A081565A635D.01"]
[null,"DB Netz AG","201084.01","Magdeburg - Berlin",">","Grün Kreuz Süd","Schönefeld",2018,2018,33,33,"19.08.2018","06:00:00","19.08.2018","22:00:00","16 h","tagsüber/\nduring the day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A0944C0F857D.01"]
[null,"DB Netz AG","201084.03","Magdeburg - Berlin",">","Schönefeld","Glasow Damm Ost",2018,2018,33,33,"19.08.2018","06:00:00","19.08.2018","22:00:00","16 h","tagsüber/\nduring the day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A0944C0F857D.03"]
[null,"DB Netz AG","10137","Magdeburg - Berlin",">","Michendorf","Seddin Bla",2018,2018,14,14,"06.04.2018","07:00:00","07.04.2018","19:00:00","1 d","tagsüber/\nduring the day","Durcharbeitung von Gleisen/\ntrackage maintenance",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-19:00 ",null,null,"1C3E3DBA003FF.01"]
[null,"DB Netz AG","10137","Magdeburg - Berlin",">","Seddin Bla","Beelitz Heilst",2018,2018,14,14,"06.04.2018","07:00:00","07.04.2018","19:00:00","1 d","tagsüber/\nduring the day","Durcharbeitung von Gleisen/\ntrackage maintenance",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-19:00 ",null,null,"1C3E3DBA003FF.02"]
[null,"DB Netz AG","201049.02\nDeleted","Magdeburg - Berlin",">","Brück (Mark)","Bad Belzig",2018,2018,14,15,"08.04.2018","22:00:00","10.04.2018","06:00:00","1 d, 08 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C76D73C89BBF.02"]
[null,"DB Netz AG","201049.03\nDeleted","Magdeburg - Berlin","<","Bad Belzig","Brück (Mark)",2018,2018,15,15,"10.04.2018","22:00:00","12.04.2018","06:00:00","1 d, 08 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C76D73C89BBF.03"]
[null,"DB Netz AG","10170\nDeleted","Magdeburg - Berlin","<","Brück (Mark)","Brück (Mark)",2018,2018,15,15,"10.04.2018","22:00:00","12.04.2018","06:00:00","1 d, 08 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C76D73C89BBF.04"]
[null,"DB Netz AG","10229\nDeleted","Magdeburg - Berlin","<","Bad Belzig","Brück (Mark)",2018,2018,15,15,"11.04.2018","22:00:00","13.04.2018","06:00:00","1 d, 08 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C76DEEE295DF.03"]
[null,"DB Netz AG","10229\nDeleted","Magdeburg - Berlin",">","Brück (Mark)","Bad Belzig",2018,2018,15,16,"14.04.2018","22:00:00","16.04.2018","06:00:00","16 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"1C76DEEE295DF.05"]
[null,"DB Netz AG","201051.01","Magdeburg - Berlin","< >","Bad Belzig","Brück (Mark)",2018,2018,27,28,"06.07.2018","06:00:00","09.07.2018","04:00:00","2 d, 22 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"19C7E1761ACFF.01"]
[null,"DB Netz AG","204009.01","Magdeburg - Berlin","< >","Roßlau Stw Rwa","Dessau Gbf",2018,2018,35,36,"01.09.2018","00:00:00","08.09.2018","04:00:00","7 d, 04 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1B682C369C6EC.01"]
[null,"DB Netz AG","304212.01","Magdeburg - Berlin","< >","Roßlau (Elbe)","Dessau Gbf",2018,2018,35,36,"01.09.2018","00:00:00","08.09.2018","04:00:00","7 d, 04 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"19C6739977DCC.01"]
[null,"DB Netz AG","301181.02","Magdeburg - Berlin",">","Seddin Bla","Beelitz Heilst",2018,2018,35,36,"01.09.2018","09:00:00","08.09.2018","09:00:00","7 d","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C66FCE26A2C.02"]
[null,"DB Netz AG","301181.04","Magdeburg - Berlin","< >","Beelitz Heilst","Beelitz Heilst",2018,2018,35,36,"01.09.2018","09:00:00","08.09.2018","09:00:00","7 d","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C66FCE26A2C.05"]
[null,"DB Netz AG","304212.03","Magdeburg - Berlin",">","Roßlau (Elbe)","Dessau Gbf",2018,2018,36,38,"08.09.2018","04:00:00","20.09.2018","04:00:00","12 d","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C6739977DCC.03"]
[null,"DB Netz AG","1C5E1A0066EBF.02\nDeleted","Magdeburg - Berlin",">","Brück (Mark)","Bad Belzig",2018,2018,36,38,"08.09.2018","09:00:00","22.09.2018","09:00:00","14 d","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C5E1A0066EBF.02"]
[null,"DB Netz AG","1C5E1A0066EBF.01","Magdeburg - Berlin","< >","Bad Belzig","Brück (Mark)",2018,2018,37,38,"14.09.2018","22:00:00","17.09.2018","04:00:00","2 d, 06 h","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C5E1A0066EBF.01"]
[null,"DB Netz AG","201052.01","Magdeburg - Berlin","< >","Bad Belzig","Brück (Mark)",2018,2018,37,38,"14.09.2018","22:00:00","17.09.2018","04:00:00","2 d, 06 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"19C7E1DD3269F.01"]
[null,"DB Netz AG","304225.02","Magdeburg - Berlin","<","Dessau Gbf","Roßlau (Elbe)",2018,2018,38,40,"20.09.2018","22:00:00","03.10.2018","04:00:00","12 d, 06 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C673A501F6C.02"]
[null,"DB Netz AG","304246.01","Magdeburg - Berlin","< >","Roßlau (Elbe)","Dessau Gbf",2018,2018,42,43,"15.10.2018","00:00:00","22.10.2018","04:00:00","7 d, 04 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"19C673B3687CC.01"]
[null,"DB Netz AG","204010.01","Magdeburg - Berlin","< >","Roßlau Stw Rwa","Dessau Gbf",2018,2018,42,43,"15.10.2018","00:00:00","22.10.2018","04:00:00","7 d, 04 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1B682D65C8BCC.01"]
[null,"DB Netz AG","1C5E1F7DA421F.01","Magdeburg - Berlin","< >","Bad Belzig","Bad Belzig",2018,2018,48,48,"26.11.2018","23:00:00","30.11.2018","05:00:00","1 d","nachts/\nat night","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1C5E1F7DA421F.01"]
[null,"DB Netz AG","1C5E1F7DA421F.02","Magdeburg - Berlin",">","Brück (Mark)","Bad Belzig",2018,2018,48,48,"26.11.2018","23:00:00","30.11.2018","05:00:00","1 d","nachts/\nat night","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1C5E1F7DA421F.02"]
[null,"DB Netz AG","104008.01","Hamburg - Magdeburg","< >","Mg-Neustadt","Magdeburg Hbf",2018,2018,3,4,"17.01.2018","23:45:00","22.01.2018","03:45:00","20 h","nachts/\nat night","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:45-03:45 ",null,null,"1BBB1AF2BD01F.01"]
[null,"DB Netz AG","104010.01","Hamburg - Magdeburg","< >","Mg-Neustadt","Magdeburg Hbf",2018,2018,6,6,"05.02.2018","23:45:00","10.02.2018","03:45:00","20 h","nachts/\nat night","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:45-03:45 ",null,null,"1BE6FA9A1A23F.01"]
[null,"DB Netz AG","304067.03","Hamburg - Magdeburg","< >","Magdeburg Hbf","Mg-Neustadt",2018,2018,9,9,"03.03.2018","00:30:00","04.03.2018","12:45:00","1 d, 12 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BF9918E25CFF.03"]
[null,"DB Netz AG","304123.01","Hamburg - Magdeburg",">","Osterburg","Stendal",2018,2018,16,25,"16.04.2018","22:00:00","19.06.2018","05:00:00","18 d, 16 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1BD99E24180FF.01"]
[null,"DB Netz AG","304164.01","Hamburg - Magdeburg","<","Stendal","Osterburg",2018,2018,24,27,"15.06.2018","22:00:00","06.07.2018","05:00:00","6 d, 03 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"19C67378A96CC.01"]
[null,"DB Netz AG","10107","Magdeburg - Berlin",">","Genshagenr Heide","Genshagenr Heide",2018,2018,13,13,"29.03.2018","16:00:00","31.03.2018","16:00:00","2 d","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C1B13A3C1A5F.01"]
[null,"DB Netz AG","301182.03","Magdeburg - Berlin","< >","Seddin Bla","Lienewitz (Lia)",2018,2018,35,36,"01.09.2018","23:00:00","08.09.2018","05:00:00","1 d, 18 h","nachts/\nat night","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"19C66FCED188C.03"]
[null,"DB Netz AG","1A396389C663D.03","Magdeburg - Berlin","< >","Stadtforst","Eichgestell Nord",2018,2018,49,49,"03.12.2018","08:00:00","03.12.2018","16:00:00","8 h","morgens, nachmittags/\nmorning, afternoon","Kabelarbeiten/\ncable work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1A396389C663D.03"]
[null,"DB Netz AG","20020","Hamburg - Magdeburg","<","Bad Bevensen","Bienenbüttel",2017,2017,50,50,"12.12.2017","00:40:00","15.12.2017","04:30:00","15 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:40-04:30 ",null,null,"1B23CB5790633.01"]
[null,"DB Netz AG","302067.01","Hamburg - Magdeburg",">","Lüneburg","Celle",2018,2018,1,2,"06.01.2018","23:00:00","14.01.2018","05:00:00","12 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 23:00-05:00 ",null,null,"1BE820AB57293.01"]
[null,"DB Netz AG","302131.01","Hamburg - Magdeburg",">","Lüneburg","Celle",2018,2018,13,48,"31.03.2018","23:00:00","02.12.2018","05:00:00","9 d","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 23:00-05:00 ",null,"X","1BE82196CD7B3.01"]
[null,"DB Netz AG","19B7EC1DBC273.01","Hamburg - Magdeburg","<","Bad Bevensen","Bienenbüttel",2018,2018,26,27,"01.07.2018","01:00:00","03.07.2018","05:00:00","12 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 01:00-05:00 ",null,null,"19B7EC1DBC273.01"]
[null,"DB Netz AG","19B7EC1DBC273.02","Hamburg - Magdeburg",">","Bienenbüttel","Bad Bevensen",2018,2018,27,27,"03.07.2018","23:55:00","06.07.2018","03:55:00","12 h","nachts/\nat night","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:55-03:55 ",null,null,"19B7EC1DBC273.02"]
[null,"DB Netz AG","198ACF4AED02C.03","Hamburg - Magdeburg","< >","Bad Bevensen","Bad Bevensen",2018,2018,27,29,"05.07.2018","10:00:00","16.07.2018","22:00:00","11 d, 12 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"198ACF4AED02C.03"]
[null,"DB Netz AG","198ACF4AED02C.04","Hamburg - Magdeburg","< >","Bad Bevensen","Bad Bevensen",2018,2018,27,29,"05.07.2018","10:00:00","20.07.2018","22:00:00","15 d, 12 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"198ACF4AED02C.04"]
[null,"DB Netz AG","302002.01","Hamburg - Magdeburg","<","Lüneburg","Hmb-Harburg",2018,2018,27,30,"06.07.2018","23:00:00","27.07.2018","05:00:00","5 d, 06 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"19898FF6A188C.01"]
[null,"DB Netz AG","302001.03","Hamburg - Magdeburg","<","Celle","Uelzen",2018,2018,27,32,"06.07.2018","23:00:00","07.08.2018","05:00:00","8 d","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"19898FE72E74C.03"]
[null,"DB Netz AG","302003.01","Hamburg - Magdeburg","<","Bad Bevensen","Bienenbüttel",2018,2018,27,28,"07.07.2018","00:00:00","09.07.2018","12:00:00","2 d, 12 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1989B896A3E0C.01"]
[null,"DB Netz AG","302004.01","Hamburg - Magdeburg",">","Bienenbüttel","Bad Bevensen",2018,2018,28,28,"09.07.2018","12:00:00","11.07.2018","23:59:00","2 d, 12 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1989B8A1E4BCC.01"]
[null,"DB Netz AG","302017.03","Hamburg - Magdeburg",">","Lüneburg Gbf","Deutsch Evern",2018,2018,28,28,"12.07.2018","00:00:00","12.07.2018","20:00:00","20 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:00-20:00 ",null,null,"198ADBA90778C.03"]
[null,"DB Netz AG","1A6DF25F2D673.01","Hamburg - Magdeburg","<","Uelzen","Bad Bevensen",2018,2018,28,28,"12.07.2018","23:00:00","15.07.2018","05:00:00","18 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1A6DF25F2D673.01"]
[null,"DB Netz AG","302006.01","Hamburg - Magdeburg","<","Uelzen","Bad Bevensen",2018,2018,28,28,"12.07.2018","23:30:00","15.07.2018","03:30:00","2 d, 04 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"198AD10047E6C.01"]
[null,"DB Netz AG","302007.01","Hamburg - Magdeburg",">","Bad Bevensen","Uelzen",2018,2018,28,29,"15.07.2018","22:00:00","19.07.2018","02:00:00","3 d, 04 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"198AD11BA6BCC.01"]
[null,"DB Netz AG","302018.02","Hamburg - Magdeburg","< >","Lüneburg Gbf","Lüneburg Gbf",2018,2018,29,30,"19.07.2018","22:00:00","26.07.2018","05:00:00","6 d, 07 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"198ADBD11560C.02"]
[null,"DB Netz AG","302018.03","Hamburg - Magdeburg","<","Deutsch Evern","Lüneburg",2018,2018,29,30,"19.07.2018","22:00:00","26.07.2018","05:00:00","6 d, 07 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"198ADBD11560C.03"]
[null,"DB Netz AG","302019.01","Hamburg - Magdeburg","< >","Deutsch Evern","Deutsch Evern",2018,2018,29,30,"20.07.2018","22:00:00","23.07.2018","05:00:00","2 d, 07 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"198ADBF5CCCAC.01"]
[null,"DB Netz AG","302019.02","Hamburg - Magdeburg","<","Bienenbüttel","Lüneburg",2018,2018,29,30,"20.07.2018","22:00:00","23.07.2018","05:00:00","2 d, 07 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"198ADBF5CCCAC.02"]
[null,"DB Netz AG","302020.01","Hamburg - Magdeburg","< >","Deutsch Evern","Deutsch Evern",2018,2018,30,30,"23.07.2018","23:00:00","26.07.2018","05:00:00","18 h","nachts/\nat night","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,"Mo-Mi/MTW, jeweils/each 23:00-05:00 ",null,null,"198ADC38D7E0C.01"]
[null,"DB Netz AG","302020.02","Hamburg - Magdeburg","<","Bienenbüttel","Lüneburg",2018,2018,30,30,"23.07.2018","23:00:00","26.07.2018","05:00:00","18 h","nachts/\nat night","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,"Mo-Mi/MTW, jeweils/each 23:00-05:00 ",null,null,"198ADC38D7E0C.02"]
[null,"DB Netz AG","302025.04","Hamburg - Magdeburg",">","Winsen (Luhe)","Lüneburg",2018,2018,30,30,"24.07.2018","23:00:00","28.07.2018","05:00:00","1 d","nachts/\nat night","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"198ADD9675D4C.04"]
[null,"DB Netz AG","302021.02","Hamburg - Magdeburg",">","Lüneburg Gbf","Deutsch Evern",2018,2018,30,30,"26.07.2018","10:00:00","27.07.2018","05:00:00","19 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"198ADC527F42C.02"]
[null,"DB Netz AG","302001.01","Hamburg - Magdeburg","<","Celle","Lüneburg",2018,2018,30,32,"27.07.2018","23:00:00","07.08.2018","05:00:00","2 d, 18 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"19898FE72E74C.01"]
[null,"DB Netz AG","302026.02","Hamburg - Magdeburg","< >","Bardowick","Bardowick",2018,2018,30,32,"28.07.2018","20:00:00","07.08.2018","05:00:00","9 d, 09 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"198ADDFEFBA4C.02"]
[null,"DB Netz AG","302026.03","Hamburg - Magdeburg","<","Lüneburg","Bardowick",2018,2018,30,32,"28.07.2018","20:00:00","07.08.2018","05:00:00","9 d, 09 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"198ADDFEFBA4C.03"]
[null,"DB Netz AG","302027.04","Hamburg - Magdeburg",">","Winsen (Luhe)","Lüneburg",2018,2018,32,32,"07.08.2018","23:00:00","11.08.2018","05:00:00","1 d","nachts/\nat night","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"198ADE0BF3F4C.04"]
[null,"DB Netz AG","1A4DB8E6B4B73.01","Hamburg - Magdeburg",">","Bienenbüttel","Uelzen",2018,2018,32,33,"11.08.2018","23:00:00","13.08.2018","05:00:00","12 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1A4DB8E6B4B73.01"]
[null,"DB Netz AG","1A4AFEE9CDC13.01","Hamburg - Magdeburg",">","Bienenbüttel","Uelzen",2018,2018,33,34,"18.08.2018","23:00:00","20.08.2018","05:00:00","12 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1A4AFEE9CDC13.01"]
[null,"DB Netz AG","202379.01","Hamburg - Magdeburg","<","Lüneburg Gbf","Lüneburg Gbf",2018,2018,36,37,"03.09.2018","08:00:00","10.09.2018","10:00:00","7 d, 02 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A3824D54F553.01"]
[null,"DB Netz AG","202383.01","Hamburg - Magdeburg","< >","Lüneburg Gbf","Lüneburg Gbf",2018,2018,37,37,"10.09.2018","12:00:00","14.09.2018","16:00:00","4 d, 04 h","ganztags/\nfull day","Gleisauswechslung/\ntrack replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A43BC4050693.01"]
[null,"DB Netz AG","1A452591480B3.01","Hamburg - Magdeburg",">","Uelzen","Klein Süstedt",2018,2018,37,37,"10.09.2018","23:30:00","13.09.2018","04:30:00","15 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:30-04:30 ",null,null,"1A452591480B3.01"]
[null,"DB Netz AG","1A451EF514EB3.03","Hamburg - Magdeburg",">","Uelzen Gbf","Suderburg",2018,2018,37,37,"14.09.2018","23:30:00","16.09.2018","05:30:00","12 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:30-05:30 ",null,null,"1A451EF514EB3.03"]
[null,"DB Netz AG","302276.03","Hamburg - Magdeburg","< >","Hannover Hbf","Hannover Hbf",2018,2018,40,42,"01.10.2018","01:00:00","15.10.2018","04:00:00","14 d, 03 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"19C67214F0F8C.03"]
[null,"DB Netz AG","202215.02","Hamburg - Magdeburg","< >","Bardowick","Bardowick",2018,2018,42,43,"20.10.2018","22:00:00","22.10.2018","06:00:00","16 h","abends, nachts/\nat night, evening","Durcharbeitung von Gleisen/\ntrackage maintenance",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"19B674521F273.02"]
[null,"DB Netz AG","202215.03","Hamburg - Magdeburg","<","Lüneburg","Bardowick",2018,2018,42,43,"20.10.2018","22:00:00","22.10.2018","06:00:00","16 h","abends, nachts/\nat night, evening","Durcharbeitung von Gleisen/\ntrackage maintenance",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"19B674521F273.03"]
[null,"DB Netz AG","202218.03","Hamburg - Magdeburg","<","Deutsch Evern","Lüneburg Gbf",2018,2018,43,44,"26.10.2018","22:00:00","29.10.2018","06:00:00","1 d","abends, nachts/\nat night, evening","Durcharbeitung von Gleisen/\ntrackage maintenance",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"19B7E00CF97F3.03"]
[null,"DB Netz AG","202218.02","Hamburg - Magdeburg","<","Bienenbüttel","Lüneburg",2018,2018,43,44,"27.10.2018","01:00:00","29.10.2018","06:00:00","15 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Durcharbeitung von Gleisen/\ntrackage maintenance",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 01:00-06:00 ",null,null,"19B7E00CF97F3.02"]
[null,"DB Netz AG","1A450B9397513.01","Hamburg - Magdeburg",">","Winsen (Luhe)","Bardowick",2018,2018,44,44,"31.10.2018","23:00:00","04.11.2018","05:00:00","1 d","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1A450B9397513.01"]
[null,"DB Netz AG","1A6DF8059D7D3.01","Hamburg - Magdeburg","<","Uelzen","Bad Bevensen",2018,2018,45,45,"09.11.2018","23:30:00","11.11.2018","05:30:00","12 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:30-05:30 ",null,null,"1A6DF8059D7D3.01"]
[null,"DB Netz AG","1A4ABE117B233.01","Hamburg - Magdeburg","< >","Uelzen Gbf","Uelzen Gbf",2018,2018,47,48,"19.11.2018","08:00:00","26.11.2018","12:00:00","7 d, 04 h","ganztags/\nfull day","Gleisauswechslung/\ntrack replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A4ABE117B233.01"]
[null,"DB Netz AG","20054","Bremerhaven - Bremen","<","Lübberstedt","Brh-Wulsdorf",2018,2018,1,1,"03.01.2018","00:50:00","07.01.2018","06:00:00","1 d, 02 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:50-06:00 ",null,null,"1B93B6E4F3A9C.01"]
[null,"DB Netz AG","1BE82A668759A.01","Bremerhaven - Bremen","<","Bremen Hbf","Brh-Speckenbütt",2018,2018,1,48,"06.01.2018","23:00:00","02.12.2018","05:00:00","12 d","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 23:00-05:00 ",null,"X","1BE82A668759A.01"]
[null,"DB Netz AG","20054","Bremerhaven - Bremen","< >","Stubben","Stubben",2018,2018,1,2,"07.01.2018","23:00:00","09.01.2018","04:00:00","10 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:00-04:00 ",null,null,"1B93BC443EDBC.01"]
[null,"DB Netz AG","20054","Bremerhaven - Bremen","<","Lübberstedt","Brh-Wulsdorf",2018,2018,2,2,"12.01.2018","00:50:00","14.01.2018","06:00:00","16 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:50-06:00 ",null,null,"1B93BC443EDBC.03"]
[null,"DB Netz AG","20077","Bremerhaven - Bremen",">","Oldenbüttel","Osterholz-Scharm",2018,2018,2,3,"14.01.2018","23:40:00","19.01.2018","05:15:00","1 d, 04 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:40-05:15 ",null,null,"194CABF7DBD11.01"]
[null,"DB Netz AG","102101.03","Bremerhaven - Bremen",">","Brh-Speckenbütt","Brh-Lehe Pbf",2018,2018,5,5,"01.02.2018","00:00:00","03.02.2018","05:00:00","15 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:00-05:00 ",null,null,"1C0283034DAFC.03"]
[null,"DB Netz AG","20166\nDeleted","Bremerhaven - Bremen",">","Brh-Speckenbütt","Brh-Lehe Pbf",2018,2018,5,5,"01.02.2018","00:00:00","03.02.2018","05:00:00","15 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:00-05:00 ",null,null,"1C029FB17387C.03"]
[null,"DB Netz AG","102129.05\nDeleted","Bremerhaven - Bremen","< >","Bremen-Burg","Brm Rbf Abzw",2018,2018,5,7,"04.02.2018","02:30:00","18.02.2018","06:30:00","12 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"So/Su, jeweils/each 02:30-06:30 ",null,null,"1A7984258F351.05"]
[null,"DB Netz AG","102130.05\nDeleted","Bremerhaven - Bremen","< >","Bremen-Burg","Brm Rbf Abzw",2018,2018,6,8,"05.02.2018","00:30:00","19.02.2018","04:30:00","12 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"Mo/M, jeweils/each 00:30-04:30 ",null,null,"1A7984B55F9D1.05"]
[null,"DB Netz AG","102027.01","Bremerhaven - Bremen","<","Oldenbüttel","Lübberstedt",2018,2018,6,7,"05.02.2018","22:30:00","16.02.2018","05:00:00","2 d, 04 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"Mo-Do/MTWTh, jeweils/each 22:30-05:00 ",null,null,"1C00F68E845DC.01"]
[null,"DB Netz AG","102131.05\nDeleted","Bremerhaven - Bremen","< >","Bremen-Burg","Brm Rbf Abzw",2018,2018,8,11,"25.02.2018","02:30:00","18.03.2018","06:30:00","16 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"So/Su, jeweils/each 02:30-06:30 ",null,null,"1A79874938831.05"]
[null,"DB Netz AG","102132.05\nDeleted","Bremerhaven - Bremen","< >","Bremen-Burg","Brm Rbf Abzw",2018,2018,9,12,"26.02.2018","00:30:00","19.03.2018","04:30:00","16 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"Mo/M, jeweils/each 00:30-04:30 ",null,null,"1A79885427791.05"]
[null,"DB Netz AG","20215","Bremerhaven - Bremen","<","Brh-L Abstellbf","Brh-L Abstellbf",2018,2018,12,12,"24.03.2018","22:00:00","25.03.2018","12:00:00","14 h","abends, nachts, morgens/\nat night, morning, evening","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C05586C02F5C.01"]
[null,"DB Netz AG","20434","Bremerhaven - Bremen",">","Brh-Speckenbütt","Brh-L Abstellbf",2018,2018,18,19,"06.05.2018","02:00:00","11.05.2018","03:00:00","5 d, 01 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C86E70C19F1C.02"]
[null,"DB Netz AG","20456","Bremerhaven - Bremen","<","Brh-L Abstellbf","Brh-Speckenbütt",2018,2018,19,20,"13.05.2018","00:00:00","18.05.2018","03:00:00","5 d, 03 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C86EB19B2F1C.02"]
[null,"DB Netz AG","302200.02","Bremerhaven - Bremen","< >","Bremen Hbf","Bremen Hbf",2018,2018,21,22,"26.05.2018","01:00:00","28.05.2018","04:00:00","2 d, 03 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C671DC1A30C.02"]
[null,"DB Netz AG","202478.02","Bremerhaven - Bremen","< >","Brm Rbf Abzw","Brm Rbf Abzw",2018,2018,22,23,"01.06.2018","10:00:00","05.06.2018","12:00:00","4 d, 02 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n","X",null,null,null,null,null,null,null,null,null,null,null,null,"1A767B2DFFAF1.02"]
[null,"DB Netz AG","1C881D80138DC.02","Bremerhaven - Bremen",">","Brh-Speckenbütt","Brh-L Abstellbf",2018,2018,22,22,"02.06.2018","00:00:00","03.06.2018","05:00:00","1 d, 05 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C881D80138DC.02"]
[null,"DB Netz AG","1C8822E7925BC.02","Bremerhaven - Bremen","<","Brh-L Abstellbf","Brh-Speckenbütt",2018,2018,22,23,"03.06.2018","05:00:00","04.06.2018","03:00:00","22 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C8822E7925BC.02"]
[null,"DB Netz AG","202425.01","Bremerhaven - Bremen",">","Oldenbüttel","Osterholz-Scharm",2018,2018,29,29,"17.07.2018","00:00:00","20.07.2018","04:00:00","16 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Schwellenauswechslung/\nsleeper replacement",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:00 ",null,null,"1A699A12A0771.01"]
[null,"DB Netz AG","202423.01","Bremerhaven - Bremen","<","Osterholz-Scharm","Oldenbüttel",2018,2018,29,30,"20.07.2018","22:00:00","23.07.2018","06:00:00","2 d, 08 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A69890239EB1.01"]
[null,"DB Netz AG","202424.01","Bremerhaven - Bremen","< >","Osterholz-Scharm","Osterholz-Scharm",2018,2018,29,30,"20.07.2018","22:00:00","23.07.2018","06:00:00","2 d, 08 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement","X",null,null,null,null,null,null,null,null,null,null,null,null,"1A698B73D62B1.01"]
[null,"DB Netz AG","202425.03","Bremerhaven - Bremen",">","Oldenbüttel","Osterholz-Scharm",2018,2018,30,30,"24.07.2018","00:00:00","26.07.2018","04:00:00","12 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Schwellenauswechslung/\nsleeper replacement",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:00 ",null,null,"1A699A12A0771.03"]
[null,"DB Netz AG","302226.01","Bremerhaven - Bremen",">","Stubben","Oldenbüttel",2018,2018,30,31,"29.07.2018","00:00:00","30.07.2018","05:00:00","1 d, 05 h","ganztags/\nfull day","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C671EEE3C2C.01"]
[null,"DB Netz AG","302227.01","Bremerhaven - Bremen",">","Stubben","Lübberstedt",2018,2018,31,38,"31.07.2018","00:00:00","22.09.2018","05:00:00","8 d, 08 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"Di-Sa/TWThFS, jeweils/each 00:00-05:00 ",null,"X","19C671EF8EA8C.01"]
[null,"DB Netz AG","302227.03","Bremerhaven - Bremen",">","Stubben","Lübberstedt",2018,2018,31,38,"04.08.2018","14:00:00","17.09.2018","05:00:00","11 d, 09 h","ganztags/\nfull day","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"Sa+So/SSu",null,"X","19C671EF8EA8C.03"]
[null,"DB Netz AG","19CC5CACB05D1.01","Bremerhaven - Bremen","<","Brh-L Abstellbf","Brh-Speckenbütt",2018,2018,36,36,"03.09.2018","23:00:00","06.09.2018","05:00:00","18 h","nachts/\nat night","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"19CC5CACB05D1.01"]
[null,"DB Netz AG","19CC5CACB05D1.02","Bremerhaven - Bremen",">","Brh-Speckenbütt","Brh-L Abstellbf",2018,2018,36,36,"06.09.2018","23:00:00","09.09.2018","05:00:00","18 h","nachts/\nat night","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"19CC5CACB05D1.02"]
[null,"DB Netz AG","302268.01","Bremerhaven - Bremen",">","Stubben","Oldenbüttel",2018,2018,38,39,"23.09.2018","00:00:00","24.09.2018","05:00:00","1 d, 05 h","ganztags/\nfull day","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","19C6720E8D3AC.01"]
[null,"DB Netz AG","19CC792047F91.01","Bremerhaven - Bremen","<","Bremen-Burg","Osterholz-Scharm",2018,2018,39,39,"24.09.2018","22:45:00","28.09.2018","05:00:00","1 d, 01 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:45-05:00 ",null,null,"19CC792047F91.01"]
[null,"DB Netz AG","19CC5DA105311.01","Bremerhaven - Bremen","<","Brh-L Abstellbf","Brh-Speckenbütt",2018,2018,39,42,"28.09.2018","23:00:00","15.10.2018","05:00:00","6 d, 18 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"Fr-So/FSSu",null,null,"19CC5DA105311.01"]
[null,"DB Netz AG","19CC798D7A131.01","Bremerhaven - Bremen","<","Bremen-Burg","Osterholz-Scharm",2018,2018,41,41,"09.10.2018","22:45:00","12.10.2018","05:00:00","19 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:45-05:00 ",null,null,"19CC798D7A131.01"]
[null,"DB Netz AG","19CC7BCE117F1.01","Bremerhaven - Bremen",">","Stubben","Lübberstedt",2018,2018,42,42,"15.10.2018","22:30:00","19.10.2018","05:00:00","1 d, 02 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:30-05:00 ",null,null,"19CC7BCE117F1.01"]
[null,"DB Netz AG","19CC5E737F071.02","Bremerhaven - Bremen",">","Brh-Speckenbütt","Brh-L Abstellbf",2018,2018,45,46,"09.11.2018","23:00:00","12.11.2018","05:00:00","2 d, 06 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"Fr-So/FSSu",null,null,"19CC5E737F071.02"]
[null,"DB Netz AG","302309.01","Bremerhaven - Bremen","<","Bremen Hbf","Brhv-Seehf DB-Gr",2018,2018,46,47,"12.11.2018","23:00:00","23.11.2018","05:00:00","2 d, 12 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"(Sa)/MTWThFSu, jeweils/each 23:00-05:00 ",null,null,"19C6722CE0E6C.01"]
[null,"DB Netz AG","202274.01","Bremerhaven - Bremen","<","Brh-L Abstellbf","Brh-Speckenbütt",2018,2018,47,48,"23.11.2018","23:00:00","26.11.2018","05:00:00","18 h","nachts/\nat night","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"19CC5F4AA5271.01"]
[null,"DB Netz AG","19CC79E4BCF11.01","Bremerhaven - Bremen","<","Bremen-Burg","Osterholz-Scharm",2018,2018,48,48,"27.11.2018","22:45:00","30.11.2018","05:00:00","19 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:45-05:00 ",null,null,"19CC79E4BCF11.01"]
[null,"DB Netz AG","19CC71F581D31.01","Bremerhaven - Bremen",">","Osterholz-Scharm","Bremen-Burg",2018,2018,49,49,"03.12.2018","22:45:00","07.12.2018","05:00:00","1 d, 01 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:45-05:00 ",null,null,"19CC71F581D31.01"]
[null,"DB Netz AG","302073.01","Bremen - Hannover",">","Bremen Hbf","Wunstorf",2018,2018,1,27,"07.01.2018","23:00:00","02.07.2018","05:00:00","6 d, 12 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"So/Su, jeweils/each 23:00-05:00 ",null,"X","1BE4242A2E0DA.01"]
[null,"DB Netz AG","20070","Bremen - Hannover","< >","Poggenhagen","Poggenhagen",2018,2018,3,9,"16.01.2018","07:00:00","02.03.2018","18:00:00","45 d, 11 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BE564AA1E83A.01"]
[null,"DB Netz AG","20070","Bremen - Hannover","< >","Neustadt a Rbg","Neustadt a Rbg",2018,2018,3,9,"16.01.2018","07:00:00","02.03.2018","18:00:00","45 d, 11 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BE564AA1E83A.02"]
[null,"DB Netz AG","302081.01","Bremen - Hannover",">","Hagen (Han)","Poggenhagen",2018,2018,3,3,"19.01.2018","23:00:00","21.01.2018","05:00:00","1 d, 06 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BE5754C2DFDA.01"]
[null,"DB Netz AG","302081.02","Bremen - Hannover",">","Neustadt a Rbg","Poggenhagen",2018,2018,3,5,"19.01.2018","23:00:00","29.01.2018","05:00:00","9 d, 06 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BE5754C2DFDA.02"]
[null,"DB Netz AG","302083.01","Bremen - Hannover","< >","Verden (Aller)","Nienburg (Weser)",2018,2018,3,13,"20.01.2018","01:15:00","30.03.2018","04:45:00","10 d, 05 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung mit BR, PSS und TE/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:15-04:45 ",null,"X","1BE57EC020D3A.01"]
[null,"DB Netz AG","302083.03","Bremen - Hannover","< >","Wunstorf","Nienburg (Weser)",2018,2018,3,13,"20.01.2018","01:30:00","30.03.2018","04:30:00","8 d, 18 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung mit BR, PSS und TE/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:30-04:30 ",null,"X","1BE57EC020D3A.03"]
[null,"DB Netz AG","302083.02","Bremen - Hannover","< >","Verden (Aller)","Bremen Hbf",2018,2018,3,13,"20.01.2018","01:50:00","30.03.2018","04:15:00","7 d, 01 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung mit BR, PSS und TE/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:50-04:15 ",null,"X","1BE57EC020D3A.02"]
[null,"DB Netz AG","20070","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2018,2018,4,4,"22.01.2018","01:35:00","26.01.2018","04:45:00","16 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 01:35-04:45 ",null,null,"1BE5869FB809A.01"]
[null,"DB Netz AG","302088.01","Bremen - Hannover",">","Neustadt a Rbg","Wunstorf",2018,2018,4,5,"26.01.2018","23:00:00","29.01.2018","05:00:00","2 d, 06 h","ganztags/\nfull day","Weicheneinbau/\nswitch mounting",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BE577A12E05A.01"]
[null,"DB Netz AG","302089.01","Bremen - Hannover",">","Baden /Kr Verden","Langwedel",2018,2018,5,8,"29.01.2018","00:00:00","22.02.2018","23:59:00","25 d","ganztags/\nfull day","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BE420AF8B1FA.01"]
[null,"DB Netz AG","20109","Bremen - Hannover",">","Rohrsen/Nienburg","Linsburg",2018,2018,5,5,"29.01.2018","01:15:00","02.02.2018","04:30:00","16 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 01:15-04:30 ",null,null,"1BE580540261A.01"]
[null,"DB Netz AG","20109","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2018,2018,5,5,"29.01.2018","01:35:00","02.02.2018","04:45:00","16 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 01:35-04:45 ",null,null,"1BE587006BE5A.05"]
[null,"DB Netz AG","20109","Bremen - Hannover",">","Rohrsen/Nienburg","Linsburg",2018,2018,6,6,"05.02.2018","01:15:00","09.02.2018","04:30:00","16 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 01:15-04:30 ",null,null,"1BE72C1A251BA.01"]
[null,"DB Netz AG","302096.02","Bremen - Hannover","< >","Poggenhagen","Poggenhagen",2018,2018,6,8,"07.02.2018","01:30:00","19.02.2018","04:30:00","1 d, 15 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung mit BR und PSS/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:30-04:30 ",null,null,"1BE57C26BFE9A.02"]
[null,"DB Netz AG","302096.03","Bremen - Hannover","<","Poggenhagen","Neustadt a Rbg",2018,2018,6,6,"09.02.2018","22:00:00","10.02.2018","10:00:00","12 h","abends, nachts, morgens/\nat night, morning, evening","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BE57C26BFE9A.03"]
[null,"DB Netz AG","302096.04","Bremen - Hannover","<","Wunstorf","Poggenhagen",2018,2018,6,6,"10.02.2018","22:00:00","11.02.2018","10:00:00","12 h","abends, nachts, morgens/\nat night, morning, evening","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BE57C26BFE9A.04"]
[null,"DB Netz AG","20146","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2018,2018,8,8,"19.02.2018","01:15:00","21.02.2018","04:45:00","10 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:15-04:45 ",null,null,"1C33D4089BB7A.01"]
[null,"DB Netz AG","302101.01","Bremen - Hannover","<","Langwedel","Baden /Kr Verden",2018,2018,8,9,"23.02.2018","00:00:00","27.02.2018","14:00:00","4 d, 14 h","ganztags/\nfull day","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BE4211E1305A.01"]
[null,"DB Netz AG","302101.03","Bremen - Hannover","< >","Etelsen","Etelsen",2018,2018,8,9,"23.02.2018","00:40:00","27.02.2018","04:40:00","20 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:40-04:40 ",null,null,"1BE4211E1305A.03"]
[null,"DB Netz AG","20146","Bremen - Hannover","< >","Etelsen","Baden /Kr Verden",2018,2018,9,9,"26.02.2018","00:40:00","27.02.2018","04:40:00","8 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Brückenprüfung/\nbridge inspection","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:40-04:40 ",null,null,"1B9FAA564803A.01"]
[null,"DB Netz AG","302102.01","Bremen - Hannover","<","Etelsen","Etelsen",2018,2018,9,10,"27.02.2018","14:00:00","11.03.2018","07:00:00","11 d, 17 h","ganztags/\nfull day","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BE422794E9FA.01"]
[null,"DB Netz AG","20165","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2018,2018,9,9,"28.02.2018","01:35:00","03.03.2018","04:45:00","13 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 01:35-04:45 ",null,null,"1BE72B324E85A.01"]
[null,"DB Netz AG","20165","Bremen - Hannover",">","Rohrsen/Nienburg","Linsburg",2018,2018,9,9,"28.02.2018","01:35:00","03.03.2018","04:45:00","13 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 01:35-04:45 ",null,null,"1BE72B324E85A.05"]
[null,"DB Netz AG","302100.02","Bremen - Hannover","< >","Poggenhagen","Poggenhagen",2018,2018,10,12,"06.03.2018","23:00:00","19.03.2018","05:00:00","12 d, 06 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BE57E19FF87A.02"]
[null,"DB Netz AG","20165","Bremen - Hannover",">","Neustadt a Rbg","Wunstorf",2018,2018,10,12,"07.03.2018","01:30:00","19.03.2018","04:30:00","1 d, 15 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 01:30-04:30 ",null,null,"1BE57E45AD2BA.01"]
[null,"DB Netz AG","20165","Bremen - Hannover","< >","Rohrsen/Nienburg","Rohrsen/Nienburg",2018,2018,11,11,"13.03.2018","01:15:00","14.03.2018","04:45:00","7 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:15-04:45 ",null,null,"1C3E1A82A1AFA.01"]
[null,"DB Netz AG","20165","Bremen - Hannover","< >","Hagen (Han)","Poggenhagen",2018,2018,11,11,"13.03.2018","01:30:00","15.03.2018","04:30:00","9 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:30-04:30 ",null,null,"1C36E424A60FA.01"]
[null,"DB Netz AG","1C2CFF8CB441A.01\nDeleted","Bremen - Hannover",">","Rohrsen/Nienburg","Nienburg (Weser)",2018,2018,11,11,"15.03.2018","07:00:00","16.03.2018","17:00:00","20 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Vegetationsarbeiten/\nvegetation work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-17:00 ",null,null,"1C2CFF8CB441A.01"]
[null,"DB Netz AG","1C2D044DC885A.01\nDeleted","Bremen - Hannover","<","Eystrup","Dörverden",2018,2018,11,12,"18.03.2018","07:00:00","20.03.2018","17:00:00","1 d, 06 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Vegetationsarbeiten/\nvegetation work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-17:00 ",null,null,"1C2D044DC885A.01"]
[null,"DB Netz AG","20198","Bremen - Hannover","< >","Nienburg (Weser)","Nienburg (Weser)",2018,2018,12,13,"19.03.2018","01:15:00","29.03.2018","04:30:00","1 d, 12 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:15-04:30 ",null,null,"1BE72D7316C5A.01"]
[null,"DB Netz AG","1C4B613FC3C7A.01\nDeleted","Bremen - Hannover","<","Achim","Achim",2018,2018,12,12,"20.03.2018","08:00:00","23.03.2018","17:00:00","1 d, 12 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 08:00-17:00 ",null,null,"1C4B613FC3C7A.01"]
[null,"DB Netz AG","20198\nDeleted","Bremen - Hannover","<","Achim","Achim",2018,2018,12,12,"20.03.2018","08:00:00","23.03.2018","17:00:00","1 d, 12 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 08:00-17:00 ",null,null,"1C4B60F0CCEFA.01"]
[null,"DB Netz AG","20216\nDeleted","Bremen - Hannover","< >","Verden (Aller)","Verden (Aller)",2018,2018,12,12,"21.03.2018","01:30:00","23.03.2018","03:30:00","6 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:30-03:30 ",null,null,"1C5C807266C1A.05"]
[null,"DB Netz AG","20198","Bremen - Hannover","< >","Achim","Achim",2018,2018,12,12,"22.03.2018","01:35:00","23.03.2018","04:20:00","6 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:35-04:20 ",null,null,"1C4B60F0CCEFA.02"]
[null,"DB Netz AG","1C2D05364A01A.01\nDeleted","Bremen - Hannover",">","Dörverden","Eystrup",2018,2018,12,12,"22.03.2018","07:00:00","23.03.2018","17:00:00","20 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Vegetationsarbeiten/\nvegetation work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-17:00 ",null,null,"1C2D05364A01A.01"]
[null,"DB Netz AG","20198","Bremen - Hannover","<","Achim","Achim",2018,2018,13,13,"26.03.2018","08:00:00","27.03.2018","17:00:00","18 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 08:00-17:00 ",null,null,"1C4B53DD982BA.01"]
[null,"DB Netz AG","20198","Bremen - Hannover","<","Achim","Achim",2018,2018,13,13,"26.03.2018","08:00:00","27.03.2018","17:00:00","18 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 08:00-17:00 ",null,null,"1C4B41E1EC21A.01"]
[null,"DB Netz AG","1C4B613FC3C7A.02\nDeleted","Bremen - Hannover","< >","Achim","Achim",2018,2018,13,13,"27.03.2018","01:35:00","28.03.2018","04:20:00","6 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:35-04:20 ",null,null,"1C4B613FC3C7A.02"]
[null,"DB Netz AG","302249.01","Bremen - Hannover",">","Bremen Hbf","Wunstorf",2018,2018,35,49,"02.09.2018","23:00:00","03.12.2018","05:00:00","3 d, 12 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"So/Su, jeweils/each 23:00-05:00 ",null,"X","19C671FED0E8C.01"]
[null,"DB Netz AG","1A6CC174D6E1A.01","Bremen - Hannover","<","Eystrup","Dörverden",2018,2018,43,43,"23.10.2018","00:00:00","26.10.2018","05:00:00","20 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:00-05:00 ",null,null,"1A6CC174D6E1A.01"]
[null,"DB Netz AG","20211","Hannover - Magdeburg","<","Braunschweig Hbf","Schandelah",2018,2018,12,13,"23.03.2018","06:15:00","26.03.2018","19:40:00","3 d, 13 h","ganztags/\nfull day","Einbau Planumsschutzschicht/\nplanum protective layer",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BC3E63BF9565.01"]
[null,"DB Netz AG","202386.03","Hannover - Magdeburg","< >","Helmstedt","Helmstedt",2018,2018,15,15,"10.04.2018","04:00:00","10.04.2018","23:59:00","20 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A4B1E6041685.03"]
[null,"DB Netz AG","202387.01","Hannover - Magdeburg","< >","Helmstedt","Helmstedt",2018,2018,15,15,"11.04.2018","04:00:00","12.04.2018","23:59:00","1 d, 20 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A4B1FC0EC9C5.01"]
[null,"DB Netz AG","202388.01","Hannover - Magdeburg","< >","Helmstedt","Helmstedt",2018,2018,16,16,"16.04.2018","04:00:00","16.04.2018","23:59:00","20 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A4B20A59D885.01"]
[null,"DB Netz AG","1A4B227F1D5A5.01","Hannover - Magdeburg","< >","Helmstedt","Helmstedt",2018,2018,20,20,"14.05.2018","07:00:00","18.05.2018","17:00:00","2 d, 02 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-17:00 ",null,null,"1A4B227F1D5A5.01"]
[null,"DB Netz AG","202389.01","Hannover - Magdeburg","< >","Helmstedt","Helmstedt",2018,2018,21,21,"23.05.2018","22:00:00","26.05.2018","04:00:00","2 d, 06 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A4B393B63965.01"]
[null,"DB Netz AG","202390.01","Hannover - Magdeburg","< >","Helmstedt","Helmstedt",2018,2018,22,22,"28.05.2018","14:00:00","30.05.2018","14:00:00","2 d","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A4B3A4E24805.01"]
[null,"DB Netz AG","202391.01","Hannover - Magdeburg","< >","Helmstedt","Helmstedt",2018,2018,22,22,"31.05.2018","14:00:00","01.06.2018","10:00:00","20 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A4B3C7A84245.01"]
[null,"DB Netz AG","202392.01","Hannover - Magdeburg","<","Frellstedt","Helmstedt",2018,2018,23,23,"04.06.2018","22:50:00","06.06.2018","05:50:00","14 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:50-05:50 ",null,null,"1A4C451662645.01"]
[null,"DB Netz AG","1A4C47B162585.01","Hannover - Magdeburg","< >","Helmstedt","Helmstedt",2018,2018,23,23,"07.06.2018","07:00:00","08.06.2018","17:00:00","20 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-17:00 ",null,null,"1A4C47B162585.01"]
[null,"DB Netz AG","202393.01","Hannover - Magdeburg","< >","Helmstedt","Helmstedt",2018,2018,23,24,"09.06.2018","21:50:00","11.06.2018","06:50:00","18 h","abends, nachts, morgens/\nat night, morning, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 21:50-06:50 ",null,null,"1A4C4CB6D77E5.01"]
[null,"DB Netz AG","202393.03","Hannover - Magdeburg",">","Helmstedt","Frellstedt",2018,2018,23,24,"09.06.2018","22:50:00","11.06.2018","05:50:00","14 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:50-05:50 ",null,null,"1A4C4CB6D77E5.03"]
[null,"DB Netz AG","19B54F0EC9385.03","Hannover - Magdeburg",">","Braunschweig Hbf","Groß Gleidingen",2018,2018,24,24,"12.06.2018","23:00:00","15.06.2018","05:00:00","18 h","nachts/\nat night","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"19B54F0EC9385.03"]
[null,"DB Netz AG","19B54FDCC7985.03","Hannover - Magdeburg",">","Braunschweig Hbf","Groß Gleidingen",2018,2018,26,26,"27.06.2018","23:00:00","30.06.2018","05:00:00","18 h","nachts/\nat night","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"19B54FDCC7985.03"]
[null,"DB Netz AG","19E8093F33D85.01","Hannover - Magdeburg","< >","Braunschweig Hbf","Braunschweig Hbf",2018,2018,36,38,"03.09.2018","08:00:00","17.09.2018","08:00:00","14 d","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19E8093F33D85.01"]
[null,"DB Netz AG","202299.01","Hannover - Magdeburg","< >","Braunschweig Hbf","Braunschweig Hbf",2018,2018,36,37,"07.09.2018","17:00:00","10.09.2018","05:00:00","2 d, 12 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19E8115D42445.01"]
[null,"DB Netz AG","202300.01","Hannover - Magdeburg","< >","Braunschweig Hbf","Braunschweig Hbf",2018,2018,37,38,"15.09.2018","19:00:00","17.09.2018","05:00:00","1 d, 10 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19E81E39A0F25.01"]
[null,"DB Netz AG","20022","Oberhausen - Hannover","<","Bückeburg","Bückeburg",2017,2017,50,50,"11.12.2017","07:00:00","15.12.2017","16:00:00","4 d, 09 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1B8C6B028A71A.01"]
[null,"DB Netz AG","20022","Oberhausen - Hannover","< >","Stadthagen","Stadthagen",2017,2017,50,52,"11.12.2017","08:00:00","31.12.2017","05:00:00","19 d, 21 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1B92941DFE3FA.01"]
[null,"DB Netz AG","302338.01","Oberhausen - Hannover","<","Minden Gbf","Lindhorst/Sch L",2017,2017,52,52,"27.12.2017","01:00:00","28.12.2017","18:00:00","1 d, 17 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1B8C6A5189F1A.01"]
[null,"DB Netz AG","302335.01","Oberhausen - Hannover","<","Kirchhorsten","Lindhorst/Sch L",2017,2017,52,52,"27.12.2017","01:00:00","29.12.2017","01:00:00","2 d","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1B928EE8F27BA.01"]
[null,"DB Netz AG","302337.01","Oberhausen - Hannover","< >","Seelze","Wunstorf",2017,2017,52,52,"27.12.2017","12:00:00","29.12.2017","18:00:00","2 d, 06 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD12B442111A.01"]
[null,"DB Netz AG","302336.02","Oberhausen - Hannover","< >","Oeynhausen Abzw","Oeynhausen Abzw",2017,2017,52,52,"27.12.2017","12:30:00","29.12.2017","17:30:00","2 d, 05 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1B9CCB2AC2B9A.02"]
[null,"DB Netz AG","302064.01","Oberhausen - Hannover",">","Lindhorst/Sch L","Stadthagen",2017,2017,52,52,"29.12.2017","01:00:00","31.12.2017","08:00:00","2 d, 07 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1B9290E32853A.01"]
[null,"DB Netz AG","20034","Oberhausen - Hannover",">","Oeynhausen Abzw","Oeynhausen Abzw",2017,2017,52,52,"29.12.2017","17:30:00","31.12.2017","06:00:00","1 d, 13 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1B9CC7BDF3D5A.01"]
[null,"DB Netz AG","302065.01","Oberhausen - Hannover",">","Seelze West","Wunstorf",2018,2018,1,1,"01.01.2018","23:00:00","04.01.2018","04:00:00","2 d, 05 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD8134F654BA.01"]
[null,"DB Netz AG","302074.01","Oberhausen - Hannover",">","Wunstorf","Minden Gbf",2018,2018,1,48,"07.01.2018","00:00:00","02.12.2018","06:00:00","12 d","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"So/Su, jeweils/each 00:00-06:00 ",null,"X","1BCF53A231EFA.01"]
[null,"DB Netz AG","19938C7DEDC1A.01","Oberhausen - Hannover",">","Minden (Westf)","Oeynhausen Abzw",2018,2018,27,29,"05.07.2018","01:00:00","16.07.2018","23:00:00","11 d, 22 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,null,null,"X",null,null,null,null,null,null,null,null,null,"19938C7DEDC1A.01"]
[null,"DB Netz AG","302224.01","Oberhausen - Hannover","<","Oeynhausen Abzw","Minden (Westf)",2018,2018,29,39,"16.07.2018","22:50:00","30.09.2018","05:50:00","22 d, 04 h","nachts/\nat night","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:50-05:50 ",null,null,"19C671ED758CC.01"]
[null,"DB Netz AG","19FB249796D1A.01","Oberhausen - Hannover","<","Minden (Westf)","Minden (Westf)",2018,2018,29,31,"20.07.2018","23:00:00","30.07.2018","05:00:00","9 d, 06 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19FB249796D1A.01"]
[null,"DB Netz AG","302276.01","Oberhausen - Hannover","< >","Hannover Hbf","Hannover Hbf",2018,2018,40,42,"01.10.2018","01:00:00","15.10.2018","04:00:00","14 d, 03 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C67214F0F8C.01"]
[null,"DB Netz AG","1C99AEF660E14.01\nDeleted","Hannover - Magdeburg","< >","Hannover Hbf","Hannover Hbf",2018,2018,29,29,"18.07.2018","23:00:00","20.07.2018","05:00:00","12 h","nachts/\nat night","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1C99AEF660E14.01"]
[null,"DB Netz AG","1A19511B3B6D4.02","Hannover - Magdeburg","< >","Hannover Hbf","Hannover Hbf",2018,2018,39,42,"29.09.2018","07:00:00","17.10.2018","17:00:00","18 d, 10 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A19511B3B6D4.02"]
[null,"DB Netz AG","302276.04","Hannover - Magdeburg","< >","Hannover Hbf","Hannover Hbf",2018,2018,40,42,"01.10.2018","01:00:00","15.10.2018","04:00:00","14 d, 03 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C67214F0F8C.04"]
[null,"DB Netz AG","1A6DA483191B4.01","Oberhausen - Hannover","< >","Han Hbf Pferdet","Han Hbf Pferdet",2018,2018,45,47,"09.11.2018","23:00:00","19.11.2018","05:00:00","9 d, 06 h","ganztags/\nfull day","Gleisauswechslung/\ntrack replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A6DA483191B4.01"]
[null,"DB Netz AG","1A6DB4E205154.05","Oberhausen - Hannover","< >","Han Hbf Pferdet","Han Hbf Pferdet",2018,2018,45,45,"10.11.2018","08:00:00","11.11.2018","16:00:00","16 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Gleisauswechslung/\ntrack replacement",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 08:00-16:00 ",null,null,"1A6DB4E205154.05"]
[null,"DB Netz AG","1A6DBAE0C4974.01","Oberhausen - Hannover","< >","Han Hbf Pferdet","Han Hbf Pferdet",2018,2018,46,47,"12.11.2018","07:00:00","19.11.2018","05:00:00","6 d, 22 h","ganztags/\nfull day","Gleisauswechslung/\ntrack replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A6DBAE0C4974.01"]
[null,"DB Netz AG","1A6DB4E205154.04","Oberhausen - Hannover","< >","Han Hbf Pferdet","Han Hbf Pferdet",2018,2018,46,47,"12.11.2018","08:00:00","19.11.2018","05:00:00","6 d, 21 h","ganztags/\nfull day","Gleisauswechslung/\ntrack replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A6DB4E205154.04"]
[null,"DB Netz AG","1A6DB4E205154.03","Oberhausen - Hannover","< >","Han Hbf Pferdet","Han Hbf Pferdet",2018,2018,46,46,"17.11.2018","08:00:00","18.11.2018","16:00:00","16 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Gleisauswechslung/\ntrack replacement",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 08:00-16:00 ",null,null,"1A6DB4E205154.03"]
[null,"DB Netz AG","19F0A89BA7C54.01","Hannover - Magdeburg","< >","Lehrte West","Lehrte West",2017,2017,50,50,"15.12.2017","10:00:00","16.12.2017","19:00:00","1 d, 09 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19F0A89BA7C54.01"]
[null,"DB Netz AG","20025","Oberhausen - Hannover","< >","Ahlem","Ahlem",2017,2017,50,51,"16.12.2017","14:00:00","18.12.2017","14:00:00","2 d","ganztags/\nfull day","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BCF5D021DC74.01"]
[null,"DB Netz AG","102009.03","Oberhausen - Hannover",">","Han-Linden Hafen","Seelze Ost",2017,2017,50,51,"16.12.2017","14:00:00","18.12.2017","14:00:00","2 d","ganztags/\nfull day","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BCF5D021DC74.03"]
[null,"DB Netz AG","19F0A89BA7C54.02","Hannover - Magdeburg","< >","Lehrte West","Lehrte Nord",2017,2017,50,51,"16.12.2017","19:00:00","18.12.2017","05:00:00","1 d, 10 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19F0A89BA7C54.02"]
[null,"DB Netz AG","20025","Oberhausen - Hannover","< >","Han-Linden Hafen","Ahlem",2017,2017,50,51,"17.12.2017","23:00:00","18.12.2017","05:00:00","6 h","night time","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BCE274834014.01"]
[null,"DB Netz AG","102076.03","Oberhausen - Hannover","<","Wunstorf","Seelze West",2017,2017,52,52,"25.12.2017","18:00:00","26.12.2017","09:00:00","15 h","nachmittags, abends, nachts, morgens/\nat night, morning, afternoon, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD8418CF92D4.03"]
[null,"DB Netz AG","302337.02","Oberhausen - Hannover",">","Seelze West","Wunstorf",2017,2017,52,52,"27.12.2017","12:00:00","29.12.2017","18:00:00","2 d, 06 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD12B442111A.02"]
[null,"DB Netz AG","302340.01","Oberhausen - Hannover","<","Wunstorf","Seelze West",2017,2017,52,52,"29.12.2017","23:00:00","30.12.2017","14:00:00","15 h","night time, morgens, nachmittags/\nmorning, afternoon","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD84289CADB4.01"]
[null,"DB Netz AG","102124.01","Oberhausen - Hannover","< >","Seelze Ost","Seelze Ost",2018,2018,1,2,"02.01.2018","18:00:00","09.01.2018","18:00:00","7 d","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BE57551E7F65.01"]
[null,"DB Netz AG","20057","Oberhausen - Hannover","< >","Seelze Ost","Seelze Ost",2018,2018,1,2,"02.01.2018","18:00:00","09.01.2018","18:00:00","7 d","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BE57551E7F65.02"]
[null,"DB Netz AG","302065.04","Oberhausen - Hannover",">","Seelze West","Wunstorf",2018,2018,1,1,"04.01.2018","23:00:00","07.01.2018","04:00:00","2 d, 05 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD8134F654BA.04"]
[null,"DB Netz AG","102124.03","Oberhausen - Hannover",">","Seelze Ost","Seelze West",2018,2018,1,2,"06.01.2018","14:00:00","08.01.2018","07:00:00","1 d, 17 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BE57551E7F65.03"]
[null,"DB Netz AG","102124.04","Oberhausen - Hannover",">","Seelze Ost","Seelze West",2018,2018,1,2,"06.01.2018","14:00:00","08.01.2018","07:00:00","1 d, 17 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BE57551E7F65.04"]
[null,"DB Netz AG","102105.02","Oberhausen - Hannover","< >","Seelze Mitte","Seelze Mitte",2018,2018,3,9,"16.01.2018","07:00:00","02.03.2018","18:00:00","45 d, 11 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BE5667CF159A.02"]
[null,"DB Netz AG","102080.03","Oberhausen - Hannover","<","Wunstorf","Seelze West",2018,2018,4,5,"27.01.2018","00:00:00","29.01.2018","06:00:00","18 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:00-06:00 ",null,null,"1BD8437CB1794.03"]
[null,"DB Netz AG","20199","Hannover - Magdeburg","<","Misburg","Lehrte West",2018,2018,11,11,"17.03.2018","23:00:00","18.03.2018","19:00:00","20 h","ganztags/\nfull day","Gleisumbau ohne Schienenwechsel/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BFCAD4F90894.02"]
[null,"DB Netz AG","20236","Hannover - Magdeburg","< >","Lehrte West","Lehrte West",2018,2018,13,16,"28.03.2018","08:00:00","16.04.2018","05:00:00","18 d, 21 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C03C798153B4.01"]
[null,"DB Netz AG","102083.02","Hannover - Magdeburg","< >","Lehrte West","Lehrte West",2018,2018,13,14,"31.03.2018","19:00:00","02.04.2018","05:00:00","1 d, 10 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C03C798153B4.02"]
[null,"DB Netz AG","202419.05","Hannover - Magdeburg","< >","Lehrte West","Lehrte West",2018,2018,15,16,"10.04.2018","08:00:00","16.04.2018","05:00:00","5 d, 21 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C03C798153B4.05"]
[null,"DB Netz AG","20423, 20429","Hannover - Magdeburg","<","Ha-Li/Fischerhof","Waldhausen",2018,2018,18,19,"06.05.2018","06:00:00","07.05.2018","16:00:00","20 h","nachts, nachmittags, abends/\nnachts, at night, afternoon, evening","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 06:00-16:00 ",null,null,"1C9B76A3EA8B4.02"]
[null,"DB Netz AG","20476\nDeleted","Oberhausen - Hannover","< >","Hannover-Linden","Hannover-Linden",2018,2018,19,21,"09.05.2018","08:00:00","24.05.2018","18:00:00","10 d, 06 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,"unterbr./discontinuous",null,null,"1C9B36452FDB4.01"]
[null,"DB Netz AG","20476\nDeleted","Oberhausen - Hannover","< >","Hannover-Linden","Hannover-Linden",2018,2018,19,21,"09.05.2018","08:00:00","24.05.2018","18:00:00","15 d, 10 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C9B36452FDB4.04"]
[null,"DB Netz AG","1C03CF9016714.01","Hannover - Magdeburg","< >","Lehrte West","Lehrte West",2018,2018,22,24,"28.05.2018","08:00:00","11.06.2018","08:00:00","14 d","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C03CF9016714.01"]
[null,"DB Netz AG","1A6F50D6790F4.01","Oberhausen - Hannover","< >","Seelze Ost","Seelze Ost",2018,2018,30,34,"27.07.2018","08:00:00","22.08.2018","18:00:00","26 d, 10 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A6F50D6790F4.01"]
[null,"DB Netz AG","1A6F50D6790F4.03","Oberhausen - Hannover","< >","Seelze Ost","Seelze Ost",2018,2018,30,34,"28.07.2018","14:00:00","20.08.2018","07:00:00","22 d, 17 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A6F50D6790F4.03"]
[null,"DB Netz AG","1A6F50D6790F4.04","Oberhausen - Hannover","< >","Seelze Ost","Seelze Ost",2018,2018,31,34,"04.08.2018","14:00:00","20.08.2018","07:00:00","15 d, 17 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A6F50D6790F4.04"]
[null,"DB Netz AG","1A6F5F07665B4.03","Oberhausen - Hannover","< >","Seelze Ost","Seelze Ost",2018,2018,44,45,"03.11.2018","14:00:00","05.11.2018","06:00:00","1 d, 16 h","ganztags/\nfull day","Durcharbeitung von Weichen/\nswitch maintenance",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A6F5F07665B4.03"]
[null,"DB Netz AG","202212.02","Hannover - Magdeburg","< >","Gr Gleid Ostkopf","Okerbrücke",2018,2018,24,26,"15.06.2018","17:00:00","25.06.2018","05:00:00","9 d, 12 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"19B55AAEBA0A5.02"]
[null,"DB Netz AG","202212.03","Hannover - Magdeburg","< >","Braunschweig Rbf","Okerbrücke",2018,2018,24,26,"15.06.2018","17:00:00","25.06.2018","05:00:00","9 d, 12 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"19B55AAEBA0A5.03"]
[null,"DB Netz AG","302334.01","Löhne - Bad Bentheim",">","Melle","Wissingen",2017,2017,50,51,"16.12.2017","00:00:00","18.12.2017","04:00:00","2 d, 04 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1B9F8FE670E7A.01"]
[null,"DB Netz AG","302334.03","Löhne - Bad Bentheim","< >","Melle","Wissingen",2017,2017,50,51,"17.12.2017","00:00:00","18.12.2017","05:00:00","10 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:00-05:00 ",null,null,"1B9F8FE670E7A.03"]
[null,"DB Netz AG","302334.04","Löhne - Bad Bentheim","<","Wissingen","Melle",2017,2017,51,51,"18.12.2017","04:00:00","20.12.2017","08:00:00","2 d, 04 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1B9F8FE670E7A.04"]
[null,"DB Netz AG","102046.01","Löhne - Bad Bentheim",">","Ibbenbüren-Esch","Rheine",2017,2017,51,51,"18.12.2017","23:50:00","23.12.2017","05:30:00","1 d, 04 h","nachts/\nat night","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:50-05:30 ",null,null,"1B89DC0EF74DA.01"]
[null,"DB Netz AG","102046.02","Löhne - Bad Bentheim","< >","Rheine","Ibbenbüren-Esch",2017,2017,51,51,"19.12.2017","01:30:00","22.12.2017","04:30:00","12 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:30-04:30 ",null,null,"1B89DC0EF74DA.02"]
[null,"DB Netz AG","20037","Löhne - Bad Bentheim",">","Löhne(Westf) Gbf","Kirchlengern",2017,2017,52,52,"27.12.2017","13:00:00","29.12.2017","17:00:00","2 d, 04 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BDC99D61971A.01"]
[null,"DB Netz AG","20037","Löhne - Bad Bentheim","< >","Löhne(Westf) Gbf","Kirchlengern",2017,2017,52,52,"28.12.2017","00:15:00","29.12.2017","05:25:00","10 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:15-05:25 ",null,null,"1BDC99D61971A.02"]
[null,"DB Netz AG","20037","Löhne - Bad Bentheim","< >","Löhne(Westf) Gbf","Kirchlengern",2017,2017,52,52,"31.12.2017","00:15:00","31.12.2017","07:40:00","7 h","nachts, morgens/\nat night, morning","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BDC99D61971A.03"]
[null,"DB Netz AG","102045.01","Löhne - Bad Bentheim","<","Rheine","Ibbenbüren-Esch",2018,2018,1,1,"02.01.2018","23:40:00","05.01.2018","05:40:00","18 h","nachts/\nat night","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:40-05:40 ",null,null,"1B89DD35EFFFA.01"]
[null,"DB Netz AG","102045.02","Löhne - Bad Bentheim","< >","Ibbenbüren-Esch","Rheine",2018,2018,1,1,"03.01.2018","01:30:00","04.01.2018","04:30:00","6 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:30-04:30 ",null,null,"1B89DD35EFFFA.02"]
[null,"DB Netz AG","102037.01","Löhne - Bad Bentheim","< >","Ibbenbüren","Ibbenbüren-Esch",2018,2018,1,1,"06.01.2018","23:50:00","07.01.2018","06:40:00","7 h","night time, morgens/\nmorning","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BEC61C683A3A.01"]
[null,"DB Netz AG","102041.01","Löhne - Bad Bentheim","< >","Bünde (Westf)","Bruchmühlen",2018,2018,1,1,"07.01.2018","00:30:00","07.01.2018","06:30:00","6 h","nachts, morgens/\nat night, morning","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BE8728AE9DFA.01"]
[null,"DB Netz AG","102044.01","Löhne - Bad Bentheim","<","Rheine","Ibbenbüren-Esch",2018,2018,2,2,"08.01.2018","23:40:00","13.01.2018","05:40:00","1 d, 06 h","nachts/\nat night","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:40-05:40 ",null,null,"1B89DE85276DA.01"]
[null,"DB Netz AG","102044.02","Löhne - Bad Bentheim","< >","Ibbenbüren-Esch","Rheine",2018,2018,2,2,"09.01.2018","01:30:00","12.01.2018","04:30:00","12 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:30-04:30 ",null,null,"1B89DE85276DA.02"]
[null,"DB Netz AG","102038.01","Löhne - Bad Bentheim","< >","Ibbenbüren","Ibbenbüren-Esch",2018,2018,2,2,"13.01.2018","23:50:00","14.01.2018","06:40:00","7 h","night time, morgens/\nmorning","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BEC621C70B5A.01"]
[null,"DB Netz AG","20087","Löhne - Bad Bentheim",">","Osnabrück Hbf Pu","Osnabrück Hbf Pu",2018,2018,3,4,"21.01.2018","23:10:00","26.01.2018","05:00:00","1 d, 05 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:10-05:00 ",null,null,"1BCF70701AE9A.01"]
[null,"DB Netz AG","102050.01","Löhne - Bad Bentheim","<","Ibbenbüren-Esch","Ibbenbüren",2018,2018,7,8,"18.02.2018","23:00:00","20.02.2018","05:20:00","13 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:20 ",null,null,"1BCF7603C16DA.01"]
[null,"DB Netz AG","20368\nDeleted","Löhne - Bad Bentheim",">","Osnabrück Hbf Pu","Osn-Eversburg",2018,2018,18,19,"02.05.2018","02:30:00","09.05.2018","03:30:00","7 d, 01 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,null,null,"X",null,null,null,null,null,null,null,null,null,"1C69E8B7C0B1A.02"]
[null,"DB Netz AG","1993DAFACC2BA.03","Löhne - Bad Bentheim","< >","Löhne(Westf) Gbf","Löhne(Westf) Gbf",2018,2018,29,32,"16.07.2018","07:00:00","08.08.2018","16:00:00","23 d, 09 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1993DAFACC2BA.03"]
[null,"DB Netz AG","302295.03","Löhne - Bad Bentheim",">","Ibbenbüren-Esch","Rheine",2018,2018,44,45,"29.10.2018","01:00:00","08.11.2018","05:00:00","1 d, 20 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,"X",null,"X",null,"jeweils/each 01:00-05:00 ",null,null,"19C672223286C.03"]
[null,"DB Netz AG","1C4880C951B1A.01","Löhne - Bad Bentheim","<","Melle","Bruchmühlen",2018,2018,48,49,"02.12.2018","23:35:00","06.12.2018","05:25:00","23 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:35-05:25 ",null,null,"1C4880C951B1A.01"]
[null,"DB Netz AG","1CAFA78E03BC1.01","Löhne - Bad Bentheim","< >","Bad Bentheim Gr","Bad Bentheim",2018,2018,28,28,"14.07.2018","23:30:00","15.07.2018","05:20:00","6 h","night time","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CAFA78E03BC1.01"]
[null,"DB Netz AG","202417.01","Löhne - Bad Bentheim","< >","Bad Bentheim Gr","Bad Bentheim",2018,2018,28,28,"14.07.2018","23:30:00","15.07.2018","05:20:00","6 h","night time","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1A6258FA59505.01"]
[null,"DB Netz AG","302336.01","Oberhausen - Hannover","< >","Bad Oeynhsn Gbf","Bad Oeynhsn Gbf",2017,2017,52,52,"27.12.2017","00:00:00","27.12.2017","12:30:00","13 h","nachts, morgens, nachmittags/\nat night, morning, afternoon","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1B9CCB2AC2B9A.01"]
[null,"DB Netz AG","302336.03","Oberhausen - Hannover","< >","Bad Oeynhsn Gbf","Bad Oeynhsn Gbf",2017,2017,52,52,"27.12.2017","12:30:00","29.12.2017","17:30:00","2 d, 05 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1B9CCB2AC2B9A.03"]
[null,"DB Netz AG","302339.01","Oberhausen - Hannover","< >","Bad Oeynhsn Gbf","Bad Oeynhsn Gbf",2017,2017,52,52,"29.12.2017","17:30:00","30.12.2017","00:00:00","7 h","nachmittags, abends, nachts/\nat night, afternoon, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1B9CCF4EAC9DA.01"]
[null,"DB Netz AG","20034","Oberhausen - Hannover","<","Bad Oeynhsn Gbf","Bad Oeynhsn Gbf",2017,2017,52,52,"29.12.2017","17:30:00","31.12.2017","06:00:00","1 d, 13 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1B9CC7BDF3D5A.02"]
[null,"DB Netz AG","303118.01","Oberhausen - Hannover","<","Bielefeld Hbf","Bielefeld Vorbf",2018,2018,6,6,"05.02.2018","00:05:00","09.02.2018","18:00:00","4 d, 18 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C1729B56D5F7.01"]
[null,"DB Netz AG","1C4A0710A07DF.04\nDeleted","Oberhausen - Hannover","< >","Gütersloh Hbf","Brackwede",2018,2018,11,11,"12.03.2018","02:00:00","12.03.2018","10:00:00","8 h","nachts, morgens/\nat night, morning","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C4A0710A07DF.04"]
[null,"DB Netz AG","1C4A07D7C10DF.04\nDeleted","Oberhausen - Hannover","< >","Gütersloh Hbf","Brackwede",2018,2018,11,11,"12.03.2018","02:00:00","12.03.2018","10:00:00","8 h","nachts, morgens/\nat night, morning","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C4A07D7C10DF.04"]
[null,"DB Netz AG","19C677482C58D.04","Oberhausen - Hannover","< >","Rheda-Wiedenbr","Rheda-Wiedenbr",2018,2018,22,24,"01.06.2018","22:00:00","11.06.2018","12:00:00","9 d, 14 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C677482C58D.04"]
[null,"DB Netz AG","303243.02","Oberhausen - Hannover","< >","Brackwede Gbf","Bielefeld Vorbf",2018,2018,24,49,"15.06.2018","22:00:00","08.12.2018","23:59:00","176 d, 02 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,"X","19C670665B7AC.02"]
[null,"DB Netz AG","303245.02","Oberhausen - Hannover","< >","Heessen","Neubeckum Gbf",2018,2018,24,26,"16.06.2018","10:00:00","25.06.2018","05:00:00","8 d, 19 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"19C67067C9B0C.02"]
[null,"DB Netz AG","303254.01","Oberhausen - Hannover","<","Heessen","Herford",2018,2018,26,27,"25.06.2018","07:00:00","06.07.2018","17:00:00","5 d","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-17:00 ",null,null,"1C1AF5FA69E57.01"]
[null,"DB Netz AG","302215.01","Oberhausen - Hannover","< >","Minden (Westf)","Bad Oeynhsn Gbf",2018,2018,27,29,"05.07.2018","01:00:00","16.07.2018","23:00:00","11 d, 22 h","ganztags/\nfull day","Arbeiten an Lärmschutzanlagen/\nnoise barrier work","X",null,null,null,null,null,null,null,null,null,null,null,null,"19C671E6F964C.01"]
[null,"DB Netz AG","303269.01","Oberhausen - Hannover","< >","Bielefeld Vorbf","Herford",2018,2018,27,27,"06.07.2018","22:00:00","08.07.2018","08:00:00","1 d, 10 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"19C670787A26C.01"]
[null,"DB Netz AG","303269.03","Oberhausen - Hannover","< >","Bielefeld Vorbf","Herford",2018,2018,27,28,"08.07.2018","08:00:00","13.07.2018","04:00:00","4 d, 20 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"19C670787A26C.03"]
[null,"DB Netz AG","303286.01","Oberhausen - Hannover",">","Herford","Bielefeld Vorbf",2018,2018,28,37,"14.07.2018","00:05:00","10.09.2018","05:00:00","58 d, 05 h","ganztags/\nfull day","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C670843514C.01"]
[null,"DB Netz AG","1993DAFACC2BA.04","Oberhausen - Hannover","< >","Löhne(Westf) Gbf","Löhne(Westf) Gbf",2018,2018,29,32,"16.07.2018","07:00:00","08.08.2018","16:00:00","23 d, 09 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1993DAFACC2BA.04"]
[null,"DB Netz AG","302223.02","Oberhausen - Hannover","< >","Löhne(Westf) Gbf","Löhne(Westf) Gbf",2018,2018,29,32,"16.07.2018","21:30:00","08.08.2018","05:00:00","22 d, 08 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C671ECB23CC.02"]
[null,"DB Netz AG","303444.01","Oberhausen - Hannover","< >","Bielefeld Hbf","Bielefeld Hbf",2018,2018,32,32,"06.08.2018","22:00:00","10.08.2018","05:00:00","1 d, 04 h","abends, nachts/\nat night, evening","Einbau Planumsschutzschicht/\nplanum protective layer",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"19FE11D1CF405.01"]
[null,"DB Netz AG","303444.02","Oberhausen - Hannover","< >","Bielefeld Hbf","Bielefeld Hbf",2018,2018,32,34,"11.08.2018","22:00:00","20.08.2018","04:30:00","8 d, 07 h","ganztags/\nfull day","Einbau Planumsschutzschicht/\nplanum protective layer",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19FE11D1CF405.02"]
[null,"DB Netz AG","303338.04","Oberhausen - Hannover","< >","Neubeckum Pbf","Rheda-Wiedenbr",2018,2018,37,44,"10.09.2018","22:00:00","31.10.2018","04:00:00","50 d, 06 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n","X",null,null,null,null,null,null,null,null,null,null,null,"X","19C670AC73D0C.04"]
[null,"DB Netz AG","303339.01","Oberhausen - Hannover","< >","Rheda-Wiedenbr","Rheda-Wiedenbr",2018,2018,37,44,"11.09.2018","00:05:00","30.10.2018","04:30:00","9 d, 05 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung mit BR, PSS und TE/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:05-04:30 ",null,null,"19C670ADC99CC.01"]
[null,"DB Netz AG","203271.03","Oberhausen - Hannover","<","Hamm Rbf Hvn","Heessen",2018,2018,42,43,"15.10.2018","12:00:00","24.10.2018","05:00:00","8 d, 17 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A05553EB5025.03"]
[null,"DB Netz AG","203162.01","Oberhausen - Hannover","<","Oelde","Gütersloh Hbf",2018,2018,43,44,"26.10.2018","22:00:00","31.10.2018","04:00:00","4 d, 06 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C66BE6697ED.01"]
[null,"DB Netz AG","203163.01","Oberhausen - Hannover","< >","Rheda-Wiedenbr","Brackwede",2018,2018,44,46,"02.11.2018","22:00:00","12.11.2018","12:00:00","5 d, 04 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,"Fr-So/FSSu",null,null,"19C6A3140B9AD.01"]
[null,"DB Netz AG","303390.02","Oberhausen - Hannover","<","Heessen","Herford",2018,2018,45,46,"05.11.2018","07:00:00","18.11.2018","17:00:00","5 d, 20 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-17:00 ",null,null,"1C1AF8A7EA2D7.02"]
[null,"DB Netz AG","19C6A5963FE6D.01","Oberhausen - Hannover","< >","Gütersloh Hbf","Gütersloh Hbf",2018,2018,45,45,"05.11.2018","12:00:00","09.11.2018","22:00:00","4 d, 10 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C6A5963FE6D.01"]
[null,"DB Netz AG","202272.02","Oberhausen - Hannover",">","Vennebeck","Gohfeld",2018,2018,45,46,"05.11.2018","23:00:00","18.11.2018","05:00:00","3 d, 06 h","nachts/\nat night","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"19CB01CFFAB5A.02"]
[null,"DB Netz AG","202273.03","Oberhausen - Hannover",">","Bad Oeynhsn Gbf","Gohfeld",2018,2018,47,49,"19.11.2018","08:00:00","07.12.2018","16:00:00","5 d","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"Mo-Fr/MTWThF, jeweils/each 08:00-16:00 ",null,null,"19CB06F63E4BA.03"]
[null,"DB Netz AG","20235\nDeleted","Wilhelmshaven - Bremen","< >","Brm Hbf ehem Bwn","Bremen Hbf",2018,2018,13,14,"29.03.2018","22:00:00","03.04.2018","05:00:00","4 d, 07 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C66E38F20E1A.02"]
[null,"DB Netz AG","1C9F9B2F746BA.02\nDeleted","Wilhelmshaven - Bremen","< >","Brm Hbf ehem Bwn","Bremen Hbf",2018,2018,13,14,"29.03.2018","22:00:00","03.04.2018","05:00:00","4 d, 07 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C9F9B2F746BA.02"]
[null,"DB Netz AG","1CA9B981BA2DA.02\nDeleted","Wilhelmshaven - Bremen","< >","Brm Hbf ehem Bwn","Bremen Hbf",2018,2018,13,14,"29.03.2018","22:00:00","03.04.2018","05:00:00","4 d, 07 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CA9B981BA2DA.02"]
[null,"DB Netz AG","1CA9B9ED34D3A.02\nDeleted","Wilhelmshaven - Bremen","< >","Brm Hbf ehem Bwn","Bremen Hbf",2018,2018,13,14,"29.03.2018","22:00:00","03.04.2018","05:00:00","4 d, 07 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CA9B9ED34D3A.02"]
[null,"DB Netz AG","20432\nDeleted","Wilhelmshaven - Bremen","< >","Bremen Hbf","Brm Hbf ehem Bwn",2018,2018,18,18,"05.05.2018","00:20:00","06.05.2018","05:20:00","10 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung mit PSS/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:20-05:20 ",null,null,"1C9A0FB57DC7A.01"]
[null,"DB Netz AG","20432\nDeleted","Wilhelmshaven - Bremen","< >","Bremen Hbf","Brm Hbf ehem Bwn",2018,2018,18,18,"05.05.2018","00:20:00","06.05.2018","05:20:00","10 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung mit PSS/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:20-05:20 ",null,null,"1C9A16B6AF65A.01"]
[null,"DB Netz AG","20432","Wilhelmshaven - Bremen","< >","Bremen Hbf","Brm Hbf ehem Bwn",2018,2018,19,19,"08.05.2018","00:00:00","09.05.2018","05:00:00","10 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung mit PSS/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:00-05:00 ",null,null,"1C9A0FB57DC7A.03"]
[null,"DB Netz AG","20432\nDeleted","Wilhelmshaven - Bremen","< >","Bremen Hbf","Brm Hbf ehem Bwn",2018,2018,19,19,"08.05.2018","00:00:00","09.05.2018","05:00:00","10 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung mit PSS/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:00-05:00 ",null,null,"1C9A16B6AF65A.03"]
[null,"DB Netz AG","20513","Wilhelmshaven - Bremen","< >","Brm Hbf ehem Bwn","Bremen Hbf",2018,2018,20,20,"17.05.2018","23:25:00","18.05.2018","05:20:00","6 h","night time","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C9E1AE2E39DA.02"]
[null,"DB Netz AG","302228.01","Wilhelmshaven - Bremen",">","Bremen-Neustadt","Delmenhorst Df",2018,2018,31,32,"03.08.2018","23:00:00","06.08.2018","05:00:00","18 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,"X","19C671F0398EC.01"]
[null,"DB Netz AG","302234.01","Wilhelmshaven - Bremen","<","Delmenhorst Df","Bremen-Neustadt",2018,2018,32,32,"06.08.2018","23:00:00","09.08.2018","05:00:00","18 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,"X","19C671F43AF2C.01"]
[null,"DB Netz AG","302234.02","Wilhelmshaven - Bremen","<","Delmenhorst Df","Bremen-Neustadt",2018,2018,32,36,"09.08.2018","23:00:00","03.09.2018","05:00:00","6 d, 06 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,"X","19C671F43AF2C.02"]
[null,"DB Netz AG","202313.01","Wilhelmshaven - Bremen","< >","Delmenhorst Df","Delmenhorst Df",2018,2018,34,36,"24.08.2018","22:00:00","03.09.2018","16:00:00","9 d, 18 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A0DCCFF699E5.01"]
[null,"DB Netz AG","302234.03","Wilhelmshaven - Bremen",">","Bremen-Neustadt","Delmenhorst Df",2018,2018,36,39,"03.09.2018","23:00:00","28.09.2018","05:00:00","6 d, 06 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,"X","19C671F43AF2C.03"]
[null,"DB Netz AG","202313.03","Wilhelmshaven - Bremen","< >","Delmenhorst Df","Delmenhorst Df",2018,2018,36,38,"07.09.2018","22:00:00","17.09.2018","16:00:00","9 d, 18 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A0DCCFF699E5.03"]
[null,"DB Netz AG","202313.04","Wilhelmshaven - Bremen","< >","Delmenhorst Df","Delmenhorst Df",2018,2018,38,40,"21.09.2018","22:00:00","01.10.2018","16:00:00","9 d, 18 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A0DCCFF699E5.04"]
[null,"DB Netz AG","302274.01","Wilhelmshaven - Bremen","< >","Bremen-Neustadt","Bremen-Neustadt",2018,2018,39,40,"28.09.2018","23:00:00","04.10.2018","23:00:00","6 d","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C672139B2CC.01"]
[null,"DB Netz AG","302274.03","Wilhelmshaven - Bremen","<","Delmenhorst Df","Brm Hbf ehem Bwn",2018,2018,39,40,"29.09.2018","22:00:00","04.10.2018","05:00:00","4 d, 07 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C672139B2CC.03"]
[null,"DB Netz AG","302278.04","Wilhelmshaven - Bremen",">","Brm Hbf ehem Bwn","Bremen-Neustadt",2018,2018,40,41,"04.10.2018","23:00:00","09.10.2018","05:00:00","4 d, 06 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C6721646C4C.04"]
[null,"DB Netz AG","202142.01","Wilhelmshaven - Bremen","<","Delmenhorst Df","Bremen-Neustadt",2018,2018,43,44,"24.10.2018","23:00:00","29.10.2018","05:00:00","1 d, 06 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1993A265EB6A5.01"]
[null,"DB Netz AG","202142.02","Wilhelmshaven - Bremen",">","Bremen-Neustadt","Delmenhorst Df",2018,2018,44,45,"31.10.2018","23:00:00","05.11.2018","05:00:00","1 d, 06 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1993A265EB6A5.02"]
[null,"DB Netz AG","202158.01","Löhne - Bad Bentheim","< >","Rheine","Rheine",2018,2018,43,45,"28.10.2018","17:00:00","08.11.2018","16:00:00","10 d, 23 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1998102C06585.01"]
[null,"DB Netz AG","202158.02","Löhne - Bad Bentheim","< >","Salzbergen","Salzbergen",2018,2018,43,45,"28.10.2018","17:00:00","08.11.2018","16:00:00","10 d, 23 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1998102C06585.02"]
[null,"DB Netz AG","302295.01","Löhne - Bad Bentheim","<","Rheine","Salzbergen",2018,2018,44,45,"29.10.2018","01:00:00","08.11.2018","05:00:00","10 d, 04 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,"X","X",null,"X",null,null,null,null,"19C672223286C.01"]
[null,"DB Netz AG","302061.01","Wilhelmshaven - Bremen","<","Sande","Schwarzer Rabe",2017,2018,49,21,"10.12.2017","00:00:00","27.05.2018","23:59:00","169 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BA69A5374841.01"]
[null,"DB Netz AG","302062.01","Wilhelmshaven - Bremen","< >","Sande","Sande",2017,2018,49,49,"10.12.2017","00:00:00","08.12.2018","23:59:00","364 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BA69AAFF6281.01"]
[null,"DB Netz AG","1BA574622A281.01","Wilhelmshaven - Bremen","<","Varel (Oldb)","Jaderberg",2017,2017,50,51,"11.12.2017","23:40:00","20.12.2017","05:00:00","1 d, 08 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"Mo-Do/MTWTh, jeweils/each 23:40-05:00 ",null,null,"1BA574622A281.01"]
[null,"DB Netz AG","102033.01","Wilhelmshaven - Bremen",">","Oldb (Oldb) Hbf","Rastede",2018,2018,2,4,"13.01.2018","05:00:00","28.01.2018","23:59:00","5 d, 09 h","ganztags/\nfull day","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,null,null,null,null,null,"Sa+So/SSu",null,null,"1BBB195F0DD81.01"]
[null,"DB Netz AG","302084.01","Wilhelmshaven - Bremen","< >","Varel (Oldb)","Sande",2018,2018,3,21,"20.01.2018","05:00:00","26.05.2018","23:59:00","15 d, 01 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 05:00-23:59 ",null,"X","1BA69B84EAC21.01"]
[null,"DB Netz AG","302084.02","Wilhelmshaven - Bremen","< >","Varel (Oldb)","Sande",2018,2018,3,21,"21.01.2018","05:00:00","27.05.2018","23:59:00","15 d, 01 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"So/Su, jeweils/each 05:00-23:59 ",null,"X","1BA69B84EAC21.02"]
[null,"DB Netz AG","102034.01","Wilhelmshaven - Bremen","<","Rastede","Oldb (Oldb) Hbf",2018,2018,5,8,"03.02.2018","05:00:00","25.02.2018","23:59:00","7 d, 04 h","ganztags/\nfull day","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,null,null,null,null,null,"Sa+So/SSu",null,null,"1BBB19AA1BB61.01"]
[null,"DB Netz AG","102035.01","Wilhelmshaven - Bremen",">","Oldb (Oldb) Hbf","Rastede",2018,2018,9,12,"03.03.2018","05:00:00","25.03.2018","23:59:00","7 d, 04 h","ganztags/\nfull day","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,null,null,null,null,null,"Sa+So/SSu",null,null,"1BBB1A1BB0DC1.01"]
[null,"DB Netz AG","20209","Wilhelmshaven - Bremen",">","Jaderberg","Varel (Oldb)",2018,2018,12,21,"24.03.2018","00:00:00","26.05.2018","05:50:00","2 d, 10 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 00:00-05:50 ",null,null,"1BA5750A02E81.02"]
[null,"DB Netz AG","20209","Wilhelmshaven - Bremen",">","Jaderberg","Varel (Oldb)",2018,2018,12,21,"25.03.2018","00:00:00","27.05.2018","07:50:00","3 d, 06 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"So/Su, jeweils/each 00:00-07:50 ",null,null,"1BA5750A02E81.03"]
[null,"DB Netz AG","20209","Wilhelmshaven - Bremen",">","Jaderberg","Varel (Oldb)",2018,2018,13,22,"26.03.2018","01:00:00","28.05.2018","05:40:00","1 d, 23 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"Mo/M, jeweils/each 01:00-05:40 ",null,null,"1BA5750A02E81.04"]
[null,"DB Netz AG","20209","Wilhelmshaven - Bremen",">","Jaderberg","Varel (Oldb)",2018,2018,13,22,"27.03.2018","00:00:00","29.05.2018","05:50:00","9 d","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"Di-Fr/TWThF, jeweils/each 00:00-05:50 ",null,null,"1BA5750A02E81.05"]
[null,"DB Netz AG","20365","Wilhelmshaven - Bremen","< >","Rastede","Jaderberg",2018,2018,16,16,"17.04.2018","23:00:00","20.04.2018","05:00:00","18 h","nachts/\nat night","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1C812DD5AF95C.01"]
[null,"DB Netz AG","20365\nDeleted","Wilhelmshaven - Bremen","<","Jaderberg","Rastede",2018,2018,17,17,"27.04.2018","05:00:00","28.04.2018","05:00:00","1 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C812DD5AF95C.03"]
[null,"DB Netz AG","20365\nDeleted","Wilhelmshaven - Bremen","<","Jaderberg","Rastede",2018,2018,17,17,"27.04.2018","05:00:00","28.04.2018","05:00:00","1 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C855EC53D8DC.03"]
[null,"DB Netz AG","20365\nDeleted","Wilhelmshaven - Bremen","< >","Varel (Oldb)","Schwarzer Rabe",2018,2018,17,18,"28.04.2018","05:00:00","01.05.2018","09:00:00","3 d, 04 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C8558100DF1C.04"]
[null,"DB Netz AG","20365","Wilhelmshaven - Bremen","<","Jaderberg","Rastede",2018,2018,20,20,"18.05.2018","05:00:00","19.05.2018","05:00:00","1 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C855CECB1DFC.04"]
[null,"DB Netz AG","20365","Wilhelmshaven - Bremen","< >","Rastede","Jaderberg",2018,2018,20,21,"19.05.2018","05:00:00","22.05.2018","23:00:00","3 d, 18 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C855CECB1DFC.01"]
[null,"DB Netz AG","20365","Wilhelmshaven - Bremen","< >","Rastede","Jaderberg",2018,2018,21,21,"23.05.2018","23:00:00","25.05.2018","05:00:00","12 h","nachts/\nat night","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1C855EC53D8DC.01"]
[null,"DB Netz AG","302202.01","Wilhelmshaven - Bremen",">","Schwarzer Rabe","Sande",2018,2018,22,49,"28.05.2018","00:00:00","08.12.2018","23:59:00","195 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,"X","19C671DD6FFCC.01"]
[null,"DB Netz AG","20365","Wilhelmshaven - Bremen","< >","Rastede","Jaderberg",2018,2018,22,22,"28.05.2018","23:00:00","31.05.2018","05:00:00","18 h","nachts/\nat night","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1C855EC53D8DC.02"]
[null,"DB Netz AG","302206.01","Wilhelmshaven - Bremen","< >","Sande","Varel (Oldb)",2018,2018,22,48,"02.06.2018","05:00:00","01.12.2018","23:59:00","21 d, 09 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 05:00-23:59 ",null,"X","19C671E064D2C.01"]
[null,"DB Netz AG","302206.02","Wilhelmshaven - Bremen","< >","Sande","Varel (Oldb)",2018,2018,22,48,"03.06.2018","05:00:00","02.12.2018","23:59:00","21 d, 09 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"So/Su, jeweils/each 05:00-23:59 ",null,"X","19C671E064D2C.02"]
[null,"DB Netz AG","202315.01","Wilhelmshaven - Bremen","<","Rastede","Oldb (Oldb) Hbf",2018,2018,37,38,"14.09.2018","18:00:00","17.09.2018","06:00:00","2 d, 12 h","ganztags/\nfull day","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A0DE56DB4405.01"]
[null,"DB Netz AG","202315.02","Wilhelmshaven - Bremen","< >","Oldb (Oldb) Hbf","Rastede",2018,2018,37,37,"16.09.2018","00:00:00","16.09.2018","06:00:00","6 h","nachts/\nat night","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1A0DE56DB4405.02"]
[null,"DB Netz AG","202316.01","Wilhelmshaven - Bremen",">","Oldb (Oldb) Hbf","Rastede",2018,2018,38,39,"21.09.2018","18:00:00","24.09.2018","06:00:00","2 d, 12 h","ganztags/\nfull day","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A0DE7FAAF565.01"]
[null,"DB Netz AG","202316.02","Wilhelmshaven - Bremen","< >","Rastede","Oldb (Oldb) Hbf",2018,2018,38,38,"23.09.2018","00:00:00","23.09.2018","06:00:00","6 h","nachts/\nat night","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1A0DE7FAAF565.02"]
[null,"DB Netz AG","20106","Oberhausen - Hannover","< >","Han-Hainholz","Han-Hainholz",2018,2018,5,5,"03.02.2018","09:00:00","04.02.2018","19:00:00","20 h","tagsüber/\nduring the day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 09:00-19:00 ",null,null,"1C16DB2456974.03"]
[null,"DB Netz AG","20199","Hannover - Magdeburg","< >","Han Hbf Pferdet","Lehrte West",2018,2018,11,11,"13.03.2018","23:50:00","15.03.2018","04:35:00","9 h","nachts/\nat night","Gleisumbau ohne Schienenwechsel/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:50-04:35 ",null,null,"1BFCBE23C9CF4.01"]
[null,"DB Netz AG","20199","Hannover - Magdeburg","< >","Lehrte West","Lehrte West",2018,2018,11,13,"14.03.2018","18:00:00","26.03.2018","18:00:00","12 d","ganztags/\nfull day","Gleisumbau ohne Schienenwechsel/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BFCAD4F90894.03"]
[null,"DB Netz AG","20199","Hannover - Magdeburg","< >","Han Hbf Pferdet","Lehrte West",2018,2018,11,13,"17.03.2018","23:00:00","26.03.2018","04:00:00","8 d, 05 h","ganztags/\nfull day","Gleisumbau ohne Schienenwechsel/\n","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BFCAD4F90894.01"]
[null,"DB Netz AG","20199","Hannover - Magdeburg","< >","Han Hbf Pferdet","Lehrte West",2018,2018,13,13,"26.03.2018","23:50:00","28.03.2018","04:35:00","9 h","nachts/\nat night","Gleisumbau ohne Schienenwechsel/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:50-04:35 ",null,null,"1C00D6DA5C9B4.01"]
[null,"DB Netz AG","202473.04","Oberhausen - Hannover","< >","Han-Hainholz","Han-Hainholz",2018,2018,15,16,"15.04.2018","00:00:00","16.04.2018","03:00:00","6 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:00-03:00 ",null,null,"1A752A98C1F74.04"]
[null,"DB Netz AG","202422.01","Hannover - Magdeburg","< >","Lehrte West","Lehrte West",2018,2018,17,18,"28.04.2018","14:00:00","30.04.2018","05:00:00","1 d, 15 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C03C9CD84354.01"]
[null,"DB Netz AG","202420.03","Hannover - Magdeburg","< >","Lehrte West","Lehrte West",2018,2018,22,23,"01.06.2018","22:00:00","05.06.2018","05:00:00","3 d, 07 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C03CF9016714.03"]
[null,"DB Netz AG","102110.01","Oberhausen - Hannover","< >","Han-Hainholz","Han-Hainholz",2018,2018,4,4,"27.01.2018","09:00:00","28.01.2018","19:00:00","20 h","tagsüber/\nduring the day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 09:00-19:00 ",null,null,"1C0B278CCA614.01"]
[null,"DB Netz AG","1BC991855B9B4.01\nDeleted","Oberhausen - Hannover","< >","Han-Hainholz","Han-Hainholz",2018,2018,15,15,"14.04.2018","09:00:00","15.04.2018","19:00:00","20 h","tagsüber/\nduring the day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 09:00-19:00 ",null,null,"1BC991855B9B4.01"]
[null,"DB Netz AG","1C688775F5994.01\nDeleted","Oberhausen - Hannover","< >","Han-Hainholz","Han-Hainholz",2018,2018,15,15,"14.04.2018","09:00:00","15.04.2018","19:00:00","20 h","tagsüber/\nduring the day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 09:00-19:00 ",null,null,"1C688775F5994.01"]
[null,"DB Netz AG","202473.03","Oberhausen - Hannover","< >","Han-Hainholz","Han-Hainholz",2018,2018,15,16,"14.04.2018","22:00:00","16.04.2018","04:00:00","12 h","abends, nachts/\nat night, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-04:00 ",null,null,"1A752A98C1F74.03"]
[null,"DB Netz AG","202473.02","Oberhausen - Hannover","< >","Han-Hainholz","Han-Hainholz",2018,2018,15,16,"14.04.2018","23:00:00","16.04.2018","03:00:00","8 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:00-03:00 ",null,null,"1A752A98C1F74.02"]
[null,"DB Netz AG","202410.01","Oberhausen - Hannover","< >","Letter Abzw","Han-Hainholz",2018,2018,42,43,"20.10.2018","12:00:00","26.10.2018","05:00:00","5 d, 17 h","ganztags/\nfull day","Gleisauswechslung/\ntrack replacement","X",null,null,null,null,null,null,null,null,null,null,null,null,"1A62433DA7994.01"]
[null,"DB Netz AG","20211","Hannover - Magdeburg","< >","Schmiedekamp","Braunschweig Rbf",2018,2018,12,13,"23.03.2018","06:15:00","26.03.2018","19:40:00","3 d, 13 h","ganztags/\nfull day","Einbau Planumsschutzschicht/\nplanum protective layer","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BC3E63BF9565.02"]
[null,"DB Netz AG","20141","Hannover - Magdeburg","< >","Braunschweig Rbf","Braunschweig Hbf",2018,2018,8,9,"24.02.2018","16:30:00","26.02.2018","05:00:00","1 d, 13 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C227B0E33885.02"]
[null,"DB Netz AG","20141","Hannover - Magdeburg","< >","Braunschweig Rbf","Braunschweig Hbf",2018,2018,9,10,"03.03.2018","16:30:00","05.03.2018","05:00:00","1 d, 13 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C22832256E45.02"]
[null,"DB Netz AG","20141","Hannover - Magdeburg","< >","Braunschweig Rbf","Braunschweig Hbf",2018,2018,10,11,"10.03.2018","16:30:00","12.03.2018","05:00:00","1 d, 13 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C22832CD4705.02"]
[null,"DB Netz AG","20141","Hannover - Magdeburg","< >","Braunschweig Rbf","Braunschweig Hbf",2018,2018,11,12,"17.03.2018","16:30:00","19.03.2018","05:00:00","1 d, 13 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C22833676425.02"]
[null,"DB Netz AG","202211.02","Hannover - Magdeburg","< >","Braunschweig Rbf","Braunschweig Rbf",2018,2018,23,24,"08.06.2018","22:00:00","11.06.2018","05:00:00","2 d, 07 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19B546EB94705.02"]
[null,"DB Netz AG","202212.04","Hannover - Magdeburg","< >","Braunschweig Hbf","Okerbrücke",2018,2018,24,26,"15.06.2018","17:00:00","25.06.2018","05:00:00","9 d, 12 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"19B55AAEBA0A5.04"]
[null,"DB Netz AG","20141","Hannover - Magdeburg",">","Braunschweig Rbf","Buchhorst Abzw",2018,2018,8,9,"24.02.2018","16:30:00","26.02.2018","05:00:00","1 d, 13 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C227B0E33885.01"]
[null,"DB Netz AG","20141","Hannover - Magdeburg",">","Braunschweig Rbf","Buchhorst Abzw",2018,2018,9,10,"03.03.2018","16:30:00","05.03.2018","05:00:00","1 d, 13 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C22832256E45.01"]
[null,"DB Netz AG","20141","Hannover - Magdeburg",">","Braunschweig Rbf","Buchhorst Abzw",2018,2018,10,11,"10.03.2018","16:30:00","12.03.2018","05:00:00","1 d, 13 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C22832CD4705.01"]
[null,"DB Netz AG","20141","Hannover - Magdeburg",">","Braunschweig Rbf","Buchhorst Abzw",2018,2018,11,12,"17.03.2018","16:30:00","19.03.2018","05:00:00","1 d, 13 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C22833676425.01"]
[null,"DB Netz AG","20273","Hannover - Magdeburg","< >","Braunschweig Rbf","Braunschweig Rbf",2018,2018,14,15,"07.04.2018","16:30:00","09.04.2018","05:00:00","1 d, 13 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2281D909225.01"]
[null,"DB Netz AG","20273","Hannover - Magdeburg","< >","Braunschweig Rbf","Braunschweig Rbf",2018,2018,15,16,"14.04.2018","16:30:00","16.04.2018","05:00:00","1 d, 13 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C22825EBDA65.01"]
[null,"DB Netz AG","20273","Hannover - Magdeburg","< >","Braunschweig Rbf","Braunschweig Rbf",2018,2018,16,17,"21.04.2018","16:30:00","23.04.2018","05:00:00","1 d, 13 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C22826BE6CA5.01"]
[null,"DB Netz AG","202208.01","Hannover - Magdeburg","< >","Braunschweig Rbf","Braunschweig Rbf",2018,2018,22,24,"28.05.2018","08:00:00","15.06.2018","17:00:00","18 d, 09 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19B53F8CD4A05.01"]
[null,"DB Netz AG","202208.02","Hannover - Magdeburg",">","Braunschweig Rbf","Buchhorst Abzw",2018,2018,22,24,"02.06.2018","22:00:00","11.06.2018","05:00:00","8 d, 07 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19B53F8CD4A05.02"]
[null,"DB Netz AG","202209.02","Hannover - Magdeburg","< >","Buchhorst Abzw","Braunschweig Rbf",2018,2018,22,22,"02.06.2018","23:35:00","03.06.2018","05:35:00","6 h","night time","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"19B54254BF9A5.02"]
[null,"DB Netz AG","202209.04","Hannover - Magdeburg","< >","Buchhorst Abzw","Braunschweig Rbf",2018,2018,22,23,"03.06.2018","23:35:00","04.06.2018","05:20:00","6 h","night time","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"19B54254BF9A5.04"]
[null,"DB Netz AG","20141","Hannover - Magdeburg","< >","Braunschweig Rbf","Schmiedekamp",2018,2018,8,9,"24.02.2018","16:30:00","26.02.2018","05:00:00","1 d, 13 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C227B0E33885.03"]
[null,"DB Netz AG","20141","Hannover - Magdeburg","< >","Braunschweig Rbf","Schmiedekamp",2018,2018,9,10,"03.03.2018","16:30:00","05.03.2018","05:00:00","1 d, 13 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C22832256E45.03"]
[null,"DB Netz AG","20141","Hannover - Magdeburg","< >","Braunschweig Rbf","Schmiedekamp",2018,2018,10,11,"10.03.2018","16:30:00","12.03.2018","05:00:00","1 d, 13 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C22832CD4705.03"]
[null,"DB Netz AG","20141","Hannover - Magdeburg","< >","Braunschweig Rbf","Schmiedekamp",2018,2018,11,12,"17.03.2018","16:30:00","19.03.2018","05:00:00","1 d, 13 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C22833676425.03"]
[null,"DB Netz AG","20211","Hannover - Magdeburg","< >","Braunschweig Rbf","Lünischteich",2018,2018,12,13,"23.03.2018","06:15:00","26.03.2018","19:40:00","3 d, 13 h","ganztags/\nfull day","Einbau Planumsschutzschicht/\nplanum protective layer","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BC3E63BF9565.03"]
[null,"DB Netz AG","202211.01","Hannover - Magdeburg","< >","Braunschweig Rbf","Schmiedekamp",2018,2018,23,24,"08.06.2018","22:00:00","11.06.2018","05:00:00","2 d, 07 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"19B546EB94705.01"]
[null,"DB Netz AG","303084.01","Emmerich - Oberhausen",">","Emmerich","Oberhausen Hbf",2017,2018,49,49,"10.12.2017","00:00:00","08.12.2018","06:00:00","13 d","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"So/Su, jeweils/each 00:00-06:00 ",null,"X","1BBF9E0318277.01"]
[null,"DB Netz AG","303419.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2017,2017,50,51,"11.12.2017","04:40:00","18.12.2017","00:20:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BDB81668BE8D.01"]
[null,"DB Netz AG","303103.01\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,3,4,"19.01.2018","23:45:00","22.01.2018","04:10:00","2 d, 04 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C670040894C.01"]
[null,"DB Netz AG","303105.01","Emmerich - Oberhausen","< >","Ob-Sterkrade","Oberhausen Hbf",2018,2018,3,4,"20.01.2018","00:20:00","22.01.2018","04:40:00","2 d, 04 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,"X","1BDB81AB7F46D.01"]
[null,"DB Netz AG","303107.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2018,2018,4,5,"22.01.2018","04:40:00","29.01.2018","00:20:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BDB81DCE5C2D.01"]
[null,"DB Netz AG","103051.01","Emmerich - Oberhausen","< >","Oberhausen Hbf","Oberhsn Hbf Obn",2018,2018,4,5,"22.01.2018","04:40:00","29.01.2018","04:40:00","7 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BDB823766B4D.01"]
[null,"DB Netz AG","303106.02\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,4,4,"27.01.2018","23:45:00","28.01.2018","06:05:00","6 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,"X","1C7C9B70C5FCD.02"]
[null,"DB Netz AG","303119.01\nDeleted","Emmerich - Oberhausen","<","Empel-Rees","Emmerich",2018,2018,6,6,"09.02.2018","23:45:00","11.02.2018","23:45:00","2 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C6700EE7C8C.01"]
[null,"DB Netz AG","303121.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2018,2018,6,7,"10.02.2018","00:20:00","12.02.2018","00:20:00","2 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BDB82A6B1EAD.01"]
[null,"DB Netz AG","303119.02\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,6,6,"10.02.2018","23:45:00","11.02.2018","06:05:00","6 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,"X",null,"X",null,null,null,"X","19C6700EE7C8C.02"]
[null,"DB Netz AG","303123.01\nDeleted","Emmerich - Oberhausen",">","Emmerich","Empel-Rees",2018,2018,8,8,"19.02.2018","04:10:00","25.02.2018","23:45:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C670119360C.01"]
[null,"DB Netz AG","303124.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2018,2018,8,9,"19.02.2018","04:40:00","26.02.2018","00:20:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BDB82F42222D.01"]
[null,"DB Netz AG","103052.02","Emmerich - Oberhausen",">","Oberhsn Hbf Obn","Oberhausen Hbf",2018,2018,8,9,"19.02.2018","04:40:00","26.02.2018","04:40:00","7 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BDB857D1BD4D.02"]
[null,"DB Netz AG","303123.02\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,8,8,"24.02.2018","23:45:00","25.02.2018","06:05:00","6 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,"X",null,"X",null,null,null,"X","19C670119360C.02"]
[null,"DB Netz AG","303144.01","Emmerich - Oberhausen","< >","Ob-Sterkrade","Oberhsn Hbf Obn",2018,2018,11,12,"17.03.2018","00:20:00","19.03.2018","04:40:00","2 d, 04 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,"X","1BDB85BEB8B4D.01"]
[null,"DB Netz AG","303152.01\nDeleted","Emmerich - Oberhausen",">","Emmerich","Empel-Rees",2018,2018,12,12,"19.03.2018","04:10:00","25.03.2018","23:45:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C6702581EAC.01"]
[null,"DB Netz AG","303151.01","Emmerich - Oberhausen",">","Voerde       Üst","Dinslaken",2018,2018,12,12,"19.03.2018","04:40:00","24.03.2018","02:00:00","4 d, 21 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1C0535784206D.01"]
[null,"DB Netz AG","303153.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2018,2018,12,13,"19.03.2018","04:40:00","26.03.2018","00:20:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BDB860A7178D.01"]
[null,"DB Netz AG","103053.04","Emmerich - Oberhausen","< >","Oberhausen Hbf","Oberhsn Hbf Obn",2018,2018,12,13,"19.03.2018","04:40:00","26.03.2018","04:40:00","7 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BDB8645F3D8D.04"]
[null,"DB Netz AG","303152.02\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,12,12,"24.03.2018","23:45:00","25.03.2018","06:05:00","6 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C6702581EAC.02"]
[null,"DB Netz AG","303183.01\nDeleted","Emmerich - Oberhausen",">","Empel-Rees","Mehrhoog",2018,2018,15,15,"13.04.2018","23:45:00","15.04.2018","23:45:00","2 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C6703A7D02C.01"]
[null,"DB Netz AG","303184.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2018,2018,15,16,"14.04.2018","00:20:00","16.04.2018","00:20:00","2 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C6703B27E8C.01"]
[null,"DB Netz AG","303183.02\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,15,15,"14.04.2018","23:45:00","15.04.2018","06:05:00","6 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C6703A7D02C.02"]
[null,"DB Netz AG","303191.01\nDeleted","Emmerich - Oberhausen","<","Empel-Rees","Emmerich",2018,2018,17,17,"23.04.2018","04:10:00","29.04.2018","23:45:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C6703FEC9CC.01"]
[null,"DB Netz AG","303190.01","Emmerich - Oberhausen","<","Dinslaken","Voerde       Üst",2018,2018,17,17,"23.04.2018","04:40:00","28.04.2018","02:00:00","4 d, 21 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C6703F294CC.01"]
[null,"DB Netz AG","303192.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2018,2018,17,18,"23.04.2018","04:40:00","30.04.2018","00:20:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C670409782C.01"]
[null,"DB Netz AG","303191.02\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,17,17,"28.04.2018","23:45:00","29.04.2018","06:05:00","6 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C6703FEC9CC.02"]
[null,"DB Netz AG","303210.01\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,20,21,"18.05.2018","23:45:00","21.05.2018","04:10:00","2 d, 04 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C6704CB418C.01"]
[null,"DB Netz AG","303211.01","Emmerich - Oberhausen","< >","Dinslaken","Oberhausen Hbf",2018,2018,20,21,"19.05.2018","00:20:00","21.05.2018","04:40:00","2 d, 04 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C6704D5EFEC.01"]
[null,"DB Netz AG","31124","Emmerich - Oberhausen",">","Empel-Rees","Mehrhoog",2018,2018,20,20,"19.05.2018","02:00:00","19.05.2018","18:00:00","16 h","nachts, morgens, nachmittags/\nat night, morning, afternoon","Einbau Planumsschutzschicht/\nplanum protective layer",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1CB010CB80D03.02"]
[null,"DB Netz AG","203331.02","Emmerich - Oberhausen",">","Empel-Rees","Mehrhoog",2018,2018,20,20,"19.05.2018","02:00:00","19.05.2018","18:00:00","16 h","nachts, morgens, nachmittags/\nat night, morning, afternoon","Einbau Planumsschutzschicht/\nplanum protective layer",null,"X",null,null,null,null,"X",null,"X",null,null,null,null,"1B0827BA4324D.02"]
[null,"DB Netz AG","31124","Emmerich - Oberhausen","< >","Empel-Rees","Emmerich",2018,2018,20,22,"19.05.2018","02:00:00","28.05.2018","04:10:00","9 d, 02 h","ganztags/\nfull day","Einbau Planumsschutzschicht/\nplanum protective layer","X",null,null,null,null,null,null,null,null,null,null,null,null,"1CB010CB80D03.01"]
[null,"DB Netz AG","203331.01","Emmerich - Oberhausen","< >","Empel-Rees","Emmerich",2018,2018,20,22,"19.05.2018","02:00:00","28.05.2018","04:10:00","9 d, 02 h","ganztags/\nfull day","Einbau Planumsschutzschicht/\nplanum protective layer","X",null,null,null,null,null,"X",null,"X",null,null,null,null,"1B0827BA4324D.01"]
[null,"DB Netz AG","31124","Emmerich - Oberhausen",">","Empel-Rees","Mehrhoog",2018,2018,20,20,"19.05.2018","18:00:00","20.05.2018","10:00:00","16 h","nachmittags, abends, nachts, morgens/\nat night, morning, afternoon, evening","Einbau Planumsschutzschicht/\nplanum protective layer",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1CB010CB80D03.03"]
[null,"DB Netz AG","203331.03","Emmerich - Oberhausen",">","Empel-Rees","Mehrhoog",2018,2018,20,20,"19.05.2018","18:00:00","20.05.2018","10:00:00","16 h","nachmittags, abends, nachts, morgens/\nat night, morning, afternoon, evening","Einbau Planumsschutzschicht/\nplanum protective layer",null,"X",null,null,null,null,"X",null,"X",null,null,null,null,"1B0827BA4324D.03"]
[null,"DB Netz AG","303216.01","Emmerich - Oberhausen","< >","Ob-Sterkrade","Ob-Sterkrade",2018,2018,21,21,"21.05.2018","04:40:00","26.05.2018","02:00:00","4 d, 21 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","19C670533040C.01"]
[null,"DB Netz AG","303217.01","Emmerich - Oberhausen","<","Voerde       Üst","Wesel",2018,2018,21,21,"21.05.2018","04:40:00","26.05.2018","02:00:00","4 d, 21 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C67053DB26C.01"]
[null,"DB Netz AG","303219.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2018,2018,21,22,"21.05.2018","04:40:00","28.05.2018","00:20:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C6705530F2C.01"]
[null,"DB Netz AG","303237.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2018,2018,23,24,"09.06.2018","00:20:00","11.06.2018","00:20:00","2 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C670625A16C.01"]
[null,"DB Netz AG","303236.01\nDeleted","Emmerich - Oberhausen","<","Mehrhoog","Empel-Rees",2018,2018,23,23,"09.06.2018","02:00:00","10.06.2018","23:45:00","1 d, 22 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C67061AF30C.01"]
[null,"DB Netz AG","203332.01","Emmerich - Oberhausen","< >","Empel-Rees","Emmerich",2018,2018,23,24,"09.06.2018","02:00:00","11.06.2018","04:10:00","2 d, 02 h","ganztags/\nfull day","Einbau Planumsschutzschicht/\nplanum protective layer","X",null,null,null,null,null,"X",null,"X",null,null,null,null,"1B083B15D712D.01"]
[null,"DB Netz AG","303236.02\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,23,23,"09.06.2018","23:45:00","10.06.2018","06:05:00","6 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C67061AF30C.02"]
[null,"DB Netz AG","303251.01\nDeleted","Emmerich - Oberhausen","<","Mehrhoog","Empel-Rees",2018,2018,25,25,"18.06.2018","04:10:00","24.06.2018","23:45:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C6706C4526C.01"]
[null,"DB Netz AG","303249.01","Emmerich - Oberhausen","< >","Ob-Sterkrade","Ob-Sterkrade",2018,2018,25,25,"18.06.2018","04:40:00","23.06.2018","02:00:00","4 d, 21 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","19C6706AD6F0C.01"]
[null,"DB Netz AG","303250.01","Emmerich - Oberhausen",">","Wesel","Voerde       Üst",2018,2018,25,25,"18.06.2018","04:40:00","23.06.2018","02:00:00","4 d, 21 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C6706B81D6C.01"]
[null,"DB Netz AG","303252.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2018,2018,25,26,"18.06.2018","04:40:00","25.06.2018","00:20:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C6706CF00CC.01"]
[null,"DB Netz AG","303251.02\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,25,25,"23.06.2018","23:45:00","24.06.2018","06:05:00","6 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C6706C4526C.02"]
[null,"DB Netz AG","203333.01","Emmerich - Oberhausen","< >","Empel-Rees","Emmerich",2018,2018,29,31,"18.07.2018","02:00:00","30.07.2018","04:10:00","12 d, 02 h","ganztags/\nfull day","Einbau Planumsschutzschicht/\nplanum protective layer","X",null,null,null,null,null,"X",null,"X",null,null,null,null,"1B083D9E25DED.01"]
[null,"DB Netz AG","303295.01\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,29,30,"18.07.2018","23:45:00","23.07.2018","04:10:00","4 d, 04 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C6708AB13CC.01"]
[null,"DB Netz AG","303296.01","Emmerich - Oberhausen","< >","Dinslaken","Oberhsn Hbf Obn",2018,2018,29,30,"19.07.2018","00:20:00","23.07.2018","04:40:00","4 d, 04 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C6708C0708C.01"]
[null,"DB Netz AG","303297.01","Emmerich - Oberhausen","< >","Ob-Sterkrade","Ob-Sterkrade",2018,2018,30,30,"23.07.2018","04:40:00","28.07.2018","02:00:00","4 d, 21 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","19C6708CB1EEC.01"]
[null,"DB Netz AG","303299.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2018,2018,30,31,"23.07.2018","04:40:00","30.07.2018","00:20:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C67090CBBCC.01"]
[null,"DB Netz AG","303298.02","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,30,30,"28.07.2018","23:45:00","29.07.2018","06:05:00","6 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,"X","1C7CEA95F738D.02"]
[null,"DB Netz AG","303303.01\nDeleted","Emmerich - Oberhausen","<","Mehrhoog","Empel-Rees",2018,2018,32,32,"10.08.2018","23:45:00","12.08.2018","23:45:00","2 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C670937754C.01"]
[null,"DB Netz AG","303304.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2018,2018,32,33,"11.08.2018","00:20:00","13.08.2018","00:20:00","2 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C67094223AC.01"]
[null,"DB Netz AG","303303.02\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,32,32,"11.08.2018","23:45:00","12.08.2018","06:05:00","6 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C670937754C.02"]
[null,"DB Netz AG","303308.01\nDeleted","Emmerich - Oberhausen",">","Empel-Rees","Mehrhoog",2018,2018,34,34,"20.08.2018","04:10:00","26.08.2018","23:45:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C67096E63CC.01"]
[null,"DB Netz AG","303309.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2018,2018,34,35,"20.08.2018","04:40:00","27.08.2018","00:20:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C670979122C.01"]
[null,"DB Netz AG","303308.02\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,34,34,"25.08.2018","23:45:00","26.08.2018","06:05:00","6 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C67096E63CC.02"]
[null,"DB Netz AG","303340.01\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,37,38,"14.09.2018","23:45:00","17.09.2018","04:10:00","2 d, 04 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C670AF1F68C.01"]
[null,"DB Netz AG","303343.01","Emmerich - Oberhausen","< >","Ob-Sterkrade","Oberhsn Hbf Obn",2018,2018,37,38,"15.09.2018","00:20:00","17.09.2018","04:40:00","2 d, 04 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C670B13884C.01"]
[null,"DB Netz AG","203334.02","Emmerich - Oberhausen",">","Emmerich","Empel-Rees",2018,2018,37,37,"15.09.2018","14:00:00","16.09.2018","06:00:00","16 h","nachmittags, abends, nachts/\nat night, afternoon, evening","Einbau Planumsschutzschicht/\nplanum protective layer",null,"X",null,null,null,"X","X",null,"X",null,null,null,null,"1B08430C827CD.02"]
[null,"DB Netz AG","303347.01\nDeleted","Emmerich - Oberhausen",">","Empel-Rees","Mehrhoog",2018,2018,38,38,"17.09.2018","04:10:00","23.09.2018","23:45:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C670B55252C.01"]
[null,"DB Netz AG","303348.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2018,2018,38,39,"17.09.2018","04:40:00","24.09.2018","00:20:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C670B5FD38C.01"]
[null,"DB Netz AG","303347.02\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,38,38,"22.09.2018","23:45:00","23.09.2018","06:05:00","6 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C670B55252C.02"]
[null,"DB Netz AG","303364.01\nDeleted","Emmerich - Oberhausen","<","Empel-Rees","Emmerich",2018,2018,40,40,"05.10.2018","23:45:00","07.10.2018","23:45:00","2 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1C7CEC559ED4D.01"]
[null,"DB Netz AG","303365.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2018,2018,40,41,"06.10.2018","00:20:00","08.10.2018","00:20:00","2 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C670C293E0C.01"]
[null,"DB Netz AG","303364.02\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,40,40,"06.10.2018","23:45:00","07.10.2018","06:05:00","6 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,"X","1C7CEC559ED4D.02"]
[null,"DB Netz AG","303377.01\nDeleted","Emmerich - Oberhausen","<","Mehrhoog","Empel-Rees",2018,2018,43,43,"22.10.2018","04:10:00","28.10.2018","23:45:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C670CB418EC.01"]
[null,"DB Netz AG","303378.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2018,2018,43,44,"22.10.2018","04:40:00","29.10.2018","00:20:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C670CBEC74C.01"]
[null,"DB Netz AG","303377.02\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,43,43,"27.10.2018","23:45:00","28.10.2018","06:05:00","6 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C670CB418EC.02"]
[null,"DB Netz AG","303398.01\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,46,47,"16.11.2018","23:45:00","19.11.2018","04:10:00","2 d, 04 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C670D95ED6C.01"]
[null,"DB Netz AG","303400.01","Emmerich - Oberhausen","< >","Ob-Sterkrade","Oberhsn Hbf Obn",2018,2018,46,47,"17.11.2018","00:20:00","19.11.2018","04:40:00","2 d, 04 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C670DACD0CC.01"]
[null,"DB Netz AG","303403.01\nDeleted","Emmerich - Oberhausen","<","Mehrhoog","Empel-Rees",2018,2018,47,47,"19.11.2018","04:10:00","25.11.2018","23:45:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C670DDC1E2C.01"]
[null,"DB Netz AG","303404.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2018,2018,47,48,"19.11.2018","04:40:00","26.11.2018","00:20:00","6 d, 20 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C670E425A0C.01"]
[null,"DB Netz AG","203204.01","Emmerich - Oberhausen",">","Emmerich Grenze","Emmerich",2018,2018,47,47,"19.11.2018","05:45:00","24.11.2018","23:59:00","5 d, 18 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,"X",null,"X",null,null,null,null,"19DFF4EC28697.01"]
[null,"DB Netz AG","303403.02\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,47,47,"24.11.2018","23:45:00","25.11.2018","06:05:00","6 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C670DDC1E2C.02"]
[null,"DB Netz AG","303408.01\nDeleted","Emmerich - Oberhausen","<","Empel-Rees","Emmerich",2018,2018,48,48,"30.11.2018","23:45:00","02.12.2018","23:45:00","2 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C670E97CD0C.01"]
[null,"DB Netz AG","303410.01","Emmerich - Oberhausen","<","Oberhsn Hbf Obn","Ob-Sterkrade",2018,2018,48,49,"01.12.2018","00:20:00","03.12.2018","00:20:00","2 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C670EC0FFEC.01"]
[null,"DB Netz AG","303408.02\nDeleted","Emmerich - Oberhausen","< >","Emmerich","Mehrhoog",2018,2018,48,48,"01.12.2018","23:45:00","02.12.2018","06:05:00","6 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,"X","19C670E97CD0C.02"]
[null,"DB Netz AG","30190","Aachen - Oberhausen","< >","Baal Gbf","Rheydt Gbf",2018,2018,15,16,"13.04.2018","22:10:00","16.04.2018","04:30:00","2 d, 06 h","ganztags/\nfull day","Arbeiten am Bahnübergang/\nrailroad crossing work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C0CC2E582F57.01"]
[null,"DB Netz AG","1C2B0E176CF77.01\nDeleted","Aachen - Oberhausen","<","Rheydt Gbf","Baal Gbf",2018,2018,21,23,"27.05.2018","23:30:00","08.06.2018","04:30:00","2 d, 12 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:30-04:30 ",null,null,"1C2B0E176CF77.01"]
[null,"DB Netz AG","203292.05\nDeleted","Aachen - Oberhausen","< >","Herzogenrath","Herzogenrath",2018,2018,22,23,"02.06.2018","21:30:00","04.06.2018","04:30:00","1 d, 07 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,"X",null,"X",null,null,null,null,"1A50964C499C5.05"]
[null,"DB Netz AG","203292.03\nDeleted","Aachen - Oberhausen","< >","Herzogenrath","Herzogenrath",2018,2018,25,26,"21.06.2018","01:00:00","25.06.2018","03:00:00","10 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,"X",null,"X",null,"jeweils/each 01:00-03:00 ",null,null,"1A50964C499C5.03"]
[null,"DB Netz AG","203292.02\nDeleted","Aachen - Oberhausen","<","Geilenkirchen","Herzogenrath",2018,2018,25,26,"21.06.2018","21:30:00","25.06.2018","04:30:00","3 d, 07 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,"X",null,"X",null,null,null,null,"1A50964C499C5.02"]
[null,"DB Netz AG","203294.03\nDeleted","Aachen - Oberhausen","< >","Herzogenrath","Herzogenrath",2018,2018,27,27,"07.07.2018","23:30:00","08.07.2018","16:00:00","16 h","night time, morgens, nachmittags/\nmorning, afternoon","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,"X",null,"X",null,null,null,null,"1A54F832450E5.03"]
[null,"DB Netz AG","1C2B0E176CF77.03\nDeleted","Aachen - Oberhausen","<","Rheydt Gbf","Baal Gbf",2018,2018,27,28,"08.07.2018","23:30:00","13.07.2018","04:30:00","1 d, 01 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:30-04:30 ",null,null,"1C2B0E176CF77.03"]
[null,"DB Netz AG","303076.01","Aachen - Oberhausen","< >","Lindern","Baal Gbf",2018,2018,28,35,"13.07.2018","23:30:00","27.08.2018","04:30:00","44 d, 05 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work","X",null,null,null,null,null,"X",null,"X",null,null,null,null,"19C2D2B5109D7.01"]
[null,"DB Netz AG","303280.01","Aachen - Oberhausen","< >","Geilenkirchen","Baal Gbf",2018,2018,28,35,"13.07.2018","23:30:00","27.08.2018","04:30:00","44 d, 05 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work","X",null,null,null,null,null,null,null,null,null,null,null,null,"19C6707FEA72C.01"]
[null,"DB Netz AG","303283.01","Aachen - Oberhausen","< >","Geilenkirchen","Baal Gbf",2018,2018,28,35,"13.07.2018","23:30:00","27.08.2018","04:30:00","44 d, 05 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work","X",null,null,null,null,null,"X",null,"X",null,null,null,null,"19C670824CCCC.01"]
[null,"DB Netz AG","303279.01","Aachen - Oberhausen","< >","Kohlscheid","Geilenkirchen",2018,2018,28,35,"13.07.2018","23:40:00","27.08.2018","04:20:00","8 d, 18 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work","X",null,null,null,null,null,"X",null,"X",null,"jeweils/each 23:40-04:20 ",null,null,"19C6707F3F8CC.01"]
[null,"DB Netz AG","303279.02","Aachen - Oberhausen","<","Herzogenrath","Aachen West Gbf",2018,2018,28,34,"14.07.2018","04:20:00","26.08.2018","23:40:00","43 d, 19 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,"X",null,"X",null,null,null,null,"19C6707F3F8CC.02"]
[null,"DB Netz AG","303285.01","Aachen - Oberhausen",">","Herzogenrath","Geilenkirchen",2018,2018,28,34,"14.07.2018","04:20:00","26.08.2018","23:40:00","43 d, 19 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,"X",null,"X",null,null,null,null,"19C67083A298C.01"]
[null,"DB Netz AG","1A55107CFD3E5.01\nDeleted","Aachen - Oberhausen","<","Geilenkirchen","Kohlscheid",2018,2018,29,29,"16.07.2018","23:00:00","19.07.2018","06:00:00","21 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-06:00 ",null,null,"1A55107CFD3E5.01"]
[null,"DB Netz AG","303325.02","Aachen - Oberhausen","< >","Geilenkirchen","Geilenkirchen",2018,2018,35,39,"27.08.2018","04:20:00","24.09.2018","06:00:00","28 d, 02 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C670A288C0C.02"]
[null,"DB Netz AG","303326.01","Aachen - Oberhausen","< >","Herzogenrath","Herzogenrath",2018,2018,35,39,"27.08.2018","04:20:00","29.09.2018","23:30:00","33 d, 19 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C670A333A6C.01"]
[null,"DB Netz AG","303326.02","Aachen - Oberhausen","<","Geilenkirchen","Kohlscheid",2018,2018,39,40,"29.09.2018","23:30:00","01.10.2018","06:00:00","13 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:30-06:00 ",null,null,"19C670A333A6C.02"]
[null,"DB Netz AG","19E6CB0224BDF.01","Aachen - Oberhausen","< >","Geilenkirchen","Geilenkirchen",2018,2018,41,42,"08.10.2018","09:00:00","15.10.2018","04:30:00","6 d, 20 h","ganztags/\nfull day","Gleisauswechslung/\ntrack replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19E6CB0224BDF.01"]
[null,"DB Netz AG","19E6CB0224BDF.02","Aachen - Oberhausen",">","Herzogenrath","Lindern",2018,2018,41,42,"08.10.2018","23:50:00","15.10.2018","04:30:00","1 d, 09 h","nachts/\nat night","Gleisauswechslung/\ntrack replacement",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:50-04:30 ",null,null,"19E6CB0224BDF.02"]
[null,"DB Netz AG","303328.03","Aachen - Oberhausen","<","Baal Gbf","Geilenkirchen",2018,2018,42,43,"20.10.2018","05:20:00","22.10.2018","04:30:00","1 d, 23 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,"X",null,null,null,null,"19C670A48972C.03"]
[null,"DB Netz AG","303379.01","Aachen - Oberhausen",">","Herzogenrath","Lindern",2018,2018,43,44,"27.10.2018","00:10:00","29.10.2018","04:00:00","2 d, 04 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,"X",null,null,null,null,"19C670CC975AC.01"]
[null,"DB Netz AG","1A55147CA9CA5.01\nDeleted","Aachen - Oberhausen","<","Geilenkirchen","Kohlscheid",2018,2018,47,48,"24.11.2018","22:00:00","26.11.2018","06:00:00","16 h","abends, nachts/\nat night, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"1A55147CA9CA5.01"]
[null,"DB Netz AG","303415.01","Oberhausen - Hannover",">","Ge-Buer Nord","Recklinghsn Ost",2017,2017,49,50,"10.12.2017","22:00:00","15.12.2017","06:00:00","1 d, 16 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"So-Do/MTWThSu, jeweils/each 22:00-06:00 ",null,null,"1BDB51D0E1232.01"]
[null,"DB Netz AG","303501.01\nDeleted","Oberhausen - Hannover","<","Ge-Buer Nord","Gladbeck West",2017,2017,50,51,"11.12.2017","22:00:00","23.12.2017","06:00:00","4 d","abends, nachts/\nat night, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"1BB562ABFC1F4.01"]
[null,"DB Netz AG","303422.04\nDeleted","Oberhausen - Hannover","<","Recklinghsn Ost","Gladbeck West",2017,2017,51,51,"18.12.2017","20:00:00","22.12.2017","06:00:00","1 d, 16 h","abends, nachts/\nat night, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 20:00-06:00 ",null,null,"1BB55C1F85514.04"]
[null,"DB Netz AG","303421.02","Oberhausen - Hannover","<","Recklinghsn Ost","Gladbeck West",2017,2017,51,51,"18.12.2017","20:00:00","22.12.2017","06:00:00","1 d, 16 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 20:00-06:00 ",null,null,"1BB99226BF854.02"]
[null,"DB Netz AG","303094.01\nDeleted","Oberhausen - Hannover","<","Ge-Buer Nord","Gladbeck West",2018,2018,2,14,"08.01.2018","20:00:00","02.04.2018","06:00:00","35 d","abends, nachts/\nat night, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 20:00-06:00 ",null,"X","1BB561868A0D4.01"]
[null,"DB Netz AG","30135","Oberhausen - Hannover",">","Lotharstraße","Mathilde",2018,2018,2,5,"12.01.2018","22:00:00","29.01.2018","06:00:00","3 d","abends, nachts/\nat night, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"Fr-So/FSSu, jeweils/each 22:00-06:00 ",null,null,"1ABC5F85F326D.02"]
[null,"DB Netz AG","303096.01\nDeleted","Oberhausen - Hannover","<","Blumenthal","Gladbeck West",2018,2018,2,3,"13.01.2018","20:00:00","21.01.2018","08:00:00","1 d","abends, nachts, morgens/\nat night, morning, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 20:00-08:00 ",null,null,"1BE3B85876834.01"]
[null,"DB Netz AG","303096.03\nDeleted","Oberhausen - Hannover","<","Blumenthal","Gladbeck West",2018,2018,2,4,"14.01.2018","20:00:00","22.01.2018","04:45:00","17 h","abends, nachts/\nat night, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"So/Su, jeweils/each 20:00-04:45 ",null,null,"1BE3B85876834.03"]
[null,"DB Netz AG","103050.01","Oberhausen - Hannover",">","Oberaden","Bergkamen",2018,2018,13,13,"27.03.2018","20:00:00","29.03.2018","06:00:00","20 h","abends, nachts/\nat night, evening","Arbeiten am Bahnübergang/\nrailroad crossing work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 20:00-06:00 ",null,null,"1C68860007423.01"]
[null,"DB Netz AG","303194.01","Oberhausen - Hannover","< >","Westerholt","Blumenthal",2018,2018,17,17,"27.04.2018","00:30:00","29.04.2018","00:30:00","2 d","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BB998A1AA234.01"]
[null,"DB Netz AG","303199.02\nDeleted","Oberhausen - Hannover","< >","Gladbeck West","Recklinghsn Ost",2018,2018,17,21,"29.04.2018","00:30:00","22.05.2018","04:30:00","23 d, 04 h","ganztags/\nfull day","Arbeiten an Lärmschutzanlagen/\nnoise barrier work","X",null,null,null,null,null,null,null,null,null,null,null,null,"19C670455C36C.02"]
[null,"DB Netz AG","303209.01\nDeleted","Oberhausen - Hannover","< >","Westerholt","Blumenthal",2018,2018,20,21,"16.05.2018","23:30:00","22.05.2018","04:30:00","5 d, 05 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BB9993670134.01"]
[null,"DB Netz AG","303228.01","Oberhausen - Hannover",">","Ge-Buer Nord","Hamm Rbf Hde",2018,2018,22,23,"28.05.2018","09:00:00","10.06.2018","17:00:00","4 d, 16 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 09:00-17:00 ",null,null,"1C1AF5579F177.01"]
[null,"DB Netz AG","303229.01","Oberhausen - Hannover",">","Bottrop Hbf-Pbf","Ge-Buer Nord",2018,2018,22,23,"28.05.2018","21:00:00","10.06.2018","05:00:00","4 d, 08 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 21:00-05:00 ",null,null,"1C1AF5A3A1197.01"]
[null,"DB Netz AG","203132.01","Oberhausen - Hannover",">","Oberaden","Bergkamen",2018,2018,23,23,"04.06.2018","07:00:00","06.06.2018","20:00:00","1 d, 15 h","tagsüber/\nduring the day","Arbeiten am Bahnübergang/\nrailroad crossing work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-20:00 ",null,null,"19995F80A24E0.01"]
[null,"DB Netz AG","203132.02","Oberhausen - Hannover","<","Bergkamen","Oberaden",2018,2018,23,23,"07.06.2018","07:00:00","08.06.2018","20:00:00","1 d, 02 h","tagsüber/\nduring the day","Arbeiten am Bahnübergang/\nrailroad crossing work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-20:00 ",null,null,"19995F80A24E0.02"]
[null,"DB Netz AG","31040\nDeleted","Oberhausen - Hannover",">","Ruhrtal","Mathilde",2018,2018,23,24,"10.06.2018","22:00:00","17.06.2018","05:00:00","2 d, 01 h","abends, nachts/\nat night, evening","Schienenerneuerung/\nrail renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1CA6D68EFD603.01"]
[null,"DB Netz AG","31040\nDeleted","Oberhausen - Hannover",">","Ruhrtal","Mathilde",2018,2018,25,25,"23.06.2018","22:00:00","24.06.2018","22:00:00","1 d","ganztags/\nfull day","Schienenerneuerung/\nrail renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1CA6D68EFD603.04"]
[null,"DB Netz AG","303259.01","Oberhausen - Hannover",">","Gladbeck West","Westerholt",2018,2018,26,26,"30.06.2018","20:00:00","01.07.2018","08:00:00","12 h","abends, nachts, morgens/\nat night, morning, evening","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C670719C56C.01"]
[null,"DB Netz AG","203133.01","Oberhausen - Hannover",">","Oberaden","Bergkamen",2018,2018,37,37,"11.09.2018","07:00:00","12.09.2018","20:00:00","1 d, 02 h","tagsüber/\nduring the day","Arbeiten am Bahnübergang/\nrailroad crossing work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-20:00 ",null,null,"1999627ED0E20.01"]
[null,"DB Netz AG","203133.02","Oberhausen - Hannover","<","Bergkamen","Oberaden",2018,2018,37,37,"13.09.2018","07:00:00","14.09.2018","20:00:00","1 d, 02 h","tagsüber/\nduring the day","Arbeiten am Bahnübergang/\nrailroad crossing work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-20:00 ",null,null,"1999627ED0E20.02"]
[null,"DB Netz AG","203134.01","Oberhausen - Hannover","< >","Oberaden","Bergkamen",2018,2018,40,40,"01.10.2018","07:00:00","05.10.2018","17:00:00","4 d, 10 h","ganztags/\nfull day","Arbeiten am Bahnübergang/\nrailroad crossing work","X",null,null,null,null,null,null,null,null,null,null,null,null,"199963DDF5760.01"]
[null,"DB Netz AG","303383.01","Oberhausen - Hannover",">","Ge-Buer Nord","Hamm Rbf Hde",2018,2018,44,45,"29.10.2018","09:00:00","11.11.2018","17:00:00","4 d, 16 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 09:00-17:00 ",null,null,"1C1AF8488C1D7.01"]
[null,"DB Netz AG","303384.01","Oberhausen - Hannover",">","Bottrop Hbf-Pbf","Ge-Buer Nord",2018,2018,44,45,"29.10.2018","21:00:00","11.11.2018","05:00:00","4 d, 08 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 21:00-05:00 ",null,null,"1C1AF86559297.01"]
[null,"DB Netz AG","203186.05","Oberhausen - Hannover","< >","Datteln","Blumenthal",2018,2018,44,45,"02.11.2018","00:00:00","05.11.2018","04:30:00","18 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung mit PSS/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:30 ",null,null,"19D736B9600D7.05"]
[null,"DB Netz AG","30008","Aachen - Oberhausen","<","Oberh West Stw 1","Ruhrtal",2017,2017,50,51,"16.12.2017","10:00:00","18.12.2017","11:00:00","2 d, 01 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1B9C763A81A74.03"]
[null,"DB Netz AG","30008","Aachen - Oberhausen","< >","Oberh West Stw 1","Oberh West Stw 1",2017,2017,50,51,"16.12.2017","10:00:00","18.12.2017","11:00:00","2 d, 01 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1B9C763A81A74.04"]
[null,"DB Netz AG","303102.01","Aachen - Oberhausen",">","Walzwerk","Prosper-Levin",2018,2018,3,3,"18.01.2018","06:00:00","19.01.2018","14:00:00","16 h","nachts, nachmittags, abends/\nnachts, at night, afternoon, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 06:00-14:00 ",null,null,"1BEE1683485F4.01"]
[null,"DB Netz AG","303102.02","Aachen - Oberhausen","<","Prosper-Levin","Walzwerk",2018,2018,3,3,"20.01.2018","06:00:00","21.01.2018","14:00:00","16 h","nachts, nachmittags, abends/\nnachts, at night, afternoon, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 06:00-14:00 ",null,null,"1BEE1683485F4.02"]
[null,"DB Netz AG","303116.01","Aachen - Oberhausen","< >","Prosper-Levin","Walzwerk",2018,2018,5,6,"03.02.2018","08:00:00","11.02.2018","18:00:00","1 d, 16 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"Sa+So/SSu, jeweils/each 08:00-18:00 ",null,null,"1BEE1760D23D4.01"]
[null,"DB Netz AG","303137.01","Aachen - Oberhausen",">","Walzwerk","Prosper-Levin",2018,2018,9,10,"03.03.2018","06:00:00","10.03.2018","18:00:00","1 d","nachts, nachmittags, abends/\nnachts, at night, afternoon, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 06:00-18:00 ",null,null,"1BEE18C4A31B4.01"]
[null,"DB Netz AG","303137.02","Aachen - Oberhausen","< >","Prosper-Levin","Walzwerk",2018,2018,9,10,"03.03.2018","18:00:00","11.03.2018","06:00:00","1 d","nachmittags, abends, nachts/\nat night, afternoon, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 18:00-06:00 ",null,null,"1BEE18C4A31B4.02"]
[null,"DB Netz AG","303137.03","Aachen - Oberhausen","<","Prosper-Levin","Walzwerk",2018,2018,9,10,"04.03.2018","06:00:00","11.03.2018","18:00:00","1 d","nachts, nachmittags, abends/\nnachts, at night, afternoon, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"So/Su, jeweils/each 06:00-18:00 ",null,null,"1BEE18C4A31B4.03"]
[null,"DB Netz AG","303177.01","Aachen - Oberhausen","< >","Prosper-Levin","Walzwerk",2018,2018,15,16,"09.04.2018","06:00:00","18.04.2018","06:00:00","9 d","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BEE19DE72A94.01"]
[null,"DB Netz AG","303187.01","Aachen - Oberhausen","< >","Prosper-Levin","Walzwerk",2018,2018,16,17,"21.04.2018","08:00:00","29.04.2018","18:00:00","1 d, 16 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"Sa+So/SSu, jeweils/each 08:00-18:00 ",null,null,"1BEE1A7FE7AB4.01"]
[null,"DB Netz AG","303214.01","Aachen - Oberhausen","< >","Prosper-Levin","Walzwerk",2018,2018,21,21,"21.05.2018","08:00:00","21.05.2018","16:00:00","8 h","morgens, nachmittags/\nmorning, afternoon","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BEE1B0690534.01"]
[null,"DB Netz AG","30191","Aachen - Oberhausen",">","M'gladbach Hbf","Krefeld Hbf",2018,2018,2,3,"14.01.2018","23:45:00","19.01.2018","04:35:00","1 d","nachts/\nat night","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"So-Do/MTWThSu, jeweils/each 23:45-04:35 ",null,null,"1C1FAE76443B7.02"]
[null,"DB Netz AG","103064.01","Aachen - Oberhausen","< >","Viersen","Krefeld Hbf",2018,2018,5,6,"04.02.2018","00:15:00","05.02.2018","04:40:00","1 d, 04 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BFB0F1F32317.01"]
[null,"DB Netz AG","30664\nDeleted","Aachen - Oberhausen",">","Viersen","Krefeld Hbf",2018,2018,6,6,"05.02.2018","00:00:00","07.02.2018","04:30:00","14 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:30 ",null,null,"1C388014560F7.03"]
[null,"DB Netz AG","30147","Aachen - Oberhausen",">","Viersen","Krefeld Hbf",2018,2018,6,7,"05.02.2018","22:00:00","15.02.2018","05:20:00","1 d, 20 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"Mo-Mi/MTW, jeweils/each 22:00-05:20 ",null,null,"1BFB0F1F32317.03"]
[null,"DB Netz AG","30664\nDeleted","Aachen - Oberhausen","< >","Viersen","Krefeld Hbf",2018,2018,7,7,"17.02.2018","00:00:00","18.02.2018","04:30:00","1 d, 04 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C388014560F7.04"]
[null,"DB Netz AG","103064.04","Aachen - Oberhausen","< >","Viersen","Krefeld Hbf",2018,2018,7,8,"18.02.2018","00:15:00","19.02.2018","04:40:00","1 d, 04 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BFB0F1F32317.04"]
[null,"DB Netz AG","30664\nDeleted","Aachen - Oberhausen","<","Krefeld Hbf","Viersen",2018,2018,8,8,"19.02.2018","00:00:00","21.02.2018","04:30:00","14 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:30 ",null,null,"1C388014560F7.02"]
[null,"DB Netz AG","30147","Aachen - Oberhausen","<","Krefeld Hbf","Viersen",2018,2018,9,9,"26.02.2018","22:00:00","04.03.2018","05:20:00","1 d, 20 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:20 ",null,null,"1BFB0F1F32317.02"]
[null,"DB Netz AG","103065.01","Aachen - Oberhausen","< >","Viersen","Krefeld Hbf",2018,2018,10,11,"09.03.2018","12:00:00","12.03.2018","04:40:00","2 d, 17 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BFB0FA32F417.01"]
[null,"DB Netz AG","31136\nDeleted","Aachen - Oberhausen",">","Viersen","Krefeld Hbf",2018,2018,16,16,"19.04.2018","22:00:00","21.04.2018","05:20:00","15 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:20 ",null,null,"1C388322BB077.02"]
[null,"DB Netz AG","31136","Aachen - Oberhausen","<","Krefeld Hbf","Viersen",2018,2018,18,18,"30.04.2018","22:00:00","04.05.2018","05:20:00","1 d, 05 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:20 ",null,null,"1C388322BB077.04"]
[null,"DB Netz AG","19E8A8D5A7AD7.01","Aachen - Oberhausen",">","Krefeld Hbf","Krefeld Hbf",2018,2018,31,32,"04.08.2018","00:30:00","09.08.2018","04:30:00","1 d","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:30-04:30 ",null,null,"19E8A8D5A7AD7.01"]
[null,"DB Netz AG","19E8A8D5A7AD7.02","Aachen - Oberhausen",">","Krefeld Hbf","Krefeld Hbf",2018,2018,31,32,"04.08.2018","00:30:00","09.08.2018","04:30:00","5 d, 04 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19E8A8D5A7AD7.02"]
[null,"DB Netz AG","303416.02\nDeleted","Oberhausen - Hannover","< >","Bottrop Süd","Nordstern    /Ge",2017,2017,49,50,"10.12.2017","08:00:00","17.12.2017","18:00:00","3 d, 08 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 08:00-18:00 ",null,null,"1BB224309B474.02"]
[null,"DB Netz AG","303093.02\nDeleted","Oberhausen - Hannover","< >","Bottrop Süd","Nordstern    /Ge",2018,2018,2,12,"08.01.2018","08:00:00","23.03.2018","18:00:00","31 d, 06 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 08:00-18:00 ",null,"X","1BB2252FB6E54.02"]
[null,"DB Netz AG","30604","Oberhausen - Hannover","< >","Bottrop Süd","Bottrop Süd",2018,2018,14,17,"07.04.2018","22:00:00","24.04.2018","06:00:00","16 d, 08 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2F7050DA7D4.01"]
[null,"DB Netz AG","30604","Oberhausen - Hannover","< >","Bottrop Süd","Bottrop Süd",2018,2018,14,17,"07.04.2018","22:00:00","24.04.2018","06:00:00","5 d, 16 h","abends, nachts/\nat night, evening","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"1C2F7050DA7D4.02"]
[null,"DB Netz AG","303178.01\nDeleted","Oberhausen - Hannover","< >","Nordstern    /Ge","Bottrop Süd",2018,2018,15,16,"09.04.2018","08:00:00","22.04.2018","18:00:00","5 d, 20 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 08:00-18:00 ",null,null,"1BB22618B2734.01"]
[null,"DB Netz AG","30604\nDeleted","Oberhausen - Hannover","<","Bottrop Süd","Nordstern    /Ge",2018,2018,15,15,"12.04.2018","08:00:00","13.04.2018","18:00:00","20 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 08:00-18:00 ",null,null,"1C2F7050DA7D4.03"]
[null,"DB Netz AG","30606\nDeleted","Oberhausen - Hannover","< >","Bottrop Süd","Bottrop Süd",2018,2018,15,15,"12.04.2018","08:00:00","13.04.2018","18:00:00","20 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 08:00-18:00 ",null,null,"1C2F73A4ACE54.03"]
[null,"DB Netz AG","30604","Oberhausen - Hannover","< >","Bottrop Süd","Bottrop Süd",2018,2018,15,16,"14.04.2018","08:00:00","16.04.2018","18:00:00","2 d, 10 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2F6CB444274.02"]
[null,"DB Netz AG","30604","Oberhausen - Hannover","<","Bottrop Süd","Nordstern    /Ge",2018,2018,15,17,"14.04.2018","08:00:00","23.04.2018","18:00:00","4 d, 20 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,"Sa-Mo/MSSu",null,null,"1C2F6CB444274.01"]
[null,"DB Netz AG","30604","Oberhausen - Hannover","< >","Bottrop Süd","Bottrop Süd",2018,2018,16,16,"16.04.2018","18:00:00","17.04.2018","12:00:00","18 h","nachmittags, abends, nachts, morgens/\nat night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2F6CB444274.04"]
[null,"DB Netz AG","30604\nDeleted","Oberhausen - Hannover","< >","Bottrop Süd","Bottrop Süd",2018,2018,16,16,"19.04.2018","08:00:00","20.04.2018","18:00:00","20 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 08:00-18:00 ",null,null,"1C2F7050DA7D4.04"]
[null,"DB Netz AG","30606\nDeleted","Oberhausen - Hannover","< >","Bottrop Süd","Bottrop Süd",2018,2018,16,16,"19.04.2018","08:00:00","20.04.2018","18:00:00","20 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 08:00-18:00 ",null,null,"1C2F73A4ACE54.04"]
[null,"DB Netz AG","30604","Oberhausen - Hannover","< >","Bottrop Süd","Bottrop Süd",2018,2018,16,17,"21.04.2018","08:00:00","23.04.2018","18:00:00","2 d, 10 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2F6CB444274.03"]
[null,"DB Netz AG","203328.01\nDeleted","Oberhausen - Hannover","< >","Nordstern    /Ge","Bottrop Süd",2018,2018,17,17,"23.04.2018","08:00:00","26.04.2018","18:00:00","1 d, 16 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 08:00-18:00 ",null,null,"1AC9C1AAE2005.01"]
[null,"DB Netz AG","30604\nDeleted","Oberhausen - Hannover","< >","Bottrop Süd","Bottrop Süd",2018,2018,17,17,"23.04.2018","18:00:00","24.04.2018","12:00:00","18 h","nachmittags, abends, nachts, morgens/\nat night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2F7050DA7D4.05"]
[null,"DB Netz AG","30604","Oberhausen - Hannover","< >","Bottrop Süd","Bottrop Süd",2018,2018,17,17,"23.04.2018","18:00:00","24.04.2018","12:00:00","18 h","nachmittags, abends, nachts, morgens/\nat night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2F6CB444274.05"]
[null,"DB Netz AG","30606\nDeleted","Oberhausen - Hannover","< >","Bottrop Süd","Bottrop Süd",2018,2018,17,17,"23.04.2018","18:00:00","24.04.2018","12:00:00","18 h","nachmittags, abends, nachts, morgens/\nat night, morning, afternoon, evening","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C2F73A4ACE54.05"]
[null,"DB Netz AG","19E81887BE8B4.01","Oberhausen - Hannover","< >","Ob-Osterf Ost","Ob-Osterf Ost",2018,2018,23,33,"07.06.2018","07:00:00","14.08.2018","07:00:00","68 d","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19E81887BE8B4.01"]
[null,"DB Netz AG","19E81676747F4.02","Oberhausen - Hannover","< >","Ob-Osterf West","Ob-Osterf West",2018,2018,23,25,"08.06.2018","22:00:00","18.06.2018","04:30:00","9 d, 07 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19E81676747F4.02"]
[null,"DB Netz AG","19E81AE7E7054.03","Oberhausen - Hannover","< >","Ob-Osterf West","Ob-Osterf West",2018,2018,24,28,"16.06.2018","14:00:00","15.07.2018","20:00:00","6 d, 06 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,"Sa+So/SSu",null,null,"19E81AE7E7054.03"]
[null,"DB Netz AG","19E8217CA9D94.01","Oberhausen - Hannover","< >","Ob-Osterf Ost","Ob-Osterf Ost",2018,2018,25,25,"23.06.2018","12:00:00","24.06.2018","22:00:00","1 d, 10 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19E8217CA9D94.01"]
[null,"DB Netz AG","19E957CF11B54.01","Oberhausen - Hannover","< >","Ob-Osterf Ost","Ob-Osterf Ost",2018,2018,26,26,"30.06.2018","12:00:00","01.07.2018","22:00:00","1 d, 10 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19E957CF11B54.01"]
[null,"DB Netz AG","19E9385792AD4.01","Oberhausen - Hannover","< >","Ob-Osterf Ost","Ob-Osterf Ost",2018,2018,27,28,"06.07.2018","22:00:00","09.07.2018","06:00:00","2 d, 08 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19E9385792AD4.01"]
[null,"DB Netz AG","19E82BCE88354.04","Oberhausen - Hannover","< >","Ob-Osterf Ost","Ob-Osterf Ost",2018,2018,27,30,"07.07.2018","14:00:00","29.07.2018","20:00:00","5 d","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,"Sa+So/SSu",null,null,"19E82BCE88354.04"]
[null,"DB Netz AG","19E93F1EF95F4.01","Oberhausen - Hannover","< >","Ob-Osterf Ost","Ob-Osterf Ost",2018,2018,28,29,"13.07.2018","22:00:00","16.07.2018","05:00:00","2 d, 07 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19E93F1EF95F4.01"]
[null,"DB Netz AG","19E93F1EF95F4.04","Oberhausen - Hannover","< >","Ob-Osterf Ost","Ob-Osterf Ost",2018,2018,28,28,"14.07.2018","14:00:00","15.07.2018","22:00:00","1 d, 08 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19E93F1EF95F4.04"]
[null,"DB Netz AG","19E831D532154.01","Oberhausen - Hannover","< >","Ob-Osterf Ost","Ob-Osterf Ost",2018,2018,29,29,"21.07.2018","06:00:00","22.07.2018","23:59:00","1 d, 18 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19E831D532154.01"]
[null,"DB Netz AG","19E9466907554.01","Oberhausen - Hannover","< >","Ob-Osterf Ost","Ob-Osterf Ost",2018,2018,30,31,"27.07.2018","22:00:00","30.07.2018","06:00:00","2 d, 08 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19E9466907554.01"]
[null,"DB Netz AG","19E94C28EDF94.04","Oberhausen - Hannover","< >","Ob-Osterf Ost","Ob-Osterf Ost",2018,2018,30,32,"28.07.2018","14:00:00","12.08.2018","20:00:00","3 d, 18 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,"Sa+So/SSu",null,null,"19E94C28EDF94.04"]
[null,"DB Netz AG","19E95F554CF14.01","Oberhausen - Hannover","< >","Ob-Osterf Ost","Ob-Osterf Ost",2018,2018,31,31,"04.08.2018","14:00:00","05.08.2018","22:00:00","1 d, 08 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19E95F554CF14.01"]
[null,"DB Netz AG","203220.01","Oberhausen - Hannover","< >","Ob-Osterf Ost","Bottrop Süd",2018,2018,32,33,"10.08.2018","23:00:00","13.08.2018","04:30:00","2 d, 05 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"19E982D5B8AF4.01"]
[null,"DB Netz AG","203220.04","Oberhausen - Hannover","<","Ob-Osterf Ost","Bottrop Hbf-Pbf",2018,2018,32,33,"10.08.2018","23:00:00","13.08.2018","04:30:00","2 d, 05 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19E982D5B8AF4.04"]
[null,"DB Netz AG","30008","Aachen - Oberhausen","< >","Du-Meiderich Ost","Oberh West Stw 1",2017,2017,50,51,"16.12.2017","10:00:00","18.12.2017","11:00:00","2 d, 01 h","ganztags/\nfull day","Schwellenauswechslung/\nsleeper replacement","X",null,null,null,null,null,null,null,null,null,null,null,null,"1B9C763A81A74.02"]
[null,"DB Netz AG","40257","Falkenberg - Horka","< >","Cossebaude","Dre Freibg Str",2017,2017,52,52,"27.12.2017","10:00:00","29.12.2017","16:00:00","2 d, 06 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C7FA22D14B2C.02"]
[null,"DB Netz AG","304053.01\nDeleted","Falkenberg - Horka",">","Königst (Sä) Üst","Bad Schandau",2018,2018,5,12,"03.02.2018","04:00:00","19.03.2018","01:00:00","43 d, 21 h","ganztags/\nfull day","Gleisumbau ohne Schienenwechsel/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1C2B6454FCB67.01"]
[null,"DB Netz AG","19FDBA6C8316D.03\nDeleted","Falkenberg - Horka","< >","Bad Schandau","Königst (Sä) Üst",2018,2018,10,10,"07.03.2018","00:00:00","11.03.2018","04:00:00","20 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:00 ",null,null,"19FDBA6C8316D.03"]
[null,"DB Netz AG","104017.01\nDeleted","Falkenberg - Horka","<","Bad Schandau","Königst (Sä) Üst",2018,2018,12,12,"19.03.2018","22:00:00","25.03.2018","05:00:00","1 d, 18 h","abends, nachts/\nat night, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,"X",null,"jeweils/each 22:00-05:00 ",null,null,"19FD91063BE8D.01"]
[null,"DB Netz AG","40068\nDeleted","Falkenberg - Horka","<","Kurort Rathen","Kurort Rathen",2018,2018,14,19,"03.04.2018","01:00:00","10.05.2018","04:00:00","37 d, 03 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C341AF6301ED.05"]
[null,"DB Netz AG","40069, 40068\nDeleted","Falkenberg - Horka","<","Kurort Rathen","Kurort Rathen",2018,2018,14,19,"03.04.2018","01:00:00","10.05.2018","04:00:00","37 d, 03 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C341D7BD352D.05"]
[null,"DB Netz AG","40070\nDeleted","Falkenberg - Horka","<","Kurort Rathen","Kurort Rathen",2018,2018,14,19,"03.04.2018","01:00:00","10.05.2018","04:00:00","37 d, 03 h","ganztags/\nfull day","Durcharbeitung von Gleisen/\ntrackage maintenance",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C342099314CD.05"]
[null,"DB Netz AG","40068","Falkenberg - Horka","< >","Kurort Rathen","Obervogelgesang",2018,2018,14,19,"03.04.2018","04:00:00","09.05.2018","22:00:00","36 d, 18 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,null,null,"X",null,null,null,null,null,null,null,null,null,"1C34134678C4D.01"]
[null,"DB Netz AG","40068","Falkenberg - Horka","<","Kurort Rathen","Obervogelgesang",2018,2018,14,19,"03.04.2018","04:00:00","09.05.2018","22:00:00","36 d, 18 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C34134678C4D.02"]
[null,"DB Netz AG","304100.01\nDeleted","Falkenberg - Horka","<","Bad Schandau","Königst (Sä) Üst",2018,2018,14,19,"03.04.2018","04:00:00","10.05.2018","01:00:00","36 d, 21 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,"X",null,null,"X",null,null,null,"X","19C6734B1380C.01"]
[null,"DB Netz AG","40068","Falkenberg - Horka","< >","Kurort Rathen","Pirna",2018,2018,14,15,"08.04.2018","00:00:00","14.04.2018","04:00:00","1 d, 04 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:00 ",null,null,"1C341AF6301ED.01"]
[null,"DB Netz AG","19FDBA6C8316D.01\nDeleted","Falkenberg - Horka","< >","Bad Schandau","Königst (Sä) Üst",2018,2018,14,16,"08.04.2018","00:00:00","16.04.2018","04:00:00","1 d, 12 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:00 ",null,null,"19FDBA6C8316D.01"]
[null,"DB Netz AG","204101.02","Falkenberg - Horka","< >","Dre-Reick Abstbf","Dre-Friedrichst",2018,2018,18,18,"05.05.2018","20:30:00","06.05.2018","04:30:00","8 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,"X",null,null,null,null,null,null,null,"19E08287E494D.02"]
[null,"DB Netz AG","40069, 40068","Falkenberg - Horka",">","Obervogelgesang","Kurort Rathen",2018,2018,19,20,"11.05.2018","22:00:00","14.05.2018","05:00:00","21 h","abends, nachts/\nat night, evening","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1C341D7BD352D.03"]
[null,"DB Netz AG","19FDD1369D5CD.01\nDeleted","Falkenberg - Horka",">","Königst (Sä) Üst","Bad Schandau",2018,2018,19,20,"11.05.2018","22:00:00","14.05.2018","05:00:00","21 h","abends, nachts/\nat night, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"19FDD1369D5CD.01"]
[null,"DB Netz AG","40070","Falkenberg - Horka","< >","Kurort Rathen","Obervogelgesang",2018,2018,26,26,"27.06.2018","22:00:00","29.06.2018","05:00:00","14 h","abends, nachts/\nat night, evening","Durcharbeitung von Gleisen/\ntrackage maintenance",null,null,null,"X",null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1C342099314CD.01"]
[null,"DB Netz AG","40070","Falkenberg - Horka","<","Kurort Rathen","Obervogelgesang",2018,2018,26,26,"27.06.2018","22:00:00","29.06.2018","05:00:00","14 h","abends, nachts/\nat night, evening","Durcharbeitung von Gleisen/\ntrackage maintenance",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1C342099314CD.02"]
[null,"DB Netz AG","19FF40F1B6BCD.01","Falkenberg - Horka","<","Königst (Sä) Üst","Kurort Rathen",2018,2018,27,27,"02.07.2018","22:00:00","05.07.2018","05:00:00","21 h","abends, nachts/\nat night, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"19FF40F1B6BCD.01"]
[null,"DB Netz AG","19C673821A6AC.01","Falkenberg - Horka","< >","Kurort Rathen","Kurort Rathen",2018,2018,27,31,"06.07.2018","04:00:00","04.08.2018","01:00:00","28 d, 21 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","19C673821A6AC.01"]
[null,"DB Netz AG","304178.02","Falkenberg - Horka",">","Kurort Rathen","Königst (Sä) Üst",2018,2018,27,31,"06.07.2018","04:00:00","04.08.2018","01:00:00","28 d, 21 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,"X",null,null,"X",null,null,null,"X","19C673821A6AC.02"]
[null,"DB Netz AG","19FF712F0884D.01","Falkenberg - Horka","< >","Bad Schandau","Obervogelgesang",2018,2018,28,29,"15.07.2018","00:00:00","20.07.2018","04:00:00","1 d","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:00 ",null,null,"19FF712F0884D.01"]
[null,"DB Netz AG","19FF7185B8E6D.01","Falkenberg - Horka","< >","Bad Schandau","Obervogelgesang",2018,2018,30,30,"28.07.2018","00:00:00","29.07.2018","04:00:00","8 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:00 ",null,null,"19FF7185B8E6D.01"]
[null,"DB Netz AG","19FF77971126D.01","Falkenberg - Horka","<","Königst (Sä) Üst","Kurort Rathen",2018,2018,31,32,"04.08.2018","22:00:00","08.08.2018","05:00:00","1 d, 04 h","abends, nachts/\nat night, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"19FF77971126D.01"]
[null,"DB Netz AG","19C673920790C.01","Falkenberg - Horka","< >","Kurort Rathen","Kurort Rathen",2018,2018,32,37,"09.08.2018","04:00:00","10.09.2018","01:00:00","31 d, 21 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","19C673920790C.01"]
[null,"DB Netz AG","304201.02","Falkenberg - Horka","<","Königst (Sä) Üst","Kurort Rathen",2018,2018,32,37,"09.08.2018","04:00:00","10.09.2018","01:00:00","31 d, 21 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,"X",null,null,"X",null,null,null,"X","19C673920790C.02"]
[null,"DB Netz AG","19FF7B66AD02D.01","Falkenberg - Horka","< >","Bad Schandau","Obervogelgesang",2018,2018,33,34,"17.08.2018","00:00:00","21.08.2018","04:00:00","20 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:00 ",null,null,"19FF7B66AD02D.01"]
[null,"DB Netz AG","19FF7BD00E8CD.01","Falkenberg - Horka","< >","Bad Schandau","Obervogelgesang",2018,2018,35,36,"30.08.2018","00:00:00","03.09.2018","04:00:00","20 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:00 ",null,null,"19FF7BD00E8CD.01"]
[null,"DB Netz AG","304215.01","Falkenberg - Horka","< >","Schöna","Schöna",2018,2018,36,43,"04.09.2018","07:00:00","28.10.2018","20:00:00","21 d, 03 h","tagsüber/\nduring the day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"Mo-Fr/MTWThF, jeweils/each 07:00-20:00 ",null,"X","19C6739B90F8C.01"]
[null,"DB Netz AG","304214.01","Falkenberg - Horka","< >","Schöna","Schöna",2018,2018,36,49,"04.09.2018","08:00:00","08.12.2018","23:59:00","95 d, 16 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","19C6739AE612C.01"]
[null,"DB Netz AG","304215.02","Falkenberg - Horka","< >","Bad Schandau Gr","Schöna",2018,2018,36,43,"08.09.2018","00:01:00","28.10.2018","23:59:00","51 d","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,null,null,"X",null,null,null,null,null,null,null,null,null,"19C6739B90F8C.02"]
[null,"DB Netz AG","204052.01","Falkenberg - Horka","< >","Dre-Friedrichst","Dre-Reick Abstbf",2018,2018,36,36,"08.09.2018","22:00:00","09.09.2018","06:00:00","8 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,"X",null,null,null,null,null,null,null,"19C9826123E8D.01"]
[null,"DB Netz AG","204118.01","Falkenberg - Horka","< >","Bad Schandau Ost","Bad Schandau Gr",2018,2018,36,37,"09.09.2018","21:45:00","10.09.2018","05:45:00","8 h","abends, nachts/\nat night, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X",null,null,"X",null,null,null,null,"1A06C11505EAD.01"]
[null,"DB Netz AG","304215.03","Falkenberg - Horka","<","Bad Schandau Gr","Schöna",2018,2018,37,43,"10.09.2018","00:01:00","28.10.2018","23:59:00","49 d","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,"X",null,null,"X",null,null,null,"X","19C6739B90F8C.03"]
[null,"DB Netz AG","304215.04","Falkenberg - Horka","< >","Bad Schandau","Bad Schandau",2018,2018,37,49,"10.09.2018","00:03:00","08.12.2018","23:59:00","90 d","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","19C6739B90F8C.04"]
[null,"DB Netz AG","19FF806BC080D.01","Falkenberg - Horka",">","Kurort Rathen","Königst (Sä) Üst",2018,2018,37,37,"10.09.2018","22:00:00","12.09.2018","05:00:00","14 h","abends, nachts/\nat night, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"19FF806BC080D.01"]
[null,"DB Netz AG","204054.01","Falkenberg - Horka","< >","Dre-Friedrichst","Dre Freibg Str",2018,2018,37,37,"14.09.2018","18:00:00","16.09.2018","06:00:00","1 d, 12 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,"X","X",null,"X",null,null,null,null,"19C98447B474D.01"]
[null,"DB Netz AG","1A068731C854D.01","Falkenberg - Horka","<","Obervogelgesang","Pirna",2018,2018,37,38,"14.09.2018","22:00:00","17.09.2018","05:00:00","21 h","abends, nachts/\nat night, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1A068731C854D.01"]
[null,"DB Netz AG","204055.01","Falkenberg - Horka","< >","Cossebaude","Dre Freibg Str",2018,2018,37,38,"16.09.2018","06:00:00","17.09.2018","06:00:00","1 d","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,"X","X",null,"X",null,null,null,null,"19C985037BBED.01"]
[null,"DB Netz AG","304224.01","Falkenberg - Horka",">","Pirna","Obervogelgesang",2018,2018,38,43,"18.09.2018","04:00:00","26.10.2018","01:00:00","37 d, 21 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,"X",null,null,"X",null,null,null,"X","19C673A45710C.01"]
[null,"DB Netz AG","204057.01","Falkenberg - Horka","< >","Dre-Friedrichst","Dre Freibg Str",2018,2018,38,38,"20.09.2018","22:00:00","21.09.2018","22:00:00","1 d","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,"X","X",null,"X",null,null,null,null,"19C98787677ED.01"]
[null,"DB Netz AG","1A069AC5A08ED.01","Falkenberg - Horka","< >","Obervogelgesang","Pirna",2018,2018,39,40,"26.09.2018","00:00:00","02.10.2018","04:00:00","1 d, 04 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:00 ",null,null,"1A069AC5A08ED.01"]
[null,"DB Netz AG","1A069AC5A08ED.02","Falkenberg - Horka","< >","Obervogelgesang","Pirna",2018,2018,40,40,"04.10.2018","00:00:00","06.10.2018","04:00:00","12 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:00 ",null,null,"1A069AC5A08ED.02"]
[null,"DB Netz AG","204121.02","Falkenberg - Horka",">","Bad Schandau Ost","Schöna",2018,2018,42,42,"15.10.2018","09:00:00","16.10.2018","17:00:00","16 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X",null,null,"X",null,"jeweils/each 09:00-17:00 ",null,null,"1A07F9AE99C4D.02"]
[null,"DB Netz AG","204122.02","Falkenberg - Horka",">","Bad Schandau Ost","Schöna",2018,2018,42,42,"17.10.2018","09:00:00","18.10.2018","17:00:00","16 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X",null,null,"X",null,"jeweils/each 09:00-17:00 ",null,null,"1A07FBBBB198D.02"]
[null,"DB Netz AG","204116.01","Falkenberg - Horka","<","Obervogelgesang","Pirna",2018,2018,43,44,"26.10.2018","22:00:00","29.10.2018","05:00:00","21 h","abends, nachts/\nat night, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,"X",null,"jeweils/each 22:00-05:00 ",null,null,"1A069CC22056D.01"]
[null,"DB Netz AG","204051.01","Falkenberg - Horka","< >","Dre-Friedrichst","Dre Freibg Str",2018,2018,43,43,"27.10.2018","21:00:00","28.10.2018","05:00:00","8 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,"X","X",null,"X",null,null,null,null,"19C97AE6D46ED.01"]
[null,"DB Netz AG","204124.01","Falkenberg - Horka","< >","Bad Schandau Ost","Bad Schandau Gr",2018,2018,43,44,"28.10.2018","20:00:00","29.10.2018","04:00:00","8 h","abends, nachts/\nat night, evening","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,"X",null,null,"X",null,null,null,null,"1A0815467760D.01"]
[null,"DB Netz AG","304261.02","Falkenberg - Horka","< >","Schöna","Bad Schandau Gr",2018,2018,44,49,"29.10.2018","00:01:00","08.12.2018","23:59:00","41 d","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,null,null,"X",null,null,null,null,null,null,null,null,null,"19C673BDE608C.02"]
[null,"DB Netz AG","304261.03","Falkenberg - Horka",">","Schöna","Bad Schandau Gr",2018,2018,44,49,"29.10.2018","00:01:00","08.12.2018","23:59:00","41 d","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C673BDE608C.03"]
[null,"DB Netz AG","1A069F485606D.01","Falkenberg - Horka","<","Kurort Rathen","Obervogelgesang",2018,2018,44,44,"29.10.2018","22:00:00","01.11.2018","05:00:00","21 h","abends, nachts/\nat night, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1A069F485606D.01"]
[null,"DB Netz AG","304268.01","Falkenberg - Horka",">","Obervogelgesang","Kurort Rathen",2018,2018,44,49,"02.11.2018","04:00:00","05.12.2018","01:00:00","32 d, 21 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,"X","X",null,"X",null,null,null,"X","19C673C29252C.01"]
[null,"DB Netz AG","1A06A2B016F8D.01","Falkenberg - Horka","< >","Kurort Rathen","Obervogelgesang",2018,2018,45,46,"11.11.2018","00:00:00","17.11.2018","04:00:00","1 d, 04 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:00 ",null,null,"1A06A2B016F8D.01"]
[null,"DB Netz AG","1A06A2B016F8D.02","Falkenberg - Horka","< >","Kurort Rathen","Obervogelgesang",2018,2018,48,48,"26.11.2018","00:00:00","30.11.2018","04:00:00","20 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:00 ",null,null,"1A06A2B016F8D.02"]
[null,"DB Netz AG","1A06A4B66966D.01","Falkenberg - Horka","<","Kurort Rathen","Obervogelgesang",2018,2018,49,49,"05.12.2018","22:00:00","08.12.2018","05:00:00","21 h","abends, nachts/\nat night, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1A06A4B66966D.01"]
[null,"DB Netz AG","304022.01","Hannover - Magdeburg",">","Magdeburg Hbf","Helmstedt",2017,2018,49,49,"10.12.2017","23:00:00","03.12.2018","05:00:00","13 d","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"So/Su, jeweils/each 23:00-05:00 ",null,"X","19C66F43642CC.01"]
[null,"DB Netz AG","304023.01","Hannover - Magdeburg","<","Helmstedt","Magdeburg Hbf",2017,2018,49,49,"10.12.2017","23:00:00","03.12.2018","05:00:00","13 d","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"So/Su, jeweils/each 23:00-05:00 ",null,"X","19C66F43F6A8C.01"]
[null,"DB Netz AG","40023","Hannover - Magdeburg","< >","Magdeburg Hbf","Mg-Sudenburg",2018,2018,3,4,"17.01.2018","23:45:00","22.01.2018","03:45:00","20 h","nachts/\nat night","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:45-03:45 ",null,null,"1BBB1A7A6275F.03"]
[null,"DB Netz AG","40035","Hannover - Magdeburg","< >","Magdeburg Hbf","Mg-Sudenburg",2018,2018,6,6,"05.02.2018","23:45:00","10.02.2018","03:45:00","20 h","nachts/\nat night","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:45-03:45 ",null,null,"1BE6F9D311FDF.03"]
[null,"DB Netz AG","304067.02","Hannover - Magdeburg","< >","Mg-Sudenburg","Magdeburg Hbf",2018,2018,9,9,"03.03.2018","00:30:00","04.03.2018","12:45:00","1 d, 12 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BF9918E25CFF.02"]
[null,"DB Netz AG","304077.01","Hannover - Magdeburg",">","Magdeburg Hbf","Harbke",2018,2018,11,13,"12.03.2018","22:00:00","26.03.2018","05:00:00","4 d, 02 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-05:00 ",null,null,"1BD854C607303.01"]
[null,"DB Netz AG","40287","Hannover - Magdeburg","< >","Eilsleb(b Mg)Gbf","Eilsleb(b Mg)Gbf",2018,2018,15,16,"13.04.2018","18:00:00","16.04.2018","18:00:00","3 d","ganztags/\nfull day","Durcharbeitung von Weichen/\nswitch maintenance",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BC4366D0C8BF.01"]
[null,"DB Netz AG","202392.02","Hannover - Magdeburg","<","Helmstedt","Harbke",2018,2018,23,23,"04.06.2018","22:50:00","06.06.2018","05:50:00","14 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:50-05:50 ",null,null,"1A4C451662645.02"]
[null,"DB Netz AG","202393.02","Hannover - Magdeburg",">","Harbke","Helmstedt",2018,2018,23,24,"09.06.2018","22:50:00","11.06.2018","05:50:00","14 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:50-05:50 ",null,null,"1A4C4CB6D77E5.02"]
[null,"DB Netz AG","1C8B56D02185F.01","Hannover - Magdeburg",">","Dreileben-Drack","Eilsleb(b Mg)Gbf",2018,2018,40,40,"01.10.2018","22:20:00","03.10.2018","04:50:00","13 h","nachts/\nat night","Schleifen von Schienen/\nrail grinding",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:20-04:50 ",null,null,"1C8B56D02185F.01"]
[null,"DB Netz AG","1C8B5856A91BF.01","Hannover - Magdeburg","<","Eilsleb(b Mg)Gbf","Dreileben-Drack",2018,2018,40,40,"03.10.2018","22:10:00","05.10.2018","04:50:00","13 h","nachts/\nat night","Schleifen von Schienen/\nrail grinding",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:10-04:50 ",null,null,"1C8B5856A91BF.01"]
[null,"DB Netz AG","304247.01","Hamburg - Magdeburg","< >","Brunau-Packeb","Salzwedel",2018,2018,42,43,"16.10.2018","23:10:00","26.10.2018","04:50:00","2 d, 09 h","nachts/\nat night","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:10-04:50 ",null,null,"19C673B41362C.01"]
[null,"DB Netz AG","1AA6755443F53.01","Hamburg - Magdeburg","< >","Uelzen Gbf","Wieren",2018,2018,42,43,"16.10.2018","23:30:00","26.10.2018","04:30:00","2 d, 02 h","nachts/\nat night","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:30-04:30 ",null,null,"1AA6755443F53.01"]
[null,"DB Netz AG","204061.01","Hamburg - Magdeburg","< >","Salzwedel Gbf","Brunau-Packeb",2018,2018,42,43,"19.10.2018","23:10:00","22.10.2018","04:50:00","2 d, 06 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"19D0B1AA2FA6B.01"]
[null,"DB Netz AG","304254.01","Hamburg - Magdeburg","< >","Brunau-Packeb","Salzwedel",2018,2018,43,43,"26.10.2018","22:00:00","28.10.2018","20:30:00","1 d, 22 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"19C673B8BFACC.01"]
[null,"DB Netz AG","204060.01","Hamburg - Magdeburg","< >","Stendal Gbf","Uelzen Gbf",2018,2018,43,44,"28.10.2018","20:30:00","29.10.2018","04:30:00","8 h","abends, nachts/\nat night, evening","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,null,null,null,null,null,null,null,null,"19D0AD9FBC50B.01"]
[null,"DB Netz AG","204070.01","Hamburg - Magdeburg","< >","Salzwedel Gbf","Brunau-Packeb",2018,2018,44,45,"30.10.2018","23:10:00","10.11.2018","04:50:00","1 d, 21 h","nachts/\nat night","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"Di-Fr/TWThF, jeweils/each 23:10-04:50 ",null,null,"19D3CF26F764B.01"]
[null,"DB Netz AG","1C610AE42CC3F.01","Magdeburg - Falkenberg","< >","Biederitz","Rodleben",2018,2018,18,25,"02.05.2018","00:10:00","22.06.2018","22:00:00","51 d, 22 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C610AE42CC3F.01"]
[null,"DB Netz AG","304133.01","Magdeburg - Falkenberg","< >","Biederitz","Rodleben",2018,2018,18,25,"02.05.2018","00:10:00","22.06.2018","22:00:00","51 d, 22 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"19C67362D29AC.01"]
[null,"DB Netz AG","1C7F7E608DB3F.02\nDeleted","Magdeburg - Falkenberg","< >","Königsborn","Königsborn",2018,2018,33,34,"17.08.2018","09:00:00","26.08.2018","20:00:00","4 d, 22 h","ganztags/\nfull day","Durcharbeitung von Weichen/\nswitch maintenance",null,"X",null,null,null,null,null,null,null,null,"Fr-So/FSSu",null,null,"1C7F7E608DB3F.02"]
[null,"DB Netz AG","1C7F7E608DB3F.03\nDeleted","Magdeburg - Falkenberg","< >","Gommern","Gommern",2018,2018,33,34,"17.08.2018","09:00:00","26.08.2018","20:00:00","4 d, 22 h","ganztags/\nfull day","Durcharbeitung von Weichen/\nswitch maintenance",null,"X",null,null,null,null,null,null,null,null,"Fr-So/FSSu",null,null,"1C7F7E608DB3F.03"]
[null,"DB Netz AG","204101.03","Falkenberg - Bad Schandau","< >","Dresden Hbf","Dre-Neustadt",2018,2018,18,18,"05.05.2018","20:30:00","06.05.2018","04:30:00","8 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"19E08287E494D.03"]
[null,"DB Netz AG","204159.02","Falkenberg - Bad Schandau",">","Riesa","Zeithain Bogendr",2018,2018,36,37,"07.09.2018","22:00:00","10.09.2018","04:00:00","2 d, 06 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,"X","X",null,"X",null,null,null,null,"1A43C1EA3048C.02"]
[null,"DB Netz AG","204052.02","Falkenberg - Bad Schandau","< >","Dre-Neustadt","Dresden Hbf",2018,2018,36,36,"08.09.2018","22:00:00","09.09.2018","06:00:00","8 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,"X","X",null,"X",null,null,null,null,"19C9826123E8D.02"]
[null,"DB Netz AG","304026.02","Magdeburg - Falkenberg","< >","Roßlau Abzw Ai","Roßlau Gbf Ost",2017,2018,49,49,"10.12.2017","00:00:00","08.12.2018","23:59:00","364 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,"X","1B8CA202F8383.02"]
[null,"DB Netz AG","304026.03","Magdeburg - Falkenberg","< >","Roßlau Gbf Ost","Roßlau Aw",2017,2018,49,49,"10.12.2017","00:00:00","08.12.2018","23:59:00","364 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,"X","1B8CA202F8383.03"]
[null,"DB Netz AG","304026.01","Magdeburg - Falkenberg","< >","Rodleben","Roßlau(Elbe) Gbf",2017,2018,49,49,"10.12.2017","00:00:00","08.12.2018","23:59:00","364 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,"X","1B8CA202F8383.01"]
[null,"DB Netz AG","304015.01","Falkenberg - Horka","< >","Ruhland","Ruhland",2017,2018,49,43,"10.12.2017","00:00:00","27.10.2018","14:00:00","321 d, 14 h","ganztags/\nfull day","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BC4126AEEAE7.01"]
[null,"DB Netz AG","304027.01","Falkenberg - Horka","< >","Knappenrode","Niesky",2017,2018,49,49,"10.12.2017","00:00:00","08.12.2018","23:59:00","364 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,"X","1BC57F300D167.01"]
[null,"DB Netz AG","304028.02","Falkenberg - Horka","< >","Horka Gbf","Niesky",2017,2018,49,49,"10.12.2017","00:00:00","08.12.2018","23:59:00","364 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,"X","1BC5813E49E27.02"]
[null,"DB Netz AG","304046.01","Falkenberg - Horka","< >","Horka Gbf","Horka Gbf",2018,2018,1,13,"02.01.2018","10:00:00","29.03.2018","17:00:00","86 d, 07 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BDB1E9B328A7.01"]
[null,"DB Netz AG","304046.02","Falkenberg - Horka","<","Horka Gbf","Horka Grenze",2018,2018,1,13,"02.01.2018","10:00:00","29.03.2018","17:00:00","86 d, 07 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BDB1E9B328A7.02"]
[null,"DB Netz AG","104032.01","Falkenberg - Horka","< >","Ruhland","Ruhland",2018,2018,2,3,"12.01.2018","22:05:00","17.01.2018","22:05:00","5 d","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BDB4179F8727.01"]
[null,"DB Netz AG","104033.01","Falkenberg - Horka","< >","Ruhland","Ruhland",2018,2018,3,4,"19.01.2018","22:05:00","24.01.2018","21:50:00","5 d","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BDB48A22B6A7.01"]
[null,"DB Netz AG","1C6D0984B9CA3.02","Magdeburg - Falkenberg","< >","Fermerswalde","Fak unt Bf W 26",2018,2018,22,23,"29.05.2018","23:00:00","05.06.2018","03:00:00","8 h","nachts/\nat night","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,"Mo+Di/MT, jeweils/each 23:00-03:00 ",null,null,"1C6D0984B9CA3.02"]
[null,"DB Netz AG","1C6D0984B9CA3.01","Magdeburg - Falkenberg",">","Fak unt Bf W 26","Fermerswalde",2018,2018,22,23,"30.05.2018","03:00:00","04.06.2018","23:00:00","5 d, 20 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1C6D0984B9CA3.01"]
[null,"DB Netz AG","304162.01","Falkenberg - Horka","< >","Horka Gbf","Horka Gbf",2018,2018,24,25,"11.06.2018","07:00:00","22.06.2018","17:00:00","4 d, 04 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"Mo-Fr/MTWThF, jeweils/each 07:00-17:00 ",null,null,"19C673773B36C.01"]
[null,"DB Netz AG","304162.02","Falkenberg - Horka","< >","Horka Grenze","Horka Gbf",2018,2018,24,25,"11.06.2018","07:00:00","22.06.2018","17:00:00","4 d, 04 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"Mo-Fr/MTWThF, jeweils/each 07:00-17:00 ",null,null,"19C673773B36C.02"]
[null,"DB Netz AG","1C74659F55883.01","Magdeburg - Falkenberg","< >","Coswig (Anh) Gbf","Roßlau Aw",2018,2018,24,25,"13.06.2018","00:00:00","22.06.2018","04:00:00","9 d, 04 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C74659F55883.01"]
[null,"DB Netz AG","304166.01","Falkenberg - Horka","< >","Horka Gbf","Horka Gbf",2018,2018,26,26,"25.06.2018","07:00:00","30.06.2018","17:00:00","2 d, 12 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-17:00 ",null,null,"19C67379FF38C.01"]
[null,"DB Netz AG","304166.02","Falkenberg - Horka","< >","Horka Grenze","Horka Gbf",2018,2018,26,26,"25.06.2018","07:00:00","30.06.2018","17:00:00","2 d, 12 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 07:00-17:00 ",null,null,"19C67379FF38C.02"]
[null,"DB Netz AG","304171.01","Falkenberg - Horka","< >","Horka Gbf","Horka Gbf",2018,2018,27,28,"02.07.2018","07:00:00","15.07.2018","17:00:00","13 d, 10 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C6737D6E20C.01"]
[null,"DB Netz AG","304171.02","Falkenberg - Horka","<","Horka Gbf","Horka Grenze",2018,2018,27,28,"02.07.2018","07:00:00","15.07.2018","17:00:00","13 d, 10 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C6737D6E20C.02"]
[null,"DB Netz AG","304189.01","Falkenberg - Horka",">","Horka Grenze","Horka Gbf",2018,2018,29,29,"16.07.2018","07:00:00","22.07.2018","17:00:00","6 d, 10 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C67389EC5EC.01"]
[null,"DB Netz AG","304193.01","Falkenberg - Horka",">","Horka Grenze","Horka Gbf",2018,2018,30,30,"23.07.2018","07:00:00","29.07.2018","17:00:00","2 d, 22 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 07:00-17:00 ",null,null,"19C6738C97F6C.01"]
[null,"DB Netz AG","204158.01","Falkenberg - Horka","<","Ruhland","Schwarzbach b Ru",2018,2018,32,33,"10.08.2018","22:05:00","15.08.2018","21:50:00","5 d","ganztags/\nfull day","Weichenausbau/\nswitch removal",null,"X",null,null,null,null,"X",null,"X",null,null,null,null,"1A439D6F9E74C.01"]
[null,"DB Netz AG","204158.04","Falkenberg - Horka","< >","Schwarzbach b Ru","Ruhland",2018,2018,33,33,"13.08.2018","22:05:00","15.08.2018","21:50:00","2 d","ganztags/\nfull day","Weichenausbau/\nswitch removal","X",null,null,null,null,"X","X",null,"X",null,null,null,null,"1A439D6F9E74C.04"]
[null,"DB Netz AG","1A43A36E458CC.01","Falkenberg - Horka","< >","Ruhland","Ruhland",2018,2018,42,42,"20.10.2018","22:00:00","21.10.2018","16:00:00","18 h","abends, nachts, morgens, nachmittags/\nat night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1A43A36E458CC.01"]
[null,"DB Netz AG","304249.01","Falkenberg - Horka","< >","Hosena","Ruhland",2018,2018,43,43,"22.10.2018","22:00:00","27.10.2018","14:00:00","4 d, 16 h","ganztags/\nfull day","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,null,"X",null,"X",null,null,null,null,"19C673B5692EC.01"]
[null,"DB Netz AG","304250.01","Falkenberg - Horka","< >","Ruhland","Ruhland",2018,2018,43,43,"24.10.2018","22:00:00","26.10.2018","22:00:00","2 d","ganztags/\nfull day","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"19C673B61414C.01"]
[null,"DB Netz AG","304250.02","Falkenberg - Horka","< >","Lauchhammer","Hosena",2018,2018,43,43,"24.10.2018","22:00:00","26.10.2018","22:00:00","2 d","ganztags/\nfull day","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,"X","X",null,"X",null,null,null,null,"19C673B61414C.02"]
[null,"DB Netz AG","304252.03","Falkenberg - Horka","< >","Ruhland","Schwarzkollm",2018,2018,43,43,"26.10.2018","20:00:00","27.10.2018","06:00:00","10 h","abends, nachts/\nat night, evening","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,"X","X",null,"X",null,null,null,null,"19C673B769E0C.03"]
[null,"DB Netz AG","304251.03","Falkenberg - Horka","< >","Hoyerswerda","Lohsa",2018,2018,43,43,"26.10.2018","22:00:00","27.10.2018","14:00:00","16 h","abends, nachts, morgens, nachmittags/\nat night, morning, afternoon, evening","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,"X","X",null,"X",null,null,null,null,"19C673B6BEFAC.03"]
[null,"DB Netz AG","304251.04","Falkenberg - Horka","< >","Lauchhammer","Hosena",2018,2018,43,43,"26.10.2018","22:00:00","27.10.2018","14:00:00","16 h","abends, nachts, morgens, nachmittags/\nat night, morning, afternoon, evening","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,"X","X",null,"X",null,null,null,null,"19C673B6BEFAC.04"]
[null,"DB Netz AG","304251.05","Falkenberg - Horka","< >","Särichen","Horka Grenze",2018,2018,43,43,"26.10.2018","22:00:00","27.10.2018","14:00:00","16 h","abends, nachts, morgens, nachmittags/\nat night, morning, afternoon, evening","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,null,null,null,null,null,null,null,null,"19C673B6BEFAC.05"]
[null,"DB Netz AG","304256.02","Falkenberg - Horka","< >","Horka Grenze","Hoyerswerda",2018,2018,43,44,"26.10.2018","22:00:00","29.10.2018","06:00:00","2 d, 08 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X",null,null,null,null,null,null,null,"19C673BA1578C.02"]
[null,"DB Netz AG","30191","Aachen - Oberhausen","< >","Vie-Helenabrunn","Rheydt Gbf",2018,2018,2,2,"08.01.2018","00:20:00","12.01.2018","05:20:00","1 d, 01 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"Mo-Fr/MTWThF, jeweils/each 00:20-05:20 ",null,null,"1C1FAE76443B7.03"]
[null,"DB Netz AG","30085","Aachen - Oberhausen","< >","Vie-Helenabrunn","Rheydt Gbf",2018,2018,5,6,"04.02.2018","01:00:00","05.02.2018","04:00:00","1 d, 03 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BF6DE281B837.02"]
[null,"DB Netz AG","30192","Aachen - Oberhausen","< >","Vie-Helenabrunn","Rheydt Gbf",2018,2018,16,17,"20.04.2018","01:00:00","23.04.2018","04:00:00","3 d, 03 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C1FBC98E36B7.03"]
[null,"DB Netz AG","30193","Aachen - Oberhausen","< >","Vie-Helenabrunn","Rheydt Gbf",2018,2018,24,25,"15.06.2018","01:00:00","18.06.2018","04:00:00","3 d, 03 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C1FBFBD1F357.05"]
[null,"DB Netz AG","203221.01","Aachen - Oberhausen","< >","Rheydt Gbf","Rheydt Gbf",2018,2018,36,38,"09.09.2018","06:00:00","22.09.2018","22:00:00","13 d, 16 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,"X",null,"X",null,null,null,null,"19EA2BD3BA277.01"]
[null,"DB Netz AG","30194","Aachen - Oberhausen","< >","Vie-Helenabrunn","Rheydt Gbf",2018,2018,44,45,"01.11.2018","01:00:00","05.11.2018","04:00:00","4 d, 03 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C1FC17B896F7.05"]
[null,"DB Netz AG","301025.01","Berlin - Frankurt (O)",">","Bln-Rummels Rgo","Frankfurt (O)",2018,2019,50,50,"12.12.2018","22:55:00","12.12.2019","04:55:00","13 d, 06 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"Mi/W, jeweils/each 22:55-04:55 ",null,"X","1BD3F30CF7E6C.01"]
[null,"DB Netz AG","301077.01","Berlin - Frankurt (O)",">","Bln-Rummels Rgo","Frankfurt (O)",2019,2019,11,13,"11.03.2019","21:00:00","25.03.2019","05:00:00","4 d, 16 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 21:00-05:00 ",null,null,"1BD3F37ABC7CC.01"]
[null,"DB Netz AG","301094.01","Berlin - Frankurt (O)","< >","Fürstenw (Spree)","Fürstenw (Spree)",2019,2019,14,20,"01.04.2019","08:00:00","14.05.2019","16:00:00","43 d, 08 h","ganztags/\nfull day","Gleiserneuerung mit BR und PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F383CBD2C.01"]
[null,"DB Netz AG","301163.01","Berlin - Frankurt (O)","< >","Pillgram","Frankfurt (O)",2019,2019,25,25,"22.06.2019","18:00:00","23.06.2019","04:00:00","10 h","nachmittags, abends, nachts/\nat night, afternoon, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F3A4B2ACC.01"]
[null,"DB Netz AG","301163.03","Berlin - Frankurt (O)","< >","Frankfurt (O)","Oderbrücke",2019,2019,25,25,"22.06.2019","18:00:00","23.06.2019","04:00:00","10 h","nachmittags, abends, nachts/\nat night, afternoon, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F3A4B2ACC.03"]
[null,"DB Netz AG","301165.01","Berlin - Frankurt (O)","< >","Pillgram","Pillgram",2019,2019,25,27,"23.06.2019","04:00:00","06.07.2019","18:00:00","13 d, 14 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F3A5A6D0C.01"]
[null,"DB Netz AG","301165.03","Berlin - Frankurt (O)","<","Frankfurt (O)","Pillgram",2019,2019,25,27,"23.06.2019","04:00:00","06.07.2019","18:00:00","13 d, 14 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,"X","X",null,null,null,null,null,null,"1BD3F3A5A6D0C.03"]
[null,"DB Netz AG","301170.01","Berlin - Frankurt (O)","< >","Frankfurt (O)","Pillgram",2019,2019,27,27,"06.07.2019","18:00:00","07.07.2019","04:00:00","10 h","nachmittags, abends, nachts/\nat night, afternoon, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F3A7F0C0C.01"]
[null,"DB Netz AG","301170.03","Berlin - Frankurt (O)","< >","Frankfurt (O)","Oderbrücke",2019,2019,27,27,"06.07.2019","18:00:00","07.07.2019","04:00:00","10 h","nachmittags, abends, nachts/\nat night, afternoon, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F3A7F0C0C.03"]
[null,"DB Netz AG","301232.01","Berlin - Frankurt (O)",">","Bln-Rummels Rgo","Frankfurt (O)",2019,2019,42,44,"14.10.2019","21:00:00","28.10.2019","05:00:00","4 d, 16 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 21:00-05:00 ",null,null,"1BD3F3C73890C.01"]
[null,"DB Netz AG","304035.01","Magdeburg - Berlin","<","Biederitz","Groß Kreutz",2018,2019,51,50,"18.12.2018","23:00:00","11.12.2019","05:00:00","13 d","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"Di/T, jeweils/each 23:00-05:00 ",null,"X","1BD3F33F9BC4C.01"]
[null,"DB Netz AG","304054.01","Magdeburg - Berlin","< >","Magdeburg Hbf","Mg-Neustadt",2019,2019,6,6,"09.02.2019","23:55:00","10.02.2019","06:00:00","6 h","night time","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F6BBF626C.01"]
[null,"DB Netz AG","304073.01","Magdeburg - Berlin","< >","Magdeburg Hbf","Mg-Neustadt",2019,2019,10,10,"09.03.2019","23:55:00","10.03.2019","10:00:00","10 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F6C6120AC.01"]
[null,"DB Netz AG","304093.01","Magdeburg - Berlin","< >","Magdeburg Hbf","Mg-Neustadt",2019,2019,11,12,"17.03.2019","23:00:00","20.03.2019","05:00:00","18 h","nachts/\nat night","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1BD3F6D0A800C.01"]
[null,"DB Netz AG","304157.01","Magdeburg - Berlin","< >","Magdeburg Hbf","Mg-Neustadt",2019,2019,19,19,"11.05.2019","23:55:00","12.05.2019","12:00:00","12 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F6F05178C.01"]
[null,"DB Netz AG","301029.02","Magdeburg - Berlin","<","Gensh Heide Ost","Eichgestell",2018,2019,50,49,"15.12.2018","22:20:00","08.12.2019","04:20:00","13 d","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 22:20-04:20 ",null,"X","1BD3F30E7E86C.02"]
[null,"DB Netz AG","301155.01","Magdeburg - Berlin","< >","Borkheide","Borkheide",2019,2019,24,26,"11.06.2019","16:00:00","24.06.2019","20:00:00","13 d, 04 h","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F3A0FA86C.01"]
[null,"DB Netz AG","301155.02","Magdeburg - Berlin","< >","Brück (Mark)","Brück (Mark)",2019,2019,24,26,"11.06.2019","20:00:00","24.06.2019","12:00:00","12 d, 16 h","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F3A0FA86C.02"]
[null,"DB Netz AG","301155.03","Magdeburg - Berlin","<","Brück (Mark)","Borkheide",2019,2019,24,26,"11.06.2019","20:00:00","24.06.2019","12:00:00","12 d, 16 h","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F3A0FA86C.03"]
[null,"DB Netz AG","301154.01","Magdeburg - Berlin","< >","Borkheide","Borkheide",2019,2019,24,26,"11.06.2019","23:00:00","24.06.2019","05:00:00","3 d, 06 h","nachts/\nat night","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,"X","1BD3F3A08074C.01"]
[null,"DB Netz AG","301154.02","Magdeburg - Berlin","<","Brück (Mark)","Beelitz Heilst",2019,2019,24,26,"11.06.2019","23:00:00","24.06.2019","05:00:00","3 d, 06 h","nachts/\nat night","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,"X","1BD3F3A08074C.02"]
[null,"DB Netz AG","301167.01","Magdeburg - Berlin","< >","Bad Belzig","Bad Belzig",2019,2019,26,28,"24.06.2019","12:00:00","08.07.2019","04:00:00","13 d, 16 h","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F3A6828AC.01"]
[null,"DB Netz AG","301167.02","Magdeburg - Berlin",">","Brück (Mark)","Bad Belzig",2019,2019,26,28,"24.06.2019","12:00:00","08.07.2019","04:00:00","13 d, 16 h","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F3A6828AC.02"]
[null,"DB Netz AG","301167.04","Magdeburg - Berlin","< >","Brück (Mark)","Brück (Mark)",2019,2019,26,28,"24.06.2019","12:00:00","08.07.2019","06:00:00","13 d, 18 h","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F3A6828AC.04"]
[null,"DB Netz AG","301166.01","Magdeburg - Berlin","< >","Borkheide","Borkheide",2019,2019,26,27,"24.06.2019","23:00:00","07.07.2019","05:00:00","3 d, 06 h","nachts/\nat night","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,"X","1BD3F3A620E2C.01"]
[null,"DB Netz AG","301166.02","Magdeburg - Berlin","< >","Brück (Mark)","Brück (Mark)",2019,2019,26,27,"24.06.2019","23:00:00","07.07.2019","05:00:00","3 d, 06 h","nachts/\nat night","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,"X","1BD3F3A620E2C.02"]
[null,"DB Netz AG","301166.03","Magdeburg - Berlin",">","Borkheide","Bad Belzig",2019,2019,26,27,"24.06.2019","23:00:00","07.07.2019","05:00:00","3 d, 06 h","nachts/\nat night","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,"X","1BD3F3A620E2C.03"]
[null,"DB Netz AG","301179.04","Magdeburg - Berlin","< >","Michendorf","Seddin",2019,2019,30,32,"26.07.2019","09:00:00","11.08.2019","18:00:00","16 d, 09 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F3AC22F8C.04"]
[null,"DB Netz AG","301206.01","Magdeburg - Berlin","<","Beelitz Heilst","Seddin Bla",2019,2019,36,37,"06.09.2019","20:00:00","13.09.2019","20:00:00","7 d","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F3B9ADC4C.01"]
[null,"DB Netz AG","301211.02","Magdeburg - Berlin","<","Borkheide","Seddin Bla",2019,2019,37,40,"13.09.2019","20:00:00","30.09.2019","04:00:00","16 d, 08 h","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F3BCD36EC.02"]
[null,"DB Netz AG","301211.03","Magdeburg - Berlin","< >","Borkheide","Beelitz Heilst",2019,2019,39,40,"27.09.2019","22:00:00","30.09.2019","04:00:00","2 d, 06 h","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F3BCD36EC.03"]
[null,"DB Netz AG","301211.04","Magdeburg - Berlin","< >","Beelitz Heilst","Beelitz Heilst",2019,2019,40,43,"30.09.2019","04:00:00","21.10.2019","12:00:00","21 d, 08 h","ganztags/\nfull day","Gleiserneuerung mit BR/\nTrack renewal with ballast cleaning",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F3BCD36EC.04"]
[null,"DB Netz AG","301250.01","Magdeburg - Berlin","< >","Beelitz Heilst","Seddin Bla",2019,2019,44,44,"28.10.2019","22:00:00","29.10.2019","04:30:00","7 h","abends, nachts/\nat night, evening","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F3CF9D00C.01"]
[null,"DB Netz AG","301250.03","Magdeburg - Berlin","<","Beelitz Heilst","Seddin Bla",2019,2019,44,45,"28.10.2019","22:00:00","04.11.2019","04:00:00","6 d, 06 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F3CF9D00C.03"]
[null,"DB Netz AG","301252.01","Magdeburg - Berlin","< >","Beelitz Heilst","Seddin Bla",2019,2019,44,45,"02.11.2019","08:00:00","04.11.2019","04:00:00","1 d, 20 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F3D09124C.01"]
[null,"DB Netz AG","301253.01","Magdeburg - Berlin",">","Michendorf","Beelitz Heilst",2019,2019,45,46,"04.11.2019","04:00:00","11.11.2019","04:00:00","7 d","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F3D10B36C.01"]
[null,"DB Netz AG","301253.03","Magdeburg - Berlin","< >","Seddin","Beelitz Heilst",2019,2019,45,46,"09.11.2019","08:00:00","11.11.2019","04:00:00","1 d, 20 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F3D10B36C.03"]
[null,"DB Netz AG","304054.03","Hamburg - Magdeburg","< >","Magdeburg Hbf","Mg-Neustadt",2019,2019,6,6,"09.02.2019","23:55:00","10.02.2019","06:00:00","6 h","night time","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F6BBF626C.03"]
[null,"DB Netz AG","304056.01","Hamburg - Magdeburg","< >","Magdeburg Hbf","Mg-Neustadt",2019,2019,6,19,"10.02.2019","06:00:00","11.05.2019","23:55:00","90 d, 18 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,"X","1BD3F6BCEA4AC.01"]
[null,"DB Netz AG","304073.03","Hamburg - Magdeburg","< >","Magdeburg Hbf","Mg-Neustadt",2019,2019,10,10,"09.03.2019","23:55:00","10.03.2019","10:00:00","10 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F6C6120AC.03"]
[null,"DB Netz AG","304093.03","Hamburg - Magdeburg","< >","Magdeburg Hbf","Mg-Neustadt",2019,2019,11,12,"17.03.2019","23:00:00","20.03.2019","05:00:00","18 h","nachts/\nat night","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1BD3F6D0A800C.03"]
[null,"DB Netz AG","304157.03","Hamburg - Magdeburg","< >","Magdeburg Hbf","Mg-Neustadt",2019,2019,19,19,"11.05.2019","23:55:00","12.05.2019","12:00:00","12 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F6F05178C.03"]
[null,"DB Netz AG","304191.03","Hamburg - Magdeburg",">","Stendal","Tangerhütte",2019,2019,21,21,"25.05.2019","13:00:00","26.05.2019","14:00:00","1 d, 01 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F7014B2CC.03"]
[null,"DB Netz AG","304420.01","Hamburg - Magdeburg","< >","Stendal","Stendal",2019,2019,21,27,"25.05.2019","13:00:00","05.07.2019","23:59:00","41 d, 11 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F77A509EC.01"]
[null,"DB Netz AG","304421.01","Hamburg - Magdeburg","< >","Stendal","Stendal",2019,2019,27,28,"06.07.2019","00:01:00","08.07.2019","01:00:00","2 d, 01 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F77ACAB0C.01"]
[null,"DB Netz AG","304421.02","Hamburg - Magdeburg","< >","Stendal","Stendal",2019,2019,27,35,"06.07.2019","00:01:00","30.08.2019","01:00:00","55 d, 01 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F77ACAB0C.02"]
[null,"DB Netz AG","304261.03","Hamburg - Magdeburg",">","Stendal","Tangerhütte",2019,2019,27,27,"07.07.2019","06:00:00","07.07.2019","18:00:00","12 h","nachts, morgens, nachmittags/\nat night, morning, afternoon","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F727278EC.03"]
[null,"DB Netz AG","304314.02","Hamburg - Magdeburg","< >","Stendal","Stendal",2019,2019,35,36,"31.08.2019","01:00:00","02.09.2019","01:00:00","2 d","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F741C314C.02"]
[null,"DB Netz AG","301029.01","Magdeburg - Berlin","<","Saarmund","Gensh Heide Ost",2018,2019,50,49,"15.12.2018","22:20:00","08.12.2019","04:20:00","13 d","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 22:20-04:20 ",null,"X","1BD3F30E7E86C.01"]
[null,"DB Netz AG","301288.01","Magdeburg - Berlin","< >","Saarmund","Michendorf",2019,2019,30,32,"26.07.2019","20:00:00","11.08.2019","20:00:00","16 d","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BEDFD37A4BD1.01"]
[null,"DB Netz AG","301183.04","Magdeburg - Berlin","<","Michendorf","Saarmund",2019,2019,30,32,"26.07.2019","20:00:00","11.08.2019","20:00:00","16 d","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F3AE6CE8C.04"]
[null,"DB Netz AG","301213.01","Magdeburg - Berlin","<","Saarmund","Gensh Heide Ost",2019,2019,38,40,"16.09.2019","21:00:00","30.09.2019","05:00:00","4 d, 16 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 21:00-05:00 ",null,null,"1BD3F3BDC792C.01"]
[null,"DB Netz AG","301312.02","Magdeburg - Berlin","< >","Stadtforst","Eichgestell",2019,2019,28,30,"12.07.2019","22:40:00","25.07.2019","04:50:00","12 d, 06 h","ganztags/\nfull day","Weicheneinbau/\nswitch mounting","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C0C90FA15911.02"]
[null,"DB Netz AG","301312.03","Magdeburg - Berlin","< >","Stadtforst","Eichgestell Nord",2019,2019,28,30,"12.07.2019","22:40:00","25.07.2019","04:50:00","12 d, 06 h","ganztags/\nfull day","Weicheneinbau/\nswitch mounting","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C0C90FA15911.03"]
[null,"DB Netz AG","301234.05","Magdeburg - Berlin","< >","Stadtforst","Eichgestell Nord",2019,2019,42,43,"15.10.2019","04:00:00","24.10.2019","04:00:00","9 d","ganztags/\nfull day","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,null,"X",null,null,null,null,null,null,"1BD3F3C8144AC.05"]
[null,"DB Netz AG","302096.03","Oberhausen - Hannover","< >","Hannover Hbf","Hannover Hbf",2019,2019,14,16,"06.04.2019","01:00:00","15.04.2019","04:00:00","9 d, 03 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F584DF7AC.03"]
[null,"DB Netz AG","302099.05","Oberhausen - Hannover","< >","Hannover Hbf","Hannover Hbf",2019,2019,16,42,"15.04.2019","04:00:00","14.10.2019","04:00:00","182 d","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F5864DB0C.05"]
[null,"DB Netz AG","302183.04","Oberhausen - Hannover","< >","Hannover Hbf","Hannover Hbf",2019,2019,29,29,"15.07.2019","02:00:00","19.07.2019","22:00:00","4 d, 20 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5B18142C.04"]
[null,"DB Netz AG","302014.01","Bremerhaven - Bremen","<","Bremen Hbf","Brh-Speckenbütt",2019,2019,1,49,"05.01.2019","23:00:00","08.12.2019","05:00:00","12 d, 06 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 23:00-05:00 ",null,"X","1BD3F55CB928C.01"]
[null,"DB Netz AG","302137.01","Bremerhaven - Bremen",">","Oldenbüttel","Osterholz-Scharm",2019,2019,22,23,"30.05.2019","04:00:00","03.06.2019","05:00:00","4 d, 01 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F59ACEB6C.01"]
[null,"DB Netz AG","302137.02","Bremerhaven - Bremen",">","Osterholz-Scharm","Bremen-Burg",2019,2019,22,23,"30.05.2019","04:00:00","03.06.2019","05:00:00","4 d, 01 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F59ACEB6C.02"]
[null,"DB Netz AG","302139.01","Bremerhaven - Bremen","< >","Bremen-Burg","Oldenbüttel",2019,2019,22,22,"31.05.2019","00:30:00","01.06.2019","04:30:00","8 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung mit PSS/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 00:30-04:30 ",null,null,"1BD3F59BC2DAC.01"]
[null,"DB Netz AG","302142.01","Bremerhaven - Bremen","< >","Osterholz-Scharm","Osterholz-Scharm",2019,2019,23,23,"03.06.2019","05:00:00","08.06.2019","22:00:00","5 d, 17 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F59D3110C.01"]
[null,"DB Netz AG","302141.01","Bremerhaven - Bremen","< >","Bremen-Burg","Bremen-Burg",2019,2019,23,23,"03.06.2019","07:00:00","08.06.2019","17:00:00","2 d, 12 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,"(So)/MTWThFS, jeweils/each 07:00-17:00 ",null,null,"1BD3F59CB6FEC.01"]
[null,"DB Netz AG","302141.02","Bremerhaven - Bremen","<","Bremen-Burg","Osterholz-Scharm",2019,2019,23,24,"08.06.2019","22:00:00","11.06.2019","05:00:00","2 d, 07 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F59CB6FEC.02"]
[null,"DB Netz AG","302142.03","Bremerhaven - Bremen","< >","Osterholz-Scharm","Osterholz-Scharm",2019,2019,23,24,"08.06.2019","22:00:00","11.06.2019","05:00:00","2 d, 07 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F59D3110C.03"]
[null,"DB Netz AG","302142.04","Bremerhaven - Bremen","<","Bremen-Burg","Osterholz-Scharm",2019,2019,23,24,"08.06.2019","22:00:00","11.06.2019","05:00:00","2 d, 07 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F59D3110C.04"]
[null,"DB Netz AG","302157.01","Bremerhaven - Bremen","< >","Osterholz-Scharm","Osterholz-Scharm",2019,2019,24,25,"12.06.2019","23:00:00","22.06.2019","05:00:00","2 d, 12 h","nachts/\nat night","Weichenerneuerung mit PSS/\n","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1BD3F5A47088C.01"]
[null,"DB Netz AG","302158.01","Bremerhaven - Bremen",">","Oldenbüttel","Osterholz-Scharm",2019,2019,24,25,"15.06.2019","04:00:00","17.06.2019","05:00:00","2 d, 01 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F5A4EA9AC.01"]
[null,"DB Netz AG","302158.02","Bremerhaven - Bremen",">","Osterholz-Scharm","Bremen-Burg",2019,2019,24,25,"15.06.2019","04:00:00","17.06.2019","05:00:00","2 d, 01 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F5A4EA9AC.02"]
[null,"DB Netz AG","302163.03","Bremerhaven - Bremen","< >","Osterholz-Scharm","Osterholz-Scharm",2019,2019,25,25,"17.06.2019","05:00:00","22.06.2019","04:00:00","4 d, 23 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5A74CF4C.03"]
[null,"DB Netz AG","302164.01","Bremerhaven - Bremen","<","Bremen Hbf","Brh-Speckenbütt",2019,2019,25,28,"17.06.2019","23:00:00","12.07.2019","05:00:00","4 d","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"Mo-Do/MTWTh, jeweils/each 23:00-05:00 ",null,null,"1BD3F5A7C706C.01"]
[null,"DB Netz AG","302166.02","Bremerhaven - Bremen","<","Osterholz-Scharm","Oldenbüttel",2019,2019,25,26,"22.06.2019","04:00:00","24.06.2019","05:00:00","2 d, 01 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F5A94DA6C.02"]
[null,"DB Netz AG","302166.04","Bremerhaven - Bremen","< >","Osterholz-Scharm","Osterholz-Scharm",2019,2019,25,26,"22.06.2019","04:00:00","24.06.2019","05:00:00","2 d, 01 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F5A94DA6C.04"]
[null,"DB Netz AG","302169.01","Bremerhaven - Bremen",">","Stubben","Oldenbüttel",2019,2019,26,26,"24.06.2019","23:30:00","29.06.2019","04:20:00","1 d","nachts/\nat night","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,"Mo-Fr/MTWThF, jeweils/each 23:30-04:20 ",null,null,"1BD3F5AABBDCC.01"]
[null,"DB Netz AG","302170.02","Bremerhaven - Bremen","<","Oldenbüttel","Lübberstedt",2019,2019,26,27,"29.06.2019","04:00:00","01.07.2019","05:00:00","2 d, 01 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F5AB35EEC.02"]
[null,"DB Netz AG","302173.02","Bremerhaven - Bremen","< >","Lübberstedt","Lübberstedt",2019,2019,27,27,"01.07.2019","05:00:00","06.07.2019","04:00:00","4 d, 23 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5ACA424C.02"]
[null,"DB Netz AG","302175.01","Bremerhaven - Bremen","< >","Stubben","Stubben",2019,2019,27,28,"06.07.2019","04:00:00","08.07.2019","05:00:00","2 d, 01 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5ADB0B2C.01"]
[null,"DB Netz AG","302175.02","Bremerhaven - Bremen",">","Stubben","Oldenbüttel",2019,2019,27,28,"06.07.2019","04:00:00","08.07.2019","05:00:00","2 d, 01 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F5ADB0B2C.02"]
[null,"DB Netz AG","302178.02","Bremerhaven - Bremen","< >","Lübberstedt","Lübberstedt",2019,2019,28,28,"08.07.2019","05:00:00","13.07.2019","04:00:00","4 d, 23 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5AF1EE8C.02"]
[null,"DB Netz AG","302181.02","Bremerhaven - Bremen","<","Lübberstedt","Stubben",2019,2019,28,29,"13.07.2019","04:00:00","15.07.2019","05:00:00","2 d, 01 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F5B08D1EC.02"]
[null,"DB Netz AG","302009.02","Bremen - Hannover","<","Wunstorf","Poggenhagen",2018,2018,52,1,"27.12.2018","00:05:00","31.12.2018","06:00:00","4 d, 06 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F3240C1AC.02"]
[null,"DB Netz AG","302012.02","Bremen - Hannover",">","Poggenhagen","Wunstorf",2019,2019,1,2,"02.01.2019","18:00:00","07.01.2019","05:00:00","4 d, 11 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F55BC504C.02"]
[null,"DB Netz AG","302012.03","Bremen - Hannover","< >","Wunstorf","Poggenhagen",2019,2019,1,1,"02.01.2019","20:05:00","06.01.2019","05:55:00","1 d, 15 h","abends, nachts/\nat night, evening","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 20:05-05:55 ",null,null,"1BD3F55BC504C.03"]
[null,"DB Netz AG","302016.01","Bremen - Hannover","< >","Wunstorf","Poggenhagen",2019,2019,1,2,"06.01.2019","23:00:00","07.01.2019","05:00:00","6 h","night time","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F55DAD4CC.01"]
[null,"DB Netz AG","302022.01","Bremen - Hannover",">","Bremen Hbf","Wunstorf",2019,2019,1,50,"06.01.2019","23:00:00","09.12.2019","05:00:00","12 d, 06 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"So/Su, jeweils/each 23:00-05:00 ",null,"X","1BD3F56089B8C.01"]
[null,"DB Netz AG","302027.01","Bremen - Hannover","<","Achim","Brm-Sebaldsbrück",2019,2019,2,4,"07.01.2019","06:00:00","21.01.2019","06:00:00","14 d","ganztags/\nfull day","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F562EC12C.01"]
[null,"DB Netz AG","302033.01","Bremen - Hannover",">","Rohrsen/Nienburg","Linsburg",2019,2019,2,2,"08.01.2019","01:00:00","12.01.2019","05:00:00","20 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 01:00-05:00 ",null,null,"1BD3F565E0E8C.01"]
[null,"DB Netz AG","302033.03","Bremen - Hannover","< >","Rohrsen/Nienburg","Linsburg",2019,2019,2,2,"08.01.2019","01:15:00","12.01.2019","04:45:00","17 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:15-04:45 ",null,null,"1BD3F565E0E8C.03"]
[null,"DB Netz AG","302039.01","Bremen - Hannover",">","Rohrsen/Nienburg","Linsburg",2019,2019,3,6,"14.01.2019","01:00:00","06.02.2019","05:00:00","4 d","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 01:00-05:00 ",null,null,"1BD3F568BD54C.01"]
[null,"DB Netz AG","302039.03","Bremen - Hannover","< >","Rohrsen/Nienburg","Linsburg",2019,2019,3,6,"14.01.2019","01:15:00","06.02.2019","04:45:00","3 d, 12 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:15-04:45 ",null,null,"1BD3F568BD54C.03"]
[null,"DB Netz AG","302043.01","Bremen - Hannover",">","Brm-Sebaldsbrück","Achim",2019,2019,4,6,"21.01.2019","06:00:00","06.02.2019","06:00:00","16 d","ganztags/\nfull day","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F56AA59CC.01"]
[null,"DB Netz AG","302047.01","Bremen - Hannover","<","Wunstorf","Bremen Hbf",2019,2019,6,8,"06.02.2019","23:00:00","20.02.2019","05:00:00","3 d, 12 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1BD3F56CA64EC.01"]
[null,"DB Netz AG","302048.01","Bremen - Hannover","< >","Verden (Aller)","Nienburg (Weser)",2019,2019,6,8,"07.02.2019","01:15:00","20.02.2019","04:45:00","2 d, 01 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Planbare kleine Instandhaltung/\nmaintenance work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:15-04:45 ",null,null,"1BD3F56D2060C.01"]
[null,"DB Netz AG","302048.02","Bremen - Hannover","< >","Wunstorf","Nienburg (Weser)",2019,2019,6,8,"07.02.2019","01:30:00","20.02.2019","04:30:00","1 d, 18 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Planbare kleine Instandhaltung/\nmaintenance work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:30-04:30 ",null,null,"1BD3F56D2060C.02"]
[null,"DB Netz AG","302048.03","Bremen - Hannover","< >","Verden (Aller)","Bremen Hbf",2019,2019,6,8,"07.02.2019","01:50:00","20.02.2019","04:15:00","1 d, 10 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Planbare kleine Instandhaltung/\nmaintenance work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:50-04:15 ",null,null,"1BD3F56D2060C.03"]
[null,"DB Netz AG","302023.02","Magdeburg - Berlin","<","Braunschweig Hbf","Helmstedt",2019,2019,1,50,"06.01.2019","23:05:00","09.12.2019","04:30:00","11 d, 01 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"So/Su, jeweils/each 23:05-04:30 ",null,"X","1BD3F56103CAC.02"]
[null,"DB Netz AG","302222.01","Magdeburg - Berlin","<","Braunschweig Hbf","Helmstedt",2019,2019,36,38,"06.09.2019","23:00:00","20.09.2019","05:00:00","3 d, 12 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1BD3F5C4DD50C.01"]
[null,"DB Netz AG","302023.01","Magdeburg - Berlin","<","Lehrte","Groß Gleidingen",2019,2019,1,50,"06.01.2019","23:00:00","09.12.2019","05:00:00","12 d, 06 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"So/Su, jeweils/each 23:00-05:00 ",null,"X","1BD3F56103CAC.01"]
[null,"DB Netz AG","302235.01","Magdeburg - Berlin","<","Lehrte","Groß Gleidingen",2019,2019,38,40,"20.09.2019","23:00:00","30.09.2019","05:00:00","2 d, 12 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1BD3F5CB410EC.01"]
[null,"DB Netz AG","302060.01","Oberhausen - Hannover",">","Wunstorf","Minden (Westf)",2019,2019,8,49,"24.02.2019","00:00:00","08.12.2019","06:00:00","10 d, 12 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"So/Su, jeweils/each 00:00-06:00 ",null,"X","1BD3F572F1A2C.01"]
[null,"DB Netz AG","303066.01","Oberhausen - Hannover",">","Löhne(Westf) Gbf","Herford",2019,2019,9,11,"01.03.2019","22:00:00","15.03.2019","06:00:00","4 d, 16 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"1BD3F4346AAAC.01"]
[null,"DB Netz AG","302096.01","Oberhausen - Hannover","< >","Hannover Hbf","Hannover Hbf",2019,2019,14,16,"06.04.2019","01:00:00","15.04.2019","04:00:00","9 d, 03 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F584DF7AC.01"]
[null,"DB Netz AG","302100.03","Oberhausen - Hannover","<","Löhne(Westf) Pbf","Oeynhausen Abzw",2019,2019,16,33,"15.04.2019","22:50:00","18.08.2019","05:30:00","24 d, 17 h","nachts/\nat night","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"So-Do/MTWThSu, jeweils/each 22:50-05:30 ",null,"X","1BD3F586E02CC.03"]
[null,"DB Netz AG","302100.04","Oberhausen - Hannover","<","Löhne(Westf) Pbf","Oeynhausen Abzw",2019,2019,16,33,"19.04.2019","22:50:00","17.08.2019","06:30:00","5 d, 18 h","nachts, morgens/\nat night, morning","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"Fr/F, jeweils/each 22:50-06:30 ",null,"X","1BD3F586E02CC.04"]
[null,"DB Netz AG","302100.05","Oberhausen - Hannover","<","Löhne(Westf) Pbf","Oeynhausen Abzw",2019,2019,16,33,"20.04.2019","22:50:00","18.08.2019","07:45:00","6 d, 16 h","nachts, morgens/\nat night, morning","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 22:50-07:45 ",null,"X","1BD3F586E02CC.05"]
[null,"DB Netz AG","302116.01","Oberhausen - Hannover","<","Oeynhausen Abzw","Minden (Westf)",2019,2019,18,24,"01.05.2019","23:00:00","11.06.2019","05:30:00","7 d, 20 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"So-Do/MTWThSu, jeweils/each 23:00-05:30 ",null,null,"1BD3F58F8DDAC.01"]
[null,"DB Netz AG","302116.02","Oberhausen - Hannover","< >","Minden (Westf)","Oeynhausen Abzw",2019,2019,18,24,"02.05.2019","00:45:00","11.06.2019","04:40:00","4 d, 18 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Bahnsteigarbeiten/\nplatform work","X",null,null,null,null,null,null,null,null,null,"Mo-Fr/MTWThF, jeweils/each 00:45-04:40 ",null,null,"1BD3F58F8DDAC.02"]
[null,"DB Netz AG","302118.01","Oberhausen - Hannover","<","Oeynhausen Abzw","Minden (Westf)",2019,2019,18,23,"03.05.2019","23:00:00","08.06.2019","05:50:00","1 d, 17 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"Fr/F, jeweils/each 23:00-05:50 ",null,null,"1BD3F59081FEC.01"]
[null,"DB Netz AG","302118.02","Oberhausen - Hannover","< >","Minden (Westf)","Oeynhausen Abzw",2019,2019,18,23,"04.05.2019","02:25:00","08.06.2019","04:40:00","14 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Bahnsteigarbeiten/\nplatform work","X",null,null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 02:25-04:40 ",null,null,"1BD3F59081FEC.02"]
[null,"DB Netz AG","302118.03","Oberhausen - Hannover","<","Oeynhausen Abzw","Minden (Westf)",2019,2019,18,23,"04.05.2019","23:00:00","09.06.2019","07:40:00","2 d, 04 h","nachts, morgens/\nat night, morning","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 23:00-07:40 ",null,null,"1BD3F59081FEC.03"]
[null,"DB Netz AG","302118.04","Oberhausen - Hannover","< >","Minden (Westf)","Oeynhausen Abzw",2019,2019,18,23,"05.05.2019","02:25:00","09.06.2019","06:05:00","22 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Bahnsteigarbeiten/\nplatform work","X",null,null,null,null,null,null,null,null,null,"So/Su, jeweils/each 02:25-06:05 ",null,null,"1BD3F59081FEC.04"]
[null,"DB Netz AG","302213.03","Oberhausen - Hannover","<","Löhne(Westf) Pbf","Minden (Westf)",2019,2019,33,41,"18.08.2019","22:50:00","11.10.2019","05:30:00","11 d, 03 h","nachts/\nat night","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"So-Do/MTWThSu, jeweils/each 22:50-05:30 ",null,"X","1BD3F5C092AEC.03"]
[null,"DB Netz AG","302213.04","Oberhausen - Hannover","<","Löhne(Westf) Pbf","Minden (Westf)",2019,2019,34,40,"23.08.2019","22:50:00","05.10.2019","06:30:00","2 d, 06 h","nachts, morgens/\nat night, morning","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"Fr/F, jeweils/each 22:50-06:30 ",null,"X","1BD3F5C092AEC.04"]
[null,"DB Netz AG","302213.05","Oberhausen - Hannover","<","Löhne(Westf) Pbf","Minden (Westf)",2019,2019,34,40,"24.08.2019","22:50:00","06.10.2019","07:45:00","2 d, 14 h","nachts, morgens/\nat night, morning","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 22:50-07:45 ",null,"X","1BD3F5C092AEC.05"]
[null,"DB Netz AG","303198.01","Oberhausen - Hannover",">","Löhne(Westf) Gbf","Herford",2019,2019,36,38,"06.09.2019","22:00:00","20.09.2019","06:00:00","4 d, 16 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"1BD3F47C52DEC.01"]
[null,"DB Netz AG","302096.04","Oberhausen - Hannover","< >","Hannover Hbf","Hannover Hbf",2019,2019,14,16,"06.04.2019","01:00:00","15.04.2019","04:00:00","9 d, 03 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F584DF7AC.04"]
[null,"DB Netz AG","302159.01","Oberhausen - Hannover","< >","Hannover Hbf","Hannover Hbf",2019,2019,24,25,"15.06.2019","08:00:00","17.06.2019","17:00:00","2 d, 09 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5A564ACC.01"]
[null,"DB Netz AG","302185.02","Oberhausen - Hannover","< >","Han Hbf Pferdet","Han Hbf Pferdet",2019,2019,29,31,"19.07.2019","17:00:00","31.07.2019","17:00:00","12 d","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5B27566C.02"]
[null,"DB Netz AG","302336.04","Oberhausen - Hannover","< >","Waldheim","Waldhausen",2018,2018,52,52,"27.12.2018","00:00:00","27.12.2018","10:00:00","10 h","nachts, morgens/\nat night, morning","Gleisumbau ohne Schienenwechsel/\n","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C0563C3F1C74.05"]
[null,"DB Netz AG","302336.01","Oberhausen - Hannover","< >","Waldhausen","Ha-Li/Fischerhof",2018,2019,52,1,"27.12.2018","00:00:00","02.01.2019","05:00:00","6 d, 05 h","ganztags/\nfull day","Gleisumbau ohne Schienenwechsel/\n","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C0563C3F1C74.01"]
[null,"DB Netz AG","302009.03","Oberhausen - Hannover","< >","Wunstorf","Wunstorf",2018,2019,52,2,"27.12.2018","00:05:00","07.01.2019","05:00:00","11 d, 05 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F3240C1AC.03"]
[null,"DB Netz AG","302012.04","Oberhausen - Hannover","< >","Gümmerwald","Wunstorf",2019,2019,1,1,"02.01.2019","20:05:00","06.01.2019","05:55:00","1 d, 15 h","abends, nachts/\nat night, evening","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 20:05-05:55 ",null,null,"1BD3F55BC504C.04"]
[null,"DB Netz AG","302016.02","Oberhausen - Hannover","< >","Gümmerwald","Wunstorf",2019,2019,1,2,"06.01.2019","23:00:00","07.01.2019","05:00:00","6 h","night time","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F55DAD4CC.02"]
[null,"DB Netz AG","302030.01","Oberhausen - Hannover","<","Waldheim","Lehrte West",2019,2019,2,50,"07.01.2019","05:00:00","09.12.2019","11:00:00","12 d, 06 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"Mo/M, jeweils/each 05:00-11:00 ",null,"X","1BD3F5645A48C.01"]
[null,"DB Netz AG","302030.02","Oberhausen - Hannover","<","Seelze West","Waldhausen",2019,2019,2,50,"07.01.2019","05:40:00","09.12.2019","11:40:00","12 d, 06 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"Mo/M, jeweils/each 05:40-11:40 ",null,"X","1BD3F5645A48C.02"]
[null,"DB Netz AG","302037.01","Oberhausen - Hannover",">","Seelze West","Wunstorf",2019,2019,2,3,"12.01.2019","12:00:00","14.01.2019","14:00:00","2 d, 02 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F567C930C.01"]
[null,"DB Netz AG","302037.02","Oberhausen - Hannover","< >","Wunstorf","Gümmerwald",2019,2019,2,3,"12.01.2019","22:00:00","14.01.2019","08:00:00","20 h","abends, nachts, morgens/\nat night, morning, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 22:00-08:00 ",null,null,"1BD3F567C930C.02"]
[null,"DB Netz AG","302040.01","Oberhausen - Hannover","<","Wunstorf","Seelze West",2019,2019,3,4,"19.01.2019","12:00:00","21.01.2019","14:00:00","2 d, 02 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5693766C.01"]
[null,"DB Netz AG","302040.02","Oberhausen - Hannover","< >","Gümmerwald","Wunstorf",2019,2019,3,4,"19.01.2019","22:00:00","21.01.2019","08:00:00","20 h","abends, nachts, morgens/\nat night, morning, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 22:00-08:00 ",null,null,"1BD3F5693766C.02"]
[null,"DB Netz AG","302044.01","Oberhausen - Hannover",">","Seelze West","Wunstorf",2019,2019,4,5,"26.01.2019","12:00:00","28.01.2019","14:00:00","2 d, 02 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F56B3818C.01"]
[null,"DB Netz AG","302044.02","Oberhausen - Hannover","< >","Wunstorf","Gümmerwald",2019,2019,4,5,"26.01.2019","22:00:00","28.01.2019","08:00:00","20 h","abends, nachts, morgens/\nat night, morning, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 22:00-08:00 ",null,null,"1BD3F56B3818C.02"]
[null,"DB Netz AG","302045.01","Oberhausen - Hannover","<","Wunstorf","Seelze West",2019,2019,5,6,"02.02.2019","12:00:00","04.02.2019","14:00:00","2 d, 02 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F56BB22AC.01"]
[null,"DB Netz AG","302045.02","Oberhausen - Hannover","< >","Gümmerwald","Wunstorf",2019,2019,5,6,"02.02.2019","22:00:00","04.02.2019","08:00:00","20 h","abends, nachts, morgens/\nat night, morning, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 22:00-08:00 ",null,null,"1BD3F56BB22AC.02"]
[null,"DB Netz AG","302223.01","Oberhausen - Hannover",">","Seelze West","Wunstorf",2019,2019,36,37,"07.09.2019","12:00:00","09.09.2019","14:00:00","2 d, 02 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5C56FCCC.01"]
[null,"DB Netz AG","302223.02","Oberhausen - Hannover","< >","Wunstorf","Gümmerwald",2019,2019,36,37,"07.09.2019","22:00:00","09.09.2019","08:00:00","20 h","abends, nachts, morgens/\nat night, morning, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 22:00-08:00 ",null,null,"1BD3F5C56FCCC.02"]
[null,"DB Netz AG","302228.01","Oberhausen - Hannover","<","Wunstorf","Seelze West",2019,2019,37,38,"14.09.2019","12:00:00","16.09.2019","14:00:00","2 d, 02 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5C7D226C.01"]
[null,"DB Netz AG","302228.02","Oberhausen - Hannover","< >","Gümmerwald","Wunstorf",2019,2019,37,38,"14.09.2019","22:00:00","16.09.2019","08:00:00","20 h","abends, nachts, morgens/\nat night, morning, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 22:00-08:00 ",null,null,"1BD3F5C7D226C.02"]
[null,"DB Netz AG","302069.02","Löhne - Bad Bentheim",">","Osnabrück Hbf Pu","Lotte(Tecklenbg)",2019,2019,10,10,"04.03.2019","00:00:00","10.03.2019","05:00:00","1 d, 11 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,"jeweils/each 00:00-05:00 ",null,null,"1BD3F57754AEC.02"]
[null,"DB Netz AG","302069.03","Löhne - Bad Bentheim","<","Lotte(Tecklenbg)","Osnabrück Hbf Pu",2019,2019,10,11,"10.03.2019","23:00:00","15.03.2019","05:00:00","1 d, 06 h","nachts/\nat night","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,"jeweils/each 23:00-05:00 ",null,null,"1BD3F57754AEC.03"]
[null,"DB Netz AG","302075.02","Löhne - Bad Bentheim",">","Osnabrück Hbf Pu","Lotte(Tecklenbg)",2019,2019,11,12,"16.03.2019","00:00:00","20.03.2019","05:00:00","1 d, 01 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,"jeweils/each 00:00-05:00 ",null,null,"1BD3F57A311AC.02"]
[null,"DB Netz AG","302075.03","Löhne - Bad Bentheim","<","Lotte(Tecklenbg)","Osnabrück Hbf Pu",2019,2019,12,12,"20.03.2019","23:00:00","22.03.2019","05:00:00","12 h","nachts/\nat night","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,"jeweils/each 23:00-05:00 ",null,null,"1BD3F57A311AC.03"]
[null,"DB Netz AG","302344.03","Löhne - Bad Bentheim",">","Osnabrück Hbf Pu","Lotte(Tecklenbg)",2019,2019,22,22,"27.05.2019","03:05:00","29.05.2019","03:05:00","2 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BF6AA7258D9A.03"]
[null,"DB Netz AG","302135.03","Löhne - Bad Bentheim",">","Osnabrück Hbf Pu","Lotte(Tecklenbg)",2019,2019,22,22,"29.05.2019","03:05:00","30.05.2019","02:05:00","23 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,null,"1BD3F599DA92C.03"]
[null,"DB Netz AG","302138.04","Löhne - Bad Bentheim",">","Osnabrück Hbf Pu","Lotte(Tecklenbg)",2019,2019,22,23,"30.05.2019","02:05:00","03.06.2019","02:05:00","4 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,null,"1BD3F59B48C8C.04"]
[null,"DB Netz AG","302136.01","Löhne - Bad Bentheim","< >","Lotte(Tecklenbg)","Osnabrück Hbf Pu",2019,2019,22,22,"02.06.2019","00:15:00","02.06.2019","05:50:00","6 h","nachts/\nat night","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,null,"1BD3F59A54A4C.01"]
[null,"DB Netz AG","302144.04","Löhne - Bad Bentheim","<","Lotte(Tecklenbg)","Osn-Eversburg",2019,2019,23,25,"04.06.2019","03:05:00","19.06.2019","02:05:00","14 d, 23 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,null,"1BD3F59E2534C.04"]
[null,"DB Netz AG","302146.02","Löhne - Bad Bentheim","< >","Osnabrück Hbf Pu","Lotte(Tecklenbg)",2019,2019,23,24,"09.06.2019","00:30:00","11.06.2019","05:30:00","15 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,"jeweils/each 00:30-05:30 ",null,null,"1BD3F59F1958C.02"]
[null,"DB Netz AG","302160.02","Löhne - Bad Bentheim","< >","Osnabrück Hbf Pu","Lotte(Tecklenbg)",2019,2019,24,25,"16.06.2019","00:30:00","17.06.2019","05:30:00","10 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,"jeweils/each 00:30-05:30 ",null,null,"1BD3F5A5DEBEC.02"]
[null,"DB Netz AG","302345.01","Löhne - Bad Bentheim","<","Lotte(Tecklenbg)","Osn-Eversburg",2019,2019,25,25,"19.06.2019","02:05:00","23.06.2019","02:05:00","4 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BF6BC0CA621A.04"]
[null,"DB Netz AG","302224.01","Löhne - Bad Bentheim",">","Osnabrück Hbf Pu","Velpe (Westf)",2019,2019,36,37,"07.09.2019","04:00:00","09.09.2019","05:00:00","2 d, 01 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,"X","X",null,"X",null,null,null,null,"1BD3F5C5E9DEC.01"]
[null,"DB Netz AG","302351.03","Löhne - Bad Bentheim","<","Lotte(Tecklenbg)","Osnabrück Hbf Pu",2019,2019,37,37,"09.09.2019","05:00:00","10.09.2019","03:05:00","22 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BF6C48A4371A.03"]
[null,"DB Netz AG","302225.03","Löhne - Bad Bentheim","<","Lotte(Tecklenbg)","Osnabrück Hbf Pu",2019,2019,37,37,"10.09.2019","03:05:00","13.09.2019","02:05:00","2 d, 23 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,"X",null,null,null,null,"1BD3F5C663F0C.03"]
[null,"DB Netz AG","302226.03","Löhne - Bad Bentheim","< >","Osnabrück Hbf Pu","Osnabrück Hbf Pu",2019,2019,37,37,"13.09.2019","18:00:00","14.09.2019","18:00:00","1 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5C6DE02C.03"]
[null,"DB Netz AG","302226.05","Löhne - Bad Bentheim","< >","Osnabrück Hbf Pu","Osnabrück Hbf Pu",2019,2019,37,37,"14.09.2019","18:00:00","15.09.2019","18:00:00","1 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5C6DE02C.05"]
[null,"DB Netz AG","302229.02","Löhne - Bad Bentheim","< >","Osnabrück Hbf Pu","Lotte(Tecklenbg)",2019,2019,37,37,"15.09.2019","00:10:00","15.09.2019","05:50:00","6 h","nachts/\nat night","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,"X",null,null,null,null,"1BD3F5C84C38C.02"]
[null,"DB Netz AG","303001.02","Hannover - Magdeburg","< >","Bielefeld Vorbf","Brackwede Gbf",2018,2019,49,11,"09.12.2018","00:01:00","15.03.2019","22:00:00","96 d, 22 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,"X","1BD3F30EF898C.02"]
[null,"DB Netz AG","303017.02","Hannover - Magdeburg","<","Hamm Rbf Hvn","Neubeckum Gbf",2019,2019,2,2,"07.01.2019","23:30:00","10.01.2019","04:30:00","15 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:30-04:30 ",null,null,"1BD3F3FE88B8C.02"]
[null,"DB Netz AG","303025.02","Hannover - Magdeburg","< >","Oelde","Oelde",2019,2019,2,3,"12.01.2019","23:10:00","15.01.2019","06:10:00","14 h","nachts, morgens/\nat night, morning","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"Sa+Mo/MS, jeweils/each 23:10-06:10 ",null,null,"1BD3F409E1FEC.02"]
[null,"DB Netz AG","303054.01","Hannover - Magdeburg",">","Löhne(Westf) Gbf","Hamm Rbf Hvn",2019,2019,7,9,"15.02.2019","22:00:00","01.03.2019","06:00:00","4 d, 16 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"1BD3F42E80FEC.01"]
[null,"DB Netz AG","303055.01","Hannover - Magdeburg","<","Hamm Rbf Hvn","Neubeckum Gbf",2019,2019,7,11,"15.02.2019","23:00:00","15.03.2019","22:00:00","27 d, 23 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F42EE2A6C.01"]
[null,"DB Netz AG","303418.01","Hannover - Magdeburg","< >","Bielefeld Vorbf","Bielefeld Vorbf",2019,2019,9,11,"25.02.2019","08:00:00","11.03.2019","22:00:00","14 d, 14 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BFC8E4098AFE.01"]
[null,"DB Netz AG","303072.02","Hannover - Magdeburg","< >","Brackwede","Brake (b Bielef)",2019,2019,11,11,"15.03.2019","22:00:00","17.03.2019","06:00:00","16 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"1BD3F437D992C.02"]
[null,"DB Netz AG","303075.03","Hannover - Magdeburg","< >","Brake (b Bielef)","Brackwede",2019,2019,11,12,"17.03.2019","20:00:00","18.03.2019","04:00:00","8 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F43947C8C.03"]
[null,"DB Netz AG","303205.01","Hannover - Magdeburg",">","Löhne(Westf) Gbf","Hamm Rbf Hvn",2019,2019,38,40,"20.09.2019","22:00:00","04.10.2019","06:00:00","4 d, 16 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"1BD3F4803BD8C.01"]
[null,"DB Netz AG","303222.05","Hannover - Magdeburg","< >","Brake (b Bielef)","Brackwede",2019,2019,41,41,"11.10.2019","22:00:00","13.10.2019","06:00:00","16 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"1BD3F48A57BCC.05"]
[null,"DB Netz AG","303228.01","Hannover - Magdeburg","< >","Brake (b Bielef)","Brackwede",2019,2019,41,42,"13.10.2019","20:00:00","14.10.2019","04:00:00","8 h","abends, nachts/\nat night, evening","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F48DAE3AC.01"]
[null,"DB Netz AG","302086.01","Wilhelmshaven - Bremen","< >","Oldb (Oldb) Hbf","Kayhauserfeld",2019,2019,13,14,"30.03.2019","23:30:00","06.04.2019","04:30:00","6 d, 05 h","ganztags/\nfull day","Durchlassarbeiten/\npassage work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F5801AC6C.01"]
[null,"DB Netz AG","302102.01","Wilhelmshaven - Bremen","<","Hude","Bookholzberg",2019,2019,16,16,"16.04.2019","01:00:00","17.04.2019","01:00:00","1 d","ganztags/\nfull day","Weichenausbau/\nswitch removal",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F587D450C.01"]
[null,"DB Netz AG","302103.02","Wilhelmshaven - Bremen",">","Hude","Wüsting",2019,2019,16,16,"17.04.2019","01:00:00","19.04.2019","05:00:00","2 d, 04 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5884E62C.02"]
[null,"DB Netz AG","302105.01","Wilhelmshaven - Bremen","<","Old-Hemmelsberg","Hude",2019,2019,16,17,"19.04.2019","05:00:00","23.04.2019","01:00:00","3 d, 20 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5894286C.01"]
[null,"DB Netz AG","302108.02","Wilhelmshaven - Bremen",">","Wüsting","Oldb (Oldb) Hbf",2019,2019,17,17,"23.04.2019","01:00:00","25.04.2019","05:00:00","2 d, 04 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F58AB0BCC.02"]
[null,"DB Netz AG","302111.03","Wilhelmshaven - Bremen","< >","Bookholzberg","Bookholzberg",2019,2019,17,20,"26.04.2019","01:00:00","17.05.2019","05:00:00","21 d, 04 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F58C1EF2C.03"]
[null,"DB Netz AG","302111.04","Wilhelmshaven - Bremen","< >","Delmenhorst Df","Delmenhorst Df",2019,2019,17,20,"26.04.2019","01:00:00","17.05.2019","05:00:00","21 d, 04 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F58C1EF2C.04"]
[null,"DB Netz AG","302112.01","Wilhelmshaven - Bremen","<","Bookholzberg","Delmenhorst",2019,2019,17,20,"26.04.2019","01:00:00","17.05.2019","05:00:00","21 d, 04 h","ganztags/\nfull day","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F58C9904C.01"]
[null,"DB Netz AG","302112.04","Wilhelmshaven - Bremen","<","Hude","Delmenhorst",2019,2019,17,20,"27.04.2019","00:00:00","17.05.2019","04:00:00","3 d, 12 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Gleiserneuerung mit BR, PSS und TE/\n",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:00-04:00 ",null,null,"1BD3F58C9904C.04"]
[null,"DB Netz AG","302122.02","Wilhelmshaven - Bremen","<","Bremen-Neustadt","Bremen Hbf",2019,2019,20,21,"17.05.2019","22:00:00","20.05.2019","04:00:00","2 d, 06 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5938F3EC.02"]
[null,"DB Netz AG","302167.02","Wilhelmshaven - Bremen",">","Wüsting","Oldb (Oldb) Hbf",2019,2019,25,34,"23.06.2019","00:30:00","25.08.2019","06:40:00","2 d, 14 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"So/Su, jeweils/each 00:30-06:40 ",null,null,"1BD3F5A9C7B8C.02"]
[null,"DB Netz AG","302167.04","Wilhelmshaven - Bremen",">","Wüsting","Oldb (Oldb) Hbf",2019,2019,25,35,"23.06.2019","23:00:00","26.08.2019","04:40:00","2 d, 09 h","nachts/\nat night","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"So/Su, jeweils/each 23:00-04:40 ",null,null,"1BD3F5A9C7B8C.04"]
[null,"DB Netz AG","302056.01","Löhne - Bad Bentheim","< >","Lingen (Ems)","Salzbergen",2019,2019,8,10,"20.02.2019","06:00:00","06.03.2019","05:00:00","13 d, 23 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,"X","X",null,"X",null,null,null,null,"1BD3F571095AC.01"]
[null,"DB Netz AG","302056.02","Löhne - Bad Bentheim","< >","Salzbergen","Lingen (Ems)",2019,2019,8,10,"20.02.2019","06:00:00","06.03.2019","05:00:00","13 d, 23 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,"X","X",null,"X",null,null,null,null,"1BD3F571095AC.02"]
[null,"DB Netz AG","302002.01","Wilhelmshaven - Bremen",">","Schwarzer Rabe","Sande",2018,2019,49,27,"09.12.2018","00:00:00","07.07.2019","23:59:00","211 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F320FEDAC.01"]
[null,"DB Netz AG","302002.03","Wilhelmshaven - Bremen","< >","Sande","Sande",2018,2019,49,35,"09.12.2018","00:00:00","31.08.2019","17:00:00","265 d, 17 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F320FEDAC.03"]
[null,"DB Netz AG","302265.02","Wilhelmshaven - Bremen","< >","Ofenerdiek","Ofenerdiek",2018,2018,49,50,"09.12.2018","20:00:00","16.12.2018","06:00:00","6 d, 10 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F8C40008C.02"]
[null,"DB Netz AG","302265.03","Wilhelmshaven - Bremen","< >","Oldb (Oldb) Hbf","Rastede",2018,2018,50,50,"10.12.2018","00:00:00","10.12.2018","06:00:00","6 h","nachts/\nat night","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F8C40008C.03"]
[null,"DB Netz AG","302266.01","Wilhelmshaven - Bremen","< >","Rastede","Oldb (Oldb) Hbf",2018,2018,50,50,"15.12.2018","18:00:00","16.12.2018","06:00:00","12 h","nachmittags, abends, nachts/\nat night, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F8C47A1AC.01"]
[null,"DB Netz AG","302026.01","Wilhelmshaven - Bremen",">","Oldb (Oldb) Hbf","Ofenerdiek",2019,2019,2,3,"07.01.2019","08:00:00","19.01.2019","17:00:00","4 d, 12 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,"(So)/MTWThFS, jeweils/each 08:00-17:00 ",null,null,"1BD3F5627200C.01"]
[null,"DB Netz AG","302041.01","Wilhelmshaven - Bremen","< >","Sande","Varel (Oldb)",2019,2019,3,27,"19.01.2019","05:00:00","06.07.2019","23:59:00","19 d, 19 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 05:00-23:59 ",null,"X","1BD3F569B178C.01"]
[null,"DB Netz AG","302041.02","Wilhelmshaven - Bremen","< >","Sande","Varel (Oldb)",2019,2019,3,27,"20.01.2019","05:00:00","07.07.2019","23:59:00","19 d, 19 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"So/Su, jeweils/each 05:00-23:59 ",null,"X","1BD3F569B178C.02"]
[null,"DB Netz AG","302042.01","Wilhelmshaven - Bremen","<","Ofenerdiek","Oldb (Oldb) Hbf",2019,2019,4,5,"21.01.2019","08:00:00","02.02.2019","17:00:00","4 d, 12 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,"(So)/MTWThFS, jeweils/each 08:00-17:00 ",null,null,"1BD3F56A2B8AC.01"]
[null,"DB Netz AG","302046.01","Wilhelmshaven - Bremen",">","Ofenerdiek","Rastede",2019,2019,6,6,"04.02.2019","08:00:00","09.02.2019","17:00:00","2 d, 06 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,"(So)/MTWThFS, jeweils/each 08:00-17:00 ",null,null,"1BD3F56C2C3CC.01"]
[null,"DB Netz AG","302050.01","Wilhelmshaven - Bremen","<","Rastede","Ofenerdiek",2019,2019,7,7,"11.02.2019","08:00:00","16.02.2019","17:00:00","2 d, 06 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,"(So)/MTWThFS, jeweils/each 08:00-17:00 ",null,null,"1BD3F56E1484C.01"]
[null,"DB Netz AG","302055.01","Wilhelmshaven - Bremen",">","Oldb (Oldb) Hbf","Ofenerdiek",2019,2019,8,9,"18.02.2019","04:00:00","28.02.2019","04:00:00","10 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5708F48C.01"]
[null,"DB Netz AG","302062.01","Wilhelmshaven - Bremen",">","Ofenerdiek","Rastede",2019,2019,9,10,"28.02.2019","04:00:00","09.03.2019","04:00:00","9 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F573E5C6C.01"]
[null,"DB Netz AG","302070.01","Wilhelmshaven - Bremen","<","Rastede","Ofenerdiek",2019,2019,10,12,"09.03.2019","04:00:00","18.03.2019","04:00:00","9 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F577CEC0C.01"]
[null,"DB Netz AG","302076.01","Wilhelmshaven - Bremen","<","Ofenerdiek","Oldb (Oldb) Hbf",2019,2019,12,13,"18.03.2019","04:00:00","28.03.2019","04:00:00","10 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F57AAB2CC.01"]
[null,"DB Netz AG","302079.03","Wilhelmshaven - Bremen","<","Wilhelmshaven","Sande",2019,2019,13,13,"27.03.2019","23:20:00","30.03.2019","04:40:00","16 h","nachts/\nat night","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,"Mi-Fr/WThF, jeweils/each 23:20-04:40 ",null,null,"1BD3F57C31CCC.03"]
[null,"DB Netz AG","302081.01","Wilhelmshaven - Bremen",">","Ofenerdiek","Rastede",2019,2019,13,17,"28.03.2019","04:00:00","28.04.2019","05:00:00","1 d, 08 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 04:00-05:00 ",null,null,"1BD3F57D25F0C.01"]
[null,"DB Netz AG","302081.02","Wilhelmshaven - Bremen","<","Ofenerdiek","Oldb (Oldb) Hbf",2019,2019,13,18,"28.03.2019","04:00:00","29.04.2019","04:00:00","32 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F57D25F0C.02"]
[null,"DB Netz AG","302081.04","Wilhelmshaven - Bremen",">","Ofenerdiek","Rastede",2019,2019,13,17,"28.03.2019","10:30:00","28.04.2019","11:30:00","1 d, 08 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 10:30-11:30 ",null,null,"1BD3F57D25F0C.04"]
[null,"DB Netz AG","302081.05","Wilhelmshaven - Bremen",">","Ofenerdiek","Rastede",2019,2019,13,17,"28.03.2019","22:00:00","28.04.2019","23:00:00","1 d, 08 h","abends, nachts/\nnachts, at night, evening","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-23:00 ",null,null,"1BD3F57D25F0C.05"]
[null,"DB Netz AG","302089.01","Wilhelmshaven - Bremen","< >","Oldb (Oldb) Hbf","Oldb (Oldb) Hbf",2019,2019,13,14,"31.03.2019","01:00:00","04.04.2019","06:00:00","4 d, 05 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F58188FCC.01"]
[null,"DB Netz AG","302089.02","Wilhelmshaven - Bremen","< >","Oldb (Oldb) Hbf","Oldb (Oldb) Hbf",2019,2019,13,14,"31.03.2019","01:00:00","04.04.2019","06:00:00","4 d, 05 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F58188FCC.02"]
[null,"DB Netz AG","302091.02","Wilhelmshaven - Bremen","< >","Sande","Wilhelmshaven",2019,2019,14,35,"01.04.2019","01:20:00","26.08.2019","04:40:00","3 d, 01 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"Mo/M, jeweils/each 01:20-04:40 ",null,"X","1BD3F5827D20C.02"]
[null,"DB Netz AG","302091.03","Wilhelmshaven - Bremen",">","Sande","Wilhelmshaven",2019,2019,14,35,"01.04.2019","04:40:00","26.08.2019","06:00:00","1 d, 05 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,"Mo/M, jeweils/each 04:40-06:00 ",null,"X","1BD3F5827D20C.03"]
[null,"DB Netz AG","302091.01","Wilhelmshaven - Bremen","<","Wilhelmshaven","Sande",2019,2019,14,35,"01.04.2019","23:20:00","31.08.2019","04:40:00","29 d, 03 h","nachts/\nat night","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,"(So)/MTWThFS, jeweils/each 23:20-04:40 ",null,"X","1BD3F5827D20C.01"]
[null,"DB Netz AG","302092.01","Wilhelmshaven - Bremen","< >","Sande","Sande",2019,2019,14,14,"02.04.2019","00:20:00","05.04.2019","04:45:00","18 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,"Di-Fr/TWThF, jeweils/each 00:20-04:45 ",null,null,"1BD3F582F732C.01"]
[null,"DB Netz AG","302092.02","Wilhelmshaven - Bremen","< >","Sande","Wilhelmshaven",2019,2019,14,35,"02.04.2019","00:20:00","31.08.2019","04:40:00","23 d, 16 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"(Mo)/TWThFSSu, jeweils/each 00:20-04:40 ",null,"X","1BD3F582F732C.02"]
[null,"DB Netz AG","302092.03","Wilhelmshaven - Bremen",">","Sande","Wilhelmshaven",2019,2019,14,35,"02.04.2019","04:40:00","31.08.2019","06:00:00","7 d, 07 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,"(Mo)/TWThFSSu, jeweils/each 04:40-06:00 ",null,"X","1BD3F582F732C.03"]
[null,"DB Netz AG","302114.01","Wilhelmshaven - Bremen","<","Rastede","Oldb (Oldb) Hbf",2019,2019,18,18,"29.04.2019","04:00:00","02.05.2019","04:00:00","3 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F58E99B6C.01"]
[null,"DB Netz AG","302114.02","Wilhelmshaven - Bremen","< >","Ofenerdiek","Rastede",2019,2019,18,20,"29.04.2019","04:00:00","19.05.2019","05:00:00","21 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 04:00-05:00 ",null,null,"1BD3F58E99B6C.02"]
[null,"DB Netz AG","302114.04","Wilhelmshaven - Bremen","< >","Ofenerdiek","Rastede",2019,2019,18,20,"29.04.2019","11:00:00","19.05.2019","12:00:00","21 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 11:00-12:00 ",null,null,"1BD3F58E99B6C.04"]
[null,"DB Netz AG","302114.05","Wilhelmshaven - Bremen","< >","Ofenerdiek","Rastede",2019,2019,18,20,"29.04.2019","22:00:00","19.05.2019","23:00:00","21 h","abends, nachts/\nnachts, at night, evening","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 22:00-23:00 ",null,null,"1BD3F58E99B6C.05"]
[null,"DB Netz AG","302117.01","Wilhelmshaven - Bremen","<","Rastede","Ofenerdiek",2019,2019,18,21,"02.05.2019","04:00:00","20.05.2019","04:00:00","18 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F59007ECC.01"]
[null,"DB Netz AG","302130.01","Wilhelmshaven - Bremen",">","Oldb (Oldb) Hbf","Rastede",2019,2019,21,25,"20.05.2019","04:00:00","20.06.2019","05:00:00","1 d, 08 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 04:00-05:00 ",null,null,"1BD3F5977838C.01"]
[null,"DB Netz AG","302130.02","Wilhelmshaven - Bremen",">","Oldb (Oldb) Hbf","Ofenerdiek",2019,2019,21,25,"20.05.2019","04:00:00","21.06.2019","04:00:00","32 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5977838C.02"]
[null,"DB Netz AG","302130.04","Wilhelmshaven - Bremen",">","Oldb (Oldb) Hbf","Rastede",2019,2019,21,25,"20.05.2019","11:00:00","20.06.2019","12:00:00","1 d, 08 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 11:00-12:00 ",null,null,"1BD3F5977838C.04"]
[null,"DB Netz AG","302130.05","Wilhelmshaven - Bremen",">","Oldb (Oldb) Hbf","Rastede",2019,2019,21,25,"20.05.2019","22:00:00","20.06.2019","23:00:00","1 d, 08 h","abends, nachts/\nnachts, at night, evening","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-23:00 ",null,null,"1BD3F5977838C.05"]
[null,"DB Netz AG","302165.01","Wilhelmshaven - Bremen",">","Oldb (Oldb) Hbf","Rastede",2019,2019,25,26,"21.06.2019","04:00:00","24.06.2019","04:00:00","3 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5A8D394C.01"]
[null,"DB Netz AG","302165.03","Wilhelmshaven - Bremen",">","Ofenerdiek","Rastede",2019,2019,26,29,"24.06.2019","04:00:00","21.07.2019","04:00:00","27 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5A8D394C.03"]
[null,"DB Netz AG","302180.01","Wilhelmshaven - Bremen","<","Schwarzer Rabe","Varel (Oldb)",2019,2019,28,43,"08.07.2019","00:00:00","27.10.2019","23:59:00","112 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F5B0130CC.01"]
[null,"DB Netz AG","302180.03","Wilhelmshaven - Bremen","< >","Sande","Varel (Oldb)",2019,2019,28,43,"13.07.2019","05:00:00","26.10.2019","23:59:00","12 d, 16 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 05:00-23:59 ",null,"X","1BD3F5B0130CC.03"]
[null,"DB Netz AG","302180.04","Wilhelmshaven - Bremen","< >","Sande","Varel (Oldb)",2019,2019,28,43,"14.07.2019","05:00:00","27.10.2019","23:59:00","12 d, 16 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"So/Su, jeweils/each 05:00-23:59 ",null,"X","1BD3F5B0130CC.04"]
[null,"DB Netz AG","302189.01","Wilhelmshaven - Bremen","<","Rastede","Ofenerdiek",2019,2019,29,30,"21.07.2019","04:00:00","28.07.2019","04:00:00","7 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5B47618C.01"]
[null,"DB Netz AG","302195.01","Wilhelmshaven - Bremen","<","Ofenerdiek","Oldb (Oldb) Hbf",2019,2019,30,31,"28.07.2019","04:00:00","04.08.2019","04:00:00","7 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5B7CC96C.01"]
[null,"DB Netz AG","302204.01","Wilhelmshaven - Bremen",">","Oldb (Oldb) Hbf","Ofenerdiek",2019,2019,31,32,"04.08.2019","04:00:00","11.08.2019","04:00:00","7 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5BC2FA2C.01"]
[null,"DB Netz AG","302210.01","Wilhelmshaven - Bremen","<","Rastede","Ofenerdiek",2019,2019,33,37,"12.08.2019","04:00:00","13.09.2019","04:00:00","32 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5BF2478C.01"]
[null,"DB Netz AG","302216.02","Wilhelmshaven - Bremen","< >","Sande","Sande",2019,2019,35,35,"27.08.2019","00:20:00","30.08.2019","04:45:00","18 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,"Di-Fr/TWThF, jeweils/each 00:20-04:45 ",null,null,"1BD3F5C200E4C.02"]
[null,"DB Netz AG","302210.02","Wilhelmshaven - Bremen","< >","Ofenerdiek","Rastede",2019,2019,35,35,"27.08.2019","01:00:00","29.08.2019","05:00:00","12 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"Di-Do/TWTh, jeweils/each 01:00-05:00 ",null,null,"1BD3F5BF2478C.02"]
[null,"DB Netz AG","302221.01","Wilhelmshaven - Bremen","< >","Sande","Sande",2019,2019,35,50,"01.09.2019","06:00:00","14.12.2019","23:59:00","104 d, 18 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F5C4633EC.01"]
[null,"DB Netz AG","302227.01","Wilhelmshaven - Bremen",">","Ofenerdiek","Rastede",2019,2019,37,40,"13.09.2019","04:00:00","01.10.2019","04:00:00","18 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5C75814C.01"]
[null,"DB Netz AG","302227.02","Wilhelmshaven - Bremen","< >","Rastede","Ofenerdiek",2019,2019,39,39,"24.09.2019","01:00:00","25.09.2019","05:00:00","8 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:00-05:00 ",null,null,"1BD3F5C75814C.02"]
[null,"DB Netz AG","302243.01","Wilhelmshaven - Bremen","<","Ofenerdiek","Oldb (Oldb) Hbf",2019,2019,40,44,"01.10.2019","04:00:00","02.11.2019","04:00:00","32 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5CF8BB0C.01"]
[null,"DB Netz AG","302243.02","Wilhelmshaven - Bremen","< >","Oldb (Oldb) Hbf","Ofenerdiek",2019,2019,42,42,"15.10.2019","01:00:00","17.10.2019","05:00:00","12 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"Di-Do/TWTh, jeweils/each 01:00-05:00 ",null,null,"1BD3F5CF8BB0C.02"]
[null,"DB Netz AG","302253.01","Wilhelmshaven - Bremen",">","Varel (Oldb)","Schwarzer Rabe",2019,2019,44,50,"28.10.2019","00:00:00","14.12.2019","05:00:00","47 d, 05 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F5D4FB4AC.01"]
[null,"DB Netz AG","302255.01","Wilhelmshaven - Bremen",">","Oldb (Oldb) Hbf","Ofenerdiek",2019,2019,44,48,"02.11.2019","04:00:00","25.11.2019","04:00:00","23 d","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5D5EF6EC.01"]
[null,"DB Netz AG","302253.03","Wilhelmshaven - Bremen","< >","Sande","Varel (Oldb)",2019,2019,44,48,"02.11.2019","05:00:00","30.11.2019","23:59:00","3 d, 23 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"Sa/S, jeweils/each 05:00-23:59 ",null,"X","1BD3F5D4FB4AC.03"]
[null,"DB Netz AG","302253.04","Wilhelmshaven - Bremen","< >","Sande","Varel (Oldb)",2019,2019,44,48,"03.11.2019","05:00:00","01.12.2019","23:59:00","3 d, 23 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"So/Su, jeweils/each 05:00-23:59 ",null,"X","1BD3F5D4FB4AC.04"]
[null,"DB Netz AG","302255.02","Wilhelmshaven - Bremen","< >","Ofenerdiek","Oldb (Oldb) Hbf",2019,2019,47,47,"19.11.2019","01:00:00","20.11.2019","05:00:00","8 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 01:00-05:00 ",null,null,"1BD3F5D5EF6EC.02"]
[null,"DB Netz AG","302258.01","Wilhelmshaven - Bremen","<","Rastede","Ofenerdiek",2019,2019,48,50,"25.11.2019","04:00:00","14.12.2019","23:59:00","19 d, 20 h","ganztags/\nfull day","Untergrundverbesserung/\nsubstructure renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F5D75DA4C.01"]
[null,"DB Netz AG","302096.02","Oberhausen - Hannover","< >","Hannover Hbf","Hannover Hbf",2019,2019,14,16,"06.04.2019","01:00:00","15.04.2019","04:00:00","9 d, 03 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F584DF7AC.02"]
[null,"DB Netz AG","302091.04","Wilhelmshaven - Bremen","< >","Sande","Weißer Floh",2019,2019,14,14,"01.04.2019","23:45:00","05.04.2019","04:45:00","20 h","nachts/\nat night","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:45-04:45 ",null,null,"1BD3F5827D20C.04"]
[null,"DB Netz AG","302216.01","Wilhelmshaven - Bremen","< >","Sande","Weißer Floh",2019,2019,35,35,"26.08.2019","23:45:00","30.08.2019","04:45:00","20 h","nachts/\nat night","Untergrundverbesserung/\nsubstructure renovation","X",null,null,null,null,null,null,null,null,null,"Mo-Do/MTWTh, jeweils/each 23:45-04:45 ",null,null,"1BD3F5C200E4C.01"]
[null,"DB Netz AG","303280.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2018,2018,50,50,"10.12.2018","05:00:00","15.12.2018","02:00:00","4 d, 21 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F86B9832C.01"]
[null,"DB Netz AG","303282.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2018,2018,50,51,"15.12.2018","02:00:00","17.12.2018","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F86C8C56C.01"]
[null,"DB Netz AG","303027.01","Emmerich - Oberhausen","< >","Oberhsn Hbf Obn","Emmerich Grenze",2019,2019,3,4,"19.01.2019","02:00:00","21.01.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,"X",null,null,null,null,null,null,"1BD3F40D387CC.01"]
[null,"DB Netz AG","303028.01","Emmerich - Oberhausen","< >","Oberhsn Hbf Obn","Ob-Sterkrade",2019,2019,3,4,"19.01.2019","02:00:00","21.01.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,"X",null,null,null,null,null,null,"1BD3F40EEFF0C.01"]
[null,"DB Netz AG","303032.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,4,4,"21.01.2019","05:00:00","26.01.2019","02:00:00","4 d, 21 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F413CD0EC.01"]
[null,"DB Netz AG","303035.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,4,5,"26.01.2019","02:00:00","28.01.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F4178534C.01"]
[null,"DB Netz AG","303048.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,6,7,"09.02.2019","02:00:00","11.02.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F42BA492C.01"]
[null,"DB Netz AG","303057.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,8,8,"18.02.2019","05:00:00","23.02.2019","02:00:00","4 d, 21 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F430079EC.01"]
[null,"DB Netz AG","303060.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,8,9,"23.02.2019","02:00:00","25.02.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F4314500C.01"]
[null,"DB Netz AG","303080.01","Emmerich - Oberhausen","< >","Oberhsn Hbf Obn","Emmerich Grenze",2019,2019,12,13,"23.03.2019","02:00:00","25.03.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,"X",null,null,null,null,null,null,"1BD3F43BAA22C.01"]
[null,"DB Netz AG","303081.01","Emmerich - Oberhausen","< >","Oberhsn Hbf Obn","Ob-Sterkrade",2019,2019,12,13,"23.03.2019","02:00:00","25.03.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,"X",null,null,null,null,null,null,"1BD3F43C2434C.01"]
[null,"DB Netz AG","303082.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,13,13,"25.03.2019","05:00:00","30.03.2019","02:00:00","4 d, 21 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F43C9E46C.01"]
[null,"DB Netz AG","303085.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,13,14,"30.03.2019","02:00:00","01.04.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F43E0C7CC.01"]
[null,"DB Netz AG","303099.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,17,17,"22.04.2019","05:00:00","27.04.2019","02:00:00","4 d, 21 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F4459532C.01"]
[null,"DB Netz AG","303103.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,17,18,"27.04.2019","02:00:00","29.04.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F4477D7AC.01"]
[null,"DB Netz AG","303118.01","Emmerich - Oberhausen","< >","Oberhsn Hbf Obn","Emmerich Grenze",2019,2019,20,21,"18.05.2019","02:00:00","20.05.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,"X",null,null,null,null,null,null,"1BD3F44F98ACC.01"]
[null,"DB Netz AG","303119.01","Emmerich - Oberhausen","< >","Oberhsn Hbf Obn","Ob-Sterkrade",2019,2019,20,21,"18.05.2019","02:00:00","20.05.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,"X",null,null,null,null,null,null,"1BD3F45012BEC.01"]
[null,"DB Netz AG","303121.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,21,21,"20.05.2019","05:00:00","25.05.2019","02:00:00","4 d, 21 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F45106E2C.01"]
[null,"DB Netz AG","303122.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,21,22,"25.05.2019","02:00:00","27.05.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F4527518C.01"]
[null,"DB Netz AG","303285.02","Emmerich - Oberhausen",">","Dinslaken","Ob-Sterkrade",2019,2019,24,25,"15.06.2019","02:00:00","17.06.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BF9F29B5DCB8.02"]
[null,"DB Netz AG","303140.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,24,25,"15.06.2019","02:00:00","17.06.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F45C2F54C.01"]
[null,"DB Netz AG","303285.05","Emmerich - Oberhausen",">","Dinslaken","Ob-Sterkrade",2019,2019,26,26,"24.06.2019","05:00:00","27.06.2019","02:00:00","2 d, 21 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BF9F29B5DCB8.05"]
[null,"DB Netz AG","303146.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,26,26,"24.06.2019","05:00:00","27.06.2019","02:00:00","2 d, 21 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F45F85D2C.01"]
[null,"DB Netz AG","303148.01","Emmerich - Oberhausen","< >","Oberhsn Hbf Obn","Emmerich Grenze",2019,2019,26,27,"27.06.2019","02:00:00","01.07.2019","05:00:00","4 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,"X",null,null,null,null,null,null,"1BD3F46079F6C.01"]
[null,"DB Netz AG","303149.01","Emmerich - Oberhausen","< >","Oberhsn Hbf Obn","Ob-Sterkrade",2019,2019,26,27,"27.06.2019","02:00:00","01.07.2019","05:00:00","4 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,"X",null,null,null,null,null,null,"1BD3F460F408C.01"]
[null,"DB Netz AG","303286.01","Emmerich - Oberhausen","< >","Dinslaken","Ob-Sterkrade",2019,2019,26,27,"27.06.2019","02:00:00","01.07.2019","05:00:00","4 d, 03 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BF9FB34291D8.01"]
[null,"DB Netz AG","303162.01","Emmerich - Oberhausen",">","Wesel","Oberhausen Hbf",2019,2019,28,34,"12.07.2019","22:00:00","23.08.2019","06:00:00","14 d","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:00-06:00 ",null,null,"1BD3F46757C6C.01"]
[null,"DB Netz AG","303169.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,28,35,"13.07.2019","02:00:00","26.08.2019","05:00:00","44 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,"X","1BD3F46AAE44C.01"]
[null,"DB Netz AG","303287.02","Emmerich - Oberhausen",">","Dinslaken","Ob-Sterkrade",2019,2019,28,35,"13.07.2019","02:00:00","26.08.2019","05:00:00","44 d, 03 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BF9FD1531A58.02"]
[null,"DB Netz AG","303171.01","Emmerich - Oberhausen","< >","Oberhsn Hbf Obn","Emmerich Grenze",2019,2019,28,34,"14.07.2019","00:20:00","25.08.2019","05:45:00","1 d, 14 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,"X",null,null,null,"So/Su, jeweils/each 00:20-05:45 ",null,null,"1BD3F46BA268C.01"]
[null,"DB Netz AG","303173.01","Emmerich - Oberhausen","< >","Oberhsn Hbf Obn","Emmerich Grenze",2019,2019,29,31,"15.07.2019","00:20:00","29.07.2019","04:10:00","11 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,"X",null,null,null,"Mo/M, jeweils/each 00:20-04:10 ",null,null,"1BD3F46C968CC.01"]
[null,"DB Netz AG","303174.01","Emmerich - Oberhausen",">","Emmerich Grenze","Wesel",2019,2019,29,34,"19.07.2019","08:00:00","23.08.2019","16:00:00","12 d","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 08:00-16:00 ",null,null,"1BD3F46D109EC.01"]
[null,"DB Netz AG","303179.01","Emmerich - Oberhausen","< >","Oberhsn Hbf Obn","Emmerich Grenze",2019,2019,33,35,"12.08.2019","00:20:00","26.08.2019","04:10:00","11 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,"X",null,null,null,"Mo/M, jeweils/each 00:20-04:10 ",null,null,"1BD3F46FD4A0C.01"]
[null,"DB Netz AG","303206.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,39,39,"23.09.2019","05:00:00","28.09.2019","02:00:00","4 d, 21 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F480B5EAC.01"]
[null,"DB Netz AG","303209.01","Emmerich - Oberhausen","< >","Oberhsn Hbf Obn","Emmerich Grenze",2019,2019,39,40,"28.09.2019","02:00:00","30.09.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,"X",null,null,null,null,null,null,"1BD3F4823C8AC.01"]
[null,"DB Netz AG","303210.01","Emmerich - Oberhausen","< >","Oberhsn Hbf Obn","Ob-Sterkrade",2019,2019,39,40,"28.09.2019","02:00:00","30.09.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,"X",null,null,null,null,null,null,"1BD3F482B69CC.01"]
[null,"DB Netz AG","303226.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,41,42,"12.10.2019","02:00:00","14.10.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F48C4004C.01"]
[null,"DB Netz AG","303246.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,44,44,"28.10.2019","05:00:00","02.11.2019","02:00:00","4 d, 21 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F4976876C.01"]
[null,"DB Netz AG","303252.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,44,45,"02.11.2019","02:00:00","04.11.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F49A8E20C.01"]
[null,"DB Netz AG","303262.01","Emmerich - Oberhausen","< >","Oberhsn Hbf Obn","Emmerich Grenze",2019,2019,46,47,"16.11.2019","02:00:00","18.11.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,"X",null,null,null,null,null,null,"1BD3F49F6B3EC.01"]
[null,"DB Netz AG","303263.01","Emmerich - Oberhausen","< >","Oberhsn Hbf Obn","Ob-Sterkrade",2019,2019,46,47,"16.11.2019","02:00:00","18.11.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,"X",null,null,null,null,null,null,"1BD3F49FE550C.01"]
[null,"DB Netz AG","303265.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,47,47,"18.11.2019","05:00:00","23.11.2019","02:00:00","4 d, 21 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F4A0D974C.01"]
[null,"DB Netz AG","303266.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,47,48,"23.11.2019","02:00:00","25.11.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F4A15386C.01"]
[null,"DB Netz AG","303272.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,48,49,"30.11.2019","02:00:00","02.12.2019","05:00:00","2 d, 03 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F4A4485CC.01"]
[null,"DB Netz AG","303279.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,50,50,"09.12.2019","05:00:00","14.12.2019","02:00:00","4 d, 21 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F4A7B744C.01"]
[null,"DB Netz AG","303477.01","Emmerich - Oberhausen",">","Emmerich Grenze","Oberhsn Hbf Obn",2019,2019,50,50,"14.12.2019","02:00:00","14.12.2019","23:59:00","22 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,"X",null,null,null,null,null,null,"1BD3F4A8AB68C.01"]
[null,"DB Netz AG","1BFB230031EA5.01","Aachen - Oberhausen",">","Aachen Hbf","Aachen West Pbf",2019,2019,33,33,"12.08.2019","00:15:00","16.08.2019","04:10:00","20 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:15-04:10 ",null,null,"1BFB230031EA5.01"]
[null,"DB Netz AG","1BFB230031EA5.02","Aachen - Oberhausen","<","Aachen West Pbf","Aachen Hbf",2019,2019,34,34,"19.08.2019","00:50:00","23.08.2019","05:00:00","21 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:50-05:00 ",null,null,"1BFB230031EA5.02"]
[null,"DB Netz AG","1BFB230031EA5.03","Aachen - Oberhausen",">","Aachen Hbf","Aachen West Pbf",2019,2019,35,35,"26.08.2019","00:15:00","30.08.2019","04:10:00","20 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:15-04:10 ",null,null,"1BFB230031EA5.03"]
[null,"DB Netz AG","1BFB230031EA5.04","Aachen - Oberhausen","<","Aachen West Pbf","Aachen Hbf",2019,2019,36,36,"02.09.2019","00:50:00","06.09.2019","05:00:00","21 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:50-05:00 ",null,null,"1BFB230031EA5.04"]
[null,"DB Netz AG","1BFB230031EA5.05","Aachen - Oberhausen",">","Aachen Hbf","Aachen West Pbf",2019,2019,37,37,"09.09.2019","00:15:00","11.09.2019","04:10:00","12 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:15-04:10 ",null,null,"1BFB230031EA5.05"]
[null,"DB Netz AG","303542.01","Aachen - Oberhausen",">","Aachen Hbf","Aachen West Pbf",2019,2019,43,43,"21.10.2019","05:00:00","27.10.2019","23:00:00","5 d, 06 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 05:00-23:00 ",null,null,"1BFC7B958B1A5.01"]
[null,"DB Netz AG","303542.02","Aachen - Oberhausen",">","Aachen Hbf","Aachen West Pbf",2019,2019,44,44,"28.10.2019","23:00:00","03.11.2019","05:00:00","1 d, 12 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1BFC7B958B1A5.02"]
[null,"DB Netz AG","303542.04","Aachen - Oberhausen",">","Aachen Hbf","Aachen West Pbf",2019,2019,45,45,"04.11.2019","05:00:00","08.11.2019","23:00:00","3 d, 18 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 05:00-23:00 ",null,null,"1BFC7B958B1A5.04"]
[null,"DB Netz AG","303545.03","Aachen - Oberhausen",">","Aachen Hbf","Aachen West Pbf",2019,2019,46,46,"12.11.2019","05:00:00","15.11.2019","23:00:00","3 d","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 05:00-23:00 ",null,null,"1BFC93EC784A5.03"]
[null,"DB Netz AG","303545.04","Aachen - Oberhausen",">","Aachen Hbf","Aachen West Pbf",2019,2019,47,47,"18.11.2019","23:00:00","22.11.2019","05:00:00","1 d","nachts/\nat night","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1BFC93EC784A5.04"]
[null,"DB Netz AG","303549.03","Aachen - Oberhausen",">","Aachen Hbf","Aachen West Pbf",2019,2019,48,48,"26.11.2019","05:00:00","29.11.2019","23:00:00","3 d","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 05:00-23:00 ",null,null,"1BFC99E335045.03"]
[null,"DB Netz AG","303549.05","Aachen - Oberhausen",">","Aachen Hbf","Aachen West Pbf",2019,2019,49,49,"03.12.2019","05:00:00","08.12.2019","23:00:00","4 d, 12 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 05:00-23:00 ",null,null,"1BFC99E335045.05"]
[null,"DB Netz AG","303549.04","Aachen - Oberhausen",">","Aachen Hbf","Aachen West Pbf",2019,2019,50,50,"09.12.2019","23:00:00","14.12.2019","05:00:00","1 d, 06 h","nachts/\nat night","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1BFC99E335045.04"]
[null,"DB Netz AG","303006.01","Oberhausen - Hannover",">","Bottrop Hbf-Pbf","Gladbeck West",2018,2019,49,50,"09.12.2018","23:00:00","09.12.2019","05:00:00","13 d, 06 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"So/Su, jeweils/each 23:00-05:00 ",null,"X","1BD3F3115AF2C.01"]
[null,"DB Netz AG","303190.01","Oberhausen - Hannover","< >","Ge-Buer Nord","Blumenthal",2019,2019,35,50,"26.08.2019","20:00:00","14.12.2019","06:00:00","45 d, 20 h","abends, nachts/\nat night, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 20:00-06:00 ",null,null,"1BD3F4761FF4C.01"]
[null,"DB Netz AG","303188.01","Oberhausen - Hannover",">","Bottrop Hbf-Gbf","Westerholt",2019,2019,35,35,"26.08.2019","22:40:00","28.08.2019","05:50:00","14 h","nachts/\nat night","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:40-05:50 ",null,null,"1BD3F4751366C.01"]
[null,"DB Netz AG","303203.01","Oberhausen - Hannover","< >","Walzwerk","Walzwerk",2019,2019,37,38,"15.09.2019","20:00:00","16.09.2019","09:00:00","13 h","abends, nachts, morgens/\nat night, morning, evening","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F47F47B4C.01"]
[null,"DB Netz AG","303236.02","Oberhausen - Hannover","< >","Lünen Süd","Lünen Süd",2019,2019,42,45,"14.10.2019","04:00:00","04.11.2019","04:00:00","21 d","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F49229B0C.02"]
[null,"DB Netz AG","303251.01","Oberhausen - Hannover","<","Ge-Buer Nord","Gladbeck West",2019,2019,44,50,"01.11.2019","20:00:00","12.12.2019","00:10:00","7 d, 03 h","abends, nachts/\nat night, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 20:00-00:10 ",null,null,"1BD3F49A140EC.01"]
[null,"DB Netz AG","303251.03","Oberhausen - Hannover","<","Ge-Buer Nord","Bottrop Hbf-Gbf",2019,2019,44,50,"02.11.2019","00:10:00","14.12.2019","04:45:00","8 d, 05 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 00:10-04:45 ",null,null,"1BD3F49A140EC.03"]
[null,"DB Netz AG","303023.01","Aachen - Oberhausen","<","Baukau","Bottrop Süd",2019,2019,2,13,"07.01.2019","08:00:00","30.03.2019","18:00:00","34 d, 14 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 08:00-18:00 ",null,null,"1BD3F4067316C.01"]
[null,"DB Netz AG","303115.01","Aachen - Oberhausen","<","Du-Hochf S Abzw","Kr-Uerdingen",2019,2019,19,20,"06.05.2019","22:30:00","17.05.2019","05:30:00","3 d, 05 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:30-05:30 ",null,null,"1BD3F44D7F90C.01"]
[null,"DB Netz AG","303127.01","Aachen - Oberhausen","<","Du-Hochf S Abzw","Kr-Uerdingen",2019,2019,22,23,"27.05.2019","22:30:00","07.06.2019","05:30:00","3 d, 05 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:30-05:30 ",null,null,"1BD3F454D772C.01"]
[null,"DB Netz AG","303248.01","Aachen - Oberhausen","<","Du-Hochf S Abzw","Kr-Uerdingen",2019,2019,44,46,"28.10.2019","22:30:00","15.11.2019","05:30:00","5 d, 06 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:30-05:30 ",null,null,"1BD3F498A5D8C.01"]
[null,"DB Netz AG","303111.02","Emmerich - Oberhausen",">","Trompet","Meerbeck    Abzw",2019,2019,18,23,"29.04.2019","22:30:00","08.06.2019","05:30:00","11 d, 16 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:30-05:30 ",null,null,"1BD3F44B6674C.02"]
[null,"DB Netz AG","303107.03","Emmerich - Oberhausen","< >","Moers","Rheinkamp",2019,2019,23,24,"07.06.2019","23:30:00","11.06.2019","05:00:00","3 d, 06 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F4497E2CC.03"]
[null,"DB Netz AG","303204.01","Emmerich - Oberhausen","< >","Moers","Rheinkamp",2019,2019,38,38,"17.09.2019","22:30:00","18.09.2019","05:15:00","7 h","night time","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F47FC1C6C.01"]
[null,"DB Netz AG","303023.02","Oberhausen - Hannover","< >","Bottrop Süd","Ob-Osterf Ost",2019,2019,2,13,"07.01.2019","08:00:00","30.03.2019","18:00:00","34 d, 14 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Planbare kleine Instandhaltung/\nmaintenance work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 08:00-18:00 ",null,null,"1BD3F4067316C.02"]
[null,"DB Netz AG","303019.03","Oberhausen - Hannover","<","Bottrop Süd","Nordstern    /Ge",2019,2019,2,2,"07.01.2019","20:00:00","12.01.2019","06:00:00","2 d, 02 h","abends, nachts/\nat night, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 20:00-06:00 ",null,null,"1BD3F40195F8C.03"]
[null,"DB Netz AG","303033.02","Oberhausen - Hannover","<","Bottrop Süd","Nordstern    /Ge",2019,2019,4,11,"21.01.2019","20:00:00","16.03.2019","06:00:00","22 d, 12 h","abends, nachts/\nat night, evening","Arbeiten an Lärmschutzanlagen/\nnoise barrier work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 20:00-06:00 ",null,null,"1BD3F4145F8AC.02"]
[null,"DB Netz AG","304154.02","Falkenberg - Bad Schandau","< >","Dre-Friedrichst","Dre Freibg Str",2019,2019,19,19,"10.05.2019","14:00:00","11.05.2019","22:00:00","1 d, 08 h","ganztags/\nfull day","Inbetriebnahme/\nstartup operations","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F6EEE342C.02"]
[null,"DB Netz AG","304158.03","Falkenberg - Bad Schandau","< >","Cossebaude","Dre Freibg Str",2019,2019,19,19,"11.05.2019","22:00:00","12.05.2019","22:00:00","1 d","ganztags/\nfull day","Inbetriebnahme/\nstartup operations","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F6F0CB8AC.03"]
[null,"DB Netz AG","304163.02","Falkenberg - Bad Schandau","< >","Dre-Reick Abstbf","Dre-Friedrichst",2019,2019,20,20,"13.05.2019","20:30:00","14.05.2019","04:30:00","8 h","abends, nachts/\nat night, evening","Inbetriebnahme/\nstartup operations","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F6F3464EC.02"]
[null,"DB Netz AG","304187.03","Falkenberg - Bad Schandau","< >","Dre-Friedrichst","Dre Freibg Str",2019,2019,20,21,"19.05.2019","08:00:00","24.05.2019","04:00:00","4 d, 20 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F6FEE8D2C.03"]
[null,"DB Netz AG","304145.03","Falkenberg - Bad Schandau","< >","Dre Freibg Str","Dre-Friedrichst",2019,2019,21,22,"24.05.2019","04:00:00","01.06.2019","04:00:00","8 d","ganztags/\nfull day","Weichenerneuerung mit PSS/\n","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F6EA8036C.03"]
[null,"DB Netz AG","304294.01","Falkenberg - Bad Schandau","< >","Bad Schandau","Bad Schandau",2019,2019,31,50,"01.08.2019","08:00:00","14.12.2019","23:59:00","135 d, 16 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F737D804C.01"]
[null,"DB Netz AG","304294.02","Falkenberg - Bad Schandau","< >","Bad Schandau Ost","Bad Schandau Ost",2019,2019,31,50,"01.08.2019","08:00:00","14.12.2019","23:59:00","135 d, 16 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F737D804C.02"]
[null,"DB Netz AG","304296.03","Falkenberg - Bad Schandau","< >","Bad Schandau Ost","Bad Schandau Ost",2019,2019,32,32,"05.08.2019","02:00:00","09.08.2019","08:00:00","4 d, 06 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F738CC28C.03"]
[null,"DB Netz AG","304300.02","Falkenberg - Bad Schandau","< >","Schöna","Bad Schandau",2019,2019,32,32,"09.08.2019","20:00:00","10.08.2019","04:00:00","8 h","abends, nachts/\nat night, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F73AB470C.02"]
[null,"DB Netz AG","304302.01","Falkenberg - Bad Schandau",">","Bad Schandau","Bad Schandau Ost",2019,2019,32,36,"10.08.2019","08:00:00","03.09.2019","16:00:00","8 d, 08 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Kabelarbeiten/\ncable work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 08:00-16:00 ",null,null,"1BD3F73BA894C.01"]
[null,"DB Netz AG","304302.02","Falkenberg - Bad Schandau","< >","Bad Schandau","Bad Schandau Ost",2019,2019,32,36,"10.08.2019","08:00:00","03.09.2019","16:00:00","8 d, 08 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Kabelarbeiten/\ncable work",null,null,null,"X",null,"X","X",null,null,null,"jeweils/each 08:00-16:00 ",null,null,"1BD3F73BA894C.02"]
[null,"DB Netz AG","304302.03","Falkenberg - Bad Schandau",">","Bad Schandau","Bad Schandau Ost",2019,2019,32,36,"10.08.2019","08:00:00","03.09.2019","16:00:00","8 d, 08 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Kabelarbeiten/\ncable work",null,"X",null,null,null,"X","X",null,null,null,"jeweils/each 08:00-16:00 ",null,null,"1BD3F73BA894C.03"]
[null,"DB Netz AG","304319.03","Falkenberg - Bad Schandau","< >","Schöna","Bad Schandau",2019,2019,36,36,"03.09.2019","20:00:00","08.09.2019","04:00:00","1 d, 16 h","abends, nachts/\nat night, evening","Kabelarbeiten/\ncable work","X",null,null,null,null,"X","X",null,null,null,"jeweils/each 20:00-04:00 ",null,null,"1BD3F744256EC.03"]
[null,"DB Netz AG","304325.02","Falkenberg - Bad Schandau","< >","Schöna","Bad Schandau",2019,2019,36,37,"08.09.2019","23:00:00","09.09.2019","05:00:00","6 h","night time","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F7477BECC.02"]
[null,"DB Netz AG","304325.03","Falkenberg - Bad Schandau","< >","Bad Schandau Ost","Bad Schandau Ost",2019,2019,37,46,"09.09.2019","05:00:00","15.11.2019","22:00:00","67 d, 17 h","ganztags/\nfull day","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F7477BECC.03"]
[null,"DB Netz AG","304327.02","Falkenberg - Bad Schandau","< >","Bad Schandau Ost","Bad Schandau",2019,2019,37,42,"10.09.2019","02:00:00","18.10.2019","04:00:00","3 d, 06 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work",null,null,null,"X",null,"X","X",null,null,null,"jeweils/each 02:00-04:00 ",null,null,"1BD3F7487010C.02"]
[null,"DB Netz AG","304327.03","Falkenberg - Bad Schandau","<","Schöna","Bad Schandau",2019,2019,37,42,"10.09.2019","02:00:00","18.10.2019","04:00:00","3 d, 06 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,null,null,"jeweils/each 02:00-04:00 ",null,null,"1BD3F7487010C.03"]
[null,"DB Netz AG","304332.01","Falkenberg - Bad Schandau","< >","Bad Schandau Ost","Bad Schandau Ost",2019,2019,38,39,"21.09.2019","08:00:00","23.09.2019","08:00:00","2 d","ganztags/\nfull day","Kabelarbeiten/\ncable work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F74AD26AC.01"]
[null,"DB Netz AG","304366.01","Falkenberg - Bad Schandau","< >","Bad Schandau Gr","Bad Schandau",2019,2019,42,42,"18.10.2019","22:00:00","19.10.2019","06:00:00","8 h","abends, nachts/\nat night, evening","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F75B39A2C.01"]
[null,"DB Netz AG","304369.01","Falkenberg - Bad Schandau","< >","Bad Schandau Ost","Bad Schandau Ost",2019,2019,42,44,"19.10.2019","06:00:00","02.11.2019","00:01:00","13 d, 18 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F75CD8ACC.01"]
[null,"DB Netz AG","304369.03","Falkenberg - Bad Schandau","< >","Bad Schandau Ost","Schöna",2019,2019,42,44,"19.10.2019","06:00:00","02.11.2019","00:01:00","13 d, 18 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,null,null,"X",null,"X","X",null,null,null,null,null,null,"1BD3F75CD8ACC.03"]
[null,"DB Netz AG","304369.04","Falkenberg - Bad Schandau",">","Bad Schandau Ost","Schöna",2019,2019,42,44,"19.10.2019","06:00:00","02.11.2019","00:01:00","13 d, 18 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,"X","X",null,null,null,null,null,null,"1BD3F75CD8ACC.04"]
[null,"DB Netz AG","304371.01","Falkenberg - Bad Schandau","< >","Bad Schandau","Bad Schandau Ost",2019,2019,42,44,"20.10.2019","02:00:00","01.11.2019","04:00:00","1 d, 02 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work",null,null,null,"X",null,"X","X",null,null,null,"jeweils/each 02:00-04:00 ",null,null,"1BD3F75DCCD0C.01"]
[null,"DB Netz AG","304371.02","Falkenberg - Bad Schandau",">","Bad Schandau","Bad Schandau Ost",2019,2019,42,44,"20.10.2019","02:00:00","01.11.2019","04:00:00","1 d, 02 h","nachts, morgens, nachmittags, abends/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,null,null,"jeweils/each 02:00-04:00 ",null,null,"1BD3F75DCCD0C.02"]
[null,"DB Netz AG","304384.01","Falkenberg - Bad Schandau","< >","Bad Schandau Gr","Bad Schandau",2019,2019,44,44,"02.11.2019","00:01:00","02.11.2019","06:00:00","6 h","nachts/\nat night","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F7655586C.01"]
[null,"DB Netz AG","304384.03","Falkenberg - Bad Schandau","< >","Bad Schandau Ost","Bad Schandau",2019,2019,44,44,"02.11.2019","06:00:00","02.11.2019","22:00:00","16 h","tagsüber/\nduring the day","Arbeiten an LST-Anlagen/\nsignal work",null,null,null,"X",null,"X","X",null,null,null,null,null,null,"1BD3F7655586C.03"]
[null,"DB Netz AG","304384.04","Falkenberg - Bad Schandau","<","Schöna","Bad Schandau",2019,2019,44,44,"02.11.2019","06:00:00","02.11.2019","22:00:00","16 h","tagsüber/\nduring the day","Arbeiten an LST-Anlagen/\nsignal work",null,"X",null,null,null,"X","X",null,null,null,null,null,null,"1BD3F7655586C.04"]
[null,"DB Netz AG","304385.01","Falkenberg - Bad Schandau","< >","Schöna","Bad Schandau Ost",2019,2019,44,46,"02.11.2019","06:00:00","15.11.2019","22:00:00","13 d, 16 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,null,null,"X",null,"X","X",null,null,null,null,null,null,"1BD3F765CF98C.01"]
[null,"DB Netz AG","304385.02","Falkenberg - Bad Schandau","<","Schöna","Bad Schandau Ost",2019,2019,44,46,"02.11.2019","06:00:00","15.11.2019","22:00:00","13 d, 16 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,"X","X",null,null,null,null,null,null,"1BD3F765CF98C.02"]
[null,"DB Netz AG","304403.01","Falkenberg - Bad Schandau","< >","Bad Schandau Gr","Bad Schandau",2019,2019,46,46,"15.11.2019","22:00:00","16.11.2019","04:00:00","6 h","abends, nachts/\nat night, evening","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F76F282CC.01"]
[null,"DB Netz AG","304403.02","Falkenberg - Bad Schandau","< >","Bad Schandau Ost","Bad Schandau",2019,2019,46,50,"16.11.2019","08:00:00","14.12.2019","16:00:00","9 d, 16 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,null,null,"X",null,"X","X",null,null,null,"jeweils/each 08:00-16:00 ",null,null,"1BD3F76F282CC.02"]
[null,"DB Netz AG","304403.03","Falkenberg - Bad Schandau","<","Bad Schandau Ost","Bad Schandau",2019,2019,46,50,"16.11.2019","08:00:00","14.12.2019","16:00:00","9 d, 16 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,"X","X",null,null,null,"jeweils/each 08:00-16:00 ",null,null,"1BD3F76F282CC.03"]
[null,"DB Netz AG","304429.01","Hannover - Magdeburg",">","Mg-Sudenburg","Harbke",2018,2019,50,50,"16.12.2018","23:00:00","09.12.2019","05:00:00","13 d","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"So/Su, jeweils/each 23:00-05:00 ",null,"X","1BD3F33F3A1CC.01"]
[null,"DB Netz AG","304054.02","Hannover - Magdeburg","< >","Magdeburg Hbf","Mg-Sudenburg",2019,2019,6,6,"09.02.2019","23:55:00","10.02.2019","06:00:00","6 h","night time","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F6BBF626C.02"]
[null,"DB Netz AG","304073.02","Hannover - Magdeburg","< >","Magdeburg Hbf","Mg-Sudenburg",2019,2019,10,10,"09.03.2019","23:55:00","10.03.2019","10:00:00","10 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F6C6120AC.02"]
[null,"DB Netz AG","304093.02","Hannover - Magdeburg","< >","Magdeburg Hbf","Mg-Sudenburg",2019,2019,11,12,"17.03.2019","23:00:00","20.03.2019","05:00:00","18 h","nachts/\nat night","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 23:00-05:00 ",null,null,"1BD3F6D0A800C.02"]
[null,"DB Netz AG","304157.02","Hannover - Magdeburg","< >","Magdeburg Hbf","Mg-Sudenburg",2019,2019,19,19,"11.05.2019","23:55:00","12.05.2019","12:00:00","12 h","night time, morgens/\nmorning","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1BD3F6F05178C.02"]
[null,"DB Netz AG","304321.01","Hannover - Magdeburg","<","Harbke","Mg-Sudenburg",2019,2019,36,38,"06.09.2019","21:30:00","20.09.2019","04:30:00","4 d, 02 h","abends, nachts/\nat night, evening","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 21:30-04:30 ",null,null,"1BD3F7451992C.01"]
[null,"DB Netz AG","304420.02","Magdeburg - Berlin","< >","Stendal","Stendal",2019,2019,21,27,"25.05.2019","13:00:00","05.07.2019","23:59:00","41 d, 11 h","ganztags/\nfull day","Bahnsteigarbeiten/\nplatform work",null,"X",null,null,null,null,null,null,null,null,null,null,"X","1BD3F77A509EC.02"]
[null,"DB Netz AG","304039.04","Falkenberg - Bad Schandau","< >","Coswig (bei Dre)","Radebeul Ost",2019,2019,2,2,"11.01.2019","18:00:00","13.01.2019","14:00:00","1 d, 20 h","ganztags/\nfull day","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F6B40BC8C.04"]
[null,"DB Netz AG","304041.04","Falkenberg - Bad Schandau","< >","Coswig (bei Dre)","Dresden Mitte",2019,2019,2,2,"12.01.2019","18:00:00","13.01.2019","14:00:00","20 h","ganztags/\nfull day","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F6B4FFECC.04"]
[null,"DB Netz AG","304047.01","Falkenberg - Bad Schandau","< >","Coswig (bei Dre)","Radebeul Nord",2019,2019,3,6,"20.01.2019","22:00:00","04.02.2019","06:00:00","5 d","abends, nachts/\nat night, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,null,null,"jeweils/each 22:00-06:00 ",null,"X","1BD3F6B82596C.01"]
[null,"DB Netz AG","304047.02","Falkenberg - Bad Schandau","< >","Coswig (bei Dre)","Radebeul Nord",2019,2019,6,22,"04.02.2019","08:00:00","28.05.2019","16:00:00","38 d","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,"jeweils/each 08:00-16:00 ",null,"X","1BD3F6B82596C.02"]
[null,"DB Netz AG","304163.03","Falkenberg - Bad Schandau","< >","Dresden Hbf","Dre-Neustadt",2019,2019,20,20,"13.05.2019","20:30:00","14.05.2019","04:30:00","8 h","abends, nachts/\nat night, evening","Inbetriebnahme/\nstartup operations","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F6F3464EC.03"]
[null,"DB Netz AG","304263.01","Falkenberg - Bad Schandau","< >","Coswig (bei Dre)","Radebeul Nord",2019,2019,28,44,"08.07.2019","08:00:00","31.10.2019","16:00:00","38 d, 16 h","morgens, nachmittags, abends, nachts/\nnachts, at night, morning, afternoon, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,null,null,"jeweils/each 08:00-16:00 ",null,"X","1BD3F7281BB2C.01"]
[null,"DB Netz AG","304348.02","Falkenberg - Bad Schandau",">","Coswig Stw 1","Coswig (bei Dre)",2019,2019,40,40,"30.09.2019","20:00:00","03.10.2019","04:00:00","1 d","abends, nachts/\nat night, evening","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 20:00-04:00 ",null,null,"1BD3F752A45EC.02"]
[null,"DB Netz AG","304348.03","Falkenberg - Bad Schandau","<","Coswig (bei Dre)","Coswig Stw 1",2019,2019,40,41,"03.10.2019","20:00:00","07.10.2019","04:00:00","3 d, 08 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F752A45EC.03"]
[null,"DB Netz AG","304376.04","Falkenberg - Bad Schandau",">","Niederau","Coswig (bei Dre)",2019,2019,43,44,"25.10.2019","18:00:00","28.10.2019","04:00:00","2 d, 10 h","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,"X","X",null,null,null,null,null,null,"1BD3F760C1A6C.04"]
[null,"DB Netz AG","304382.03","Falkenberg - Bad Schandau","<","Coswig (bei Dre)","Coswig Stw 1",2019,2019,44,45,"01.11.2019","04:00:00","05.11.2019","04:00:00","4 d","ganztags/\nfull day","Weichenerneuerung mit PSS/\n",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F7641824C.03"]
[null,"DB Netz AG","304263.02","Falkenberg - Bad Schandau","< >","Coswig (bei Dre)","Radebeul Nord",2019,2019,45,50,"05.11.2019","22:00:00","14.12.2019","06:00:00","13 d","abends, nachts/\nat night, evening","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,"X","X",null,null,null,"jeweils/each 22:00-06:00 ",null,null,"1BD3F7281BB2C.02"]
[null,"DB Netz AG","304018.02","Magdeburg - Falkenberg","< >","Roßlau Abzw Ai","Roßlau Gbf Ost",2018,2019,49,50,"09.12.2018","00:00:00","14.12.2019","23:59:00","371 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,"X","1BD3F3371EEAC.02"]
[null,"DB Netz AG","304018.01","Magdeburg - Falkenberg","< >","Roßlau Aw","Roßlau(Elbe) Gbf",2018,2019,49,50,"09.12.2018","00:00:00","14.12.2019","23:59:00","371 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,"X","1BD3F3371EEAC.01"]
[null,"DB Netz AG","304018.03","Magdeburg - Falkenberg","< >","Rodleben","Roßlau(Elbe) Gbf",2018,2019,49,50,"09.12.2018","00:00:00","14.12.2019","23:59:00","371 d","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work","X",null,null,null,null,null,null,null,null,null,null,null,"X","1BD3F3371EEAC.03"]
[null,"DB Netz AG","304013.01","Falkenberg - Horka","<","Niesky","Särichen",2018,2019,49,43,"09.12.2018","00:00:00","27.10.2019","06:00:00","322 d, 06 h","ganztags/\nfull day","sonstige Arbeiten/\nmisc. work",null,"X",null,null,null,"X","X",null,null,null,null,null,"X","1BD3F334A426C.01"]
[null,"DB Netz AG","304087.01","Magdeburg - Falkenberg","< >","Jessen (Elster)","Fermerswalde",2019,2019,11,13,"11.03.2019","23:20:00","25.03.2019","04:00:00","13 d, 05 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,"X","X",null,null,null,null,null,null,"1BD3F6CCEFDAC.01"]
[null,"DB Netz AG","304218.01","Magdeburg - Falkenberg","< >","Fermerswalde","Fermerswalde",2019,2019,24,28,"11.06.2019","18:00:00","13.07.2019","18:00:00","32 d","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work",null,"X",null,null,null,null,null,null,null,null,null,null,null,"1BD3F70FE286C.01"]
[null,"DB Netz AG","304218.02","Magdeburg - Falkenberg","< >","Fermerswalde","Jessen (Elster)",2019,2019,24,28,"11.06.2019","22:00:00","13.07.2019","04:00:00","31 d, 06 h","ganztags/\nfull day","Oberleitungsarbeiten/\ncatenary work","X",null,null,null,null,null,"X",null,null,null,null,null,null,"1BD3F70FE286C.02"]
[null,"DB Netz AG","304247.01","Magdeburg - Falkenberg","< >","Lu Wittenberg","Elster (Elbe)",2019,2019,26,28,"28.06.2019","23:20:00","13.07.2019","04:00:00","14 d, 05 h","ganztags/\nfull day","Gleiserneuerung/\ntrack renovation","X",null,null,null,null,null,"X",null,null,null,null,null,null,"1BD3F72049BEC.01"]
[null,"DB Netz AG","304260.02","Magdeburg - Falkenberg","< >","Jessen (Elster)","Jessen (Elster)",2019,2019,28,28,"10.07.2019","21:00:00","13.07.2019","04:00:00","2 d, 07 h","ganztags/\nfull day","Weichenerneuerung/\nswitch renovation","X",null,null,null,null,null,"X",null,null,null,null,null,null,"1BD3F7269512C.02"]
[null,"DB Netz AG","304449.01","Falkenberg - Horka","< >","Horka Grenze","Hoyerswerda",2019,2019,43,43,"26.10.2019","18:00:00","27.10.2019","06:00:00","12 h","nachmittags, abends, nachts/\nat night, afternoon, evening","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C252066E368C.01"]
[null,"DB Netz AG","304449.02","Falkenberg - Horka","< >","Lauchhammer","Hosena",2019,2019,43,43,"26.10.2019","18:00:00","27.10.2019","06:00:00","12 h","nachmittags, abends, nachts/\nat night, afternoon, evening","Arbeiten an LST-Anlagen/\nsignal work","X",null,null,null,null,null,null,null,null,null,null,null,null,"1C252066E368C.02"]
[null,"DB Netz AG","303111.03","Aachen - Oberhausen",">","Mühlenberg","Trompet",2019,2019,18,23,"29.04.2019","22:30:00","08.06.2019","05:30:00","11 d, 16 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:30-05:30 ",null,null,"1BD3F44B6674C.03"]
[null,"DB Netz AG","303115.02","Aachen - Oberhausen","<","Kr-Uerdingen","Krefeld-Linn",2019,2019,19,20,"06.05.2019","22:30:00","17.05.2019","05:30:00","3 d, 05 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:30-05:30 ",null,null,"1BD3F44D7F90C.02"]
[null,"DB Netz AG","303127.02","Aachen - Oberhausen","<","Kr-Uerdingen","Krefeld-Linn",2019,2019,22,23,"27.05.2019","22:30:00","07.06.2019","05:30:00","3 d, 05 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:30-05:30 ",null,null,"1BD3F454D772C.02"]
[null,"DB Netz AG","303248.02","Aachen - Oberhausen","<","Kr-Uerdingen","Krefeld-Linn",2019,2019,44,46,"28.10.2019","22:30:00","15.11.2019","05:30:00","5 d, 06 h","nachts/\nat night","Planbare kleine Instandhaltung/\nmaintenance work",null,"X",null,null,null,null,null,null,null,null,"jeweils/each 22:30-05:30 ",null,null,"1BD3F498A5D8C.02"]
[null,"DB Netz AG","303029.01","Aachen - Oberhausen","< >","Rheydt Gbf","Vie-Helenabrunn",2019,2019,3,39,"19.01.2019","10:00:00","29.09.2019","18:00:00","253 d, 08 h","ganztags/\nfull day","Brückenarbeiten/\nbridgework","X",null,null,null,null,null,"X",null,null,null,null,null,null,"1BD3F4105E26C.01"]
[null,"PKP PLK",14,"Poznan - Warszawa","E-W","Retkinia","Lublinek",2018,2019,48,15,"2018-11-28","00:01:00","2019-04-12","23:59:00",135,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",14,"Poznan - Warszawa","W-E","Lublinek","Retkinia",2018,2018,41,48,"2018-10-12","00:01:00","2018-11-28","23:59:00",47,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",14,"Poznan - Warszawa","E-W","Lodz Kaliska","Retkinia",2018,2018,20,28,"2018-05-15","00:01:00","2018-07-13","23:59:00",59,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",14,"Poznan - Warszawa","W-E","Retkinia","Lodz Kaliska",2018,2018,28,41,"2018-07-13","00:01:00","2018-10-12","23:59:00",91,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",14,"Poznan - Warszawa","E-W","Pabianice","Lask",2018,2019,43,15,"2018-10-28","00:01:00","2019-04-12","23:59:00",181,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",14,"Poznan - Warszawa","W-E","Lask","Pabianice",2018,2018,20,43,"2018-05-15","00:01:00","2018-10-28","23:59:00",181,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",14,"Poznan - Warszawa","W-E","Zduńska Wola","Zduńska Wola",2018,2018,20,37,"2018-05-15","00:01:00","2018-09-12","23:59:00",120,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"close track 2,4"]
[null,"PKP PLK",14,"Poznan - Warszawa","E-W","Zduńska Wola","Zduńska Wola",2018,2019,37,2,"2018-09-12","00:01:00","2019-01-11","23:59:00",121,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"close track 1,3"]
[null,"PKP PLK",14,"Poznan - Warszawa","W-E","Radliczyce","Opatówek",2018,2018,41,41,"2018-10-08","00:01:00","2018-10-12","23:59:00",4,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",14,"Poznan - Warszawa","E-W","Opatówek","Radliczyce",2018,2018,40,40,"2018-10-01","00:01:00","2018-10-05","23:59:00",4,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",14,"Poznan - Warszawa","W-E","Pępowo ","Krobia",2018,2018,43,43,"2018-10-22","00:01:00","2018-10-26","23:59:00",4,"All day","track closure",null,"x",null,null,"x",null,null,null,"x"]
[null,"PKP PLK",14,"Poznan - Warszawa","E-W","Krobia","Pępowo ",2018,2018,42,42,"2018-10-15","00:01:00","2018-10-19","23:59:00",4,"All day","track closure",null,"x",null,null,"x",null,null,null,"x"]
[null,"PKP PLK",14,"Poznan - Warszawa","W-E","Pępowo ","Krobia",2018,2018,45,45,"2018-11-05","00:01:00","2018-11-09","23:59:00",4,"All day","track closure",null,"x",null,null,"x",null,null,null,"x"]
[null,"PKP PLK",14,"Poznan - Warszawa","E-W","Krobia","Pępowo ",2018,2018,44,44,"2018-10-29","00:01:00","2018-11-03","23:59:00",5,"All day","track closure",null,"x",null,null,"x",null,null,null,"x"]
[null,"PKP PLK",14,"Poznan - Warszawa","E-W","Leszno ","Leszno Grzybowo",2018,2018,46,46,"2018-11-12","00:01:00","2018-11-16","23:59:00",4,"All day","track closure",null,"x",null,null,"x",null,null,null,"x"]
[null,"PKP PLK",14,"Poznan - Warszawa","W-E","Leszno Grzybowo","Leszno ",2018,2018,47,47,"2018-11-19","00:01:00","2018-11-23","23:59:00",4,"All day","track closure",null,"x",null,null,"x",null,null,null,"x"]
[null,"PKP PLK",2,"Warszawa - Terespol","E-W","Biała Podlaska","Biała Podlaska",2018,2019,11,5,"2018-03-15","00:01:00","2019-01-31","23:59:00",322,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"closure track 1,3,5,9,11,13,15,17,23,25,29"]
[null,"PKP PLK",2,"Warszawa - Terespol","E-W","Małaszewicze","Małaszewicze",2019,2019,3,11,"2019-01-14","00:01:00","2019-03-14","23:59:00",332,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"closure track 1,3,3a,5,7,9,11,41,41b,101,405,405b,407"]
[null,"PKP PLK",2,"Warszawa - Terespol","E-W","Terespol","Terespol",2018,2019,10,10,"2018-03-08","00:01:00","2019-03-07","23:59:00",364,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"closure track 1,3,5,7,51,53,55,47,9,11,13,15,17"]
[null,"PKP PLK",2,"Warszawa - Terespol","E-W","Biała Podlaska","Chotyłów",2018,2019,11,5,"2018-03-15","00:01:00","2019-01-31","06:00:00",322,"night","track closure","x","x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",2,"Warszawa - Terespol","E-W","Chotyłów ","Małaszewicze",2018,2019,11,10,"2018-03-12","00:01:00","2019-03-07","06:00:00",332,"night","track closure","x","x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","W-E","Krzewie ","Kłodawa",2017,2018,41,8,"2017-10-15","00:01:00","2018-02-22","23:59:00",255,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","W-E","Krzewie ","Krzewie ",2017,2018,42,16,"2017-10-16","00:01:00","2018-04-19","23:59:00",311,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"closure track 2,4"]
[null,"PKP PLK",3,"Poznan - Warszawa","<=>","Krzewie","Kutno",2018,2018,37,42,"2018-09-15","00:01:00","2018-10-15","23:59:00",30,"All day","track closure","x",null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","<=>","Kłodawa ","Krzewie",2018,2018,37,42,"2018-09-15","00:01:00","2018-10-15","23:59:00",30,"All day","track closure","x",null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","<=>","Kłodawa ","Kłodawa ",2018,2018,37,42,"2018-09-15","00:01:00","2018-10-15","23:59:00",30,"All day","track closure","x","ST",null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","<=>","Barłogi ","Kłodawa",2018,2018,37,42,"2018-09-15","00:01:00","2018-10-15","23:59:00",30,"All day","track closure","x",null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","E-W","Jackowice","Jackowice",2018,2018,7,16,"2018-02-17","00:01:00","2018-04-18","23:59:00",60,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"closure track 2,4"]
[null,"PKP PLK",3,"Poznan - Warszawa","E-W","Kłodawa","Kłodawa",2018,2019,29,25,"2018-07-16","00:01:00","2019-06-17","23:59:00",336,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"closure track 1,2"]
[null,"PKP PLK",3,"Poznan - Warszawa","E-W","Swarzędz","Poznań Wsch.",2018,2018,24,28,"2018-06-11","00:01:00","2018-07-10","23:59:00",29,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","W-E","Podstolice","Podstolice",2018,2018,15,38,"2018-04-11","00:01:00","2018-09-23","23:59:00",165,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"closure track 1"]
[null,"PKP PLK",3,"Poznan - Warszawa","E-W","Podstolice ","Kostrzyn Wlkp",2018,2018,15,38,"2018-04-11","00:01:00","2018-09-23","23:59:00",165,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","W-E","Kostrzyn WLKP.","Kostrzyn WLKP.",2017,2018,43,15,"2017-10-28","00:01:00","2018-04-11","23:59:00",165,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"closure track 1,3,5"]
[null,"PKP PLK",3,"Poznan - Warszawa","W-E,E-W","Kostrzyn Wlkp.","Swarzędz",2017,2018,47,19,"2017-11-24","00:01:00","2018-05-08","23:59:00",330,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","W-E","Konin","Konin",2017,2018,42,42,"2017-10-16","00:01:00","2018-10-17","23:59:00",94,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"several tracks - alternatively"]
[null,"PKP PLK",3,"Poznan - Warszawa","<=>","Konin","Konin",2017,2018,24,28,"2017-06-12","00:01:00","2018-07-15","23:59:00",395,"All day","track closure","x",null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","<=>","Konin","Cienin",2017,2018,24,28,"2017-06-12","00:01:00","2018-07-15","23:59:00",395,"All day","track closure","x",null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","<=>","Cienin","Strzałkowo",2017,2018,24,28,"2017-06-12","00:01:00","2018-07-15","23:59:00",395,"All day","track closure","x",null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","<=>","Strzałkowo","Strzałkowo",2017,2018,24,28,"2017-06-12","00:01:00","2018-07-15","23:59:00",395,"All day","track closure","x",null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","<=>","Strzałkowo","Podstolice",2017,2018,24,28,"2017-06-12","00:01:00","2018-07-15","23:59:00",395,"All day","track closure","x",null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","<=>","Podstolice","Podstolice",2017,2018,24,28,"2017-06-12","00:01:00","2018-07-15","23:59:00",395,"All day","track closure","x",null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","<=>","Barłogi ","Barłogi ",2018,2019,33,25,"2018-08-16","00:01:00","2019-06-17","23:59:00",305,"All day","track closure","x",null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","<=>","Koło","Barłogi",2018,2019,29,31,"2018-07-16","00:01:00","2019-07-30","23:59:00",379,"All day","track closure","x",null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","W-E","Barłogi ","Koło",2017,2018,50,31,"2017-12-11","00:01:00","2018-07-31","23:59:00",232,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","W-E","Koło","Koło",2017,2018,50,31,"2017-12-11","00:01:00","2018-07-31","23:59:00",232,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"Closure track 1"]
[null,"PKP PLK",3,"Poznan - Warszawa","<=>","Koło","Koło",2018,2019,29,31,"2018-07-16","00:01:00","2019-07-30","23:59:00",379,"All day","track closure","x",null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","W-E","Koło","Kramsk",2017,2018,50,31,"2017-12-11","00:01:00","2018-07-31","23:59:00",232,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","<=>","Koło","Kramsk",2018,2019,29,31,"2018-07-16","00:01:00","2019-07-30","23:59:00",379,"All day","track closure","x",null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","W-E","Kramsk","Kramsk",2017,2018,50,31,"2017-12-11","00:01:00","2018-07-31","23:59:00",232,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"Closure track 1"]
[null,"PKP PLK",3,"Poznan - Warszawa","<=>","Kramsk","Kramsk",2018,2019,29,31,"2018-07-16","00:01:00","2019-07-30","23:59:00",379,"All day","track closure","x",null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","<=>","Cienin","Cienin",2017,2018,49,28,"2017-12-10","00:01:00","2018-07-15","23:59:00",217,"All day","track closure","x",null,null,null,null,null,"x"]
[null,"PKP PLK",2,"Warszawa - Terespol","W-E","Warszawa Włochy","Pruszków",2017,2017,18,36,"2017-05-04","00:01:00","2017-09-04","23:59:00",123,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",2,"Warszawa - Terespol","W-E","Pruszków","Grodzisk Mazowiecki",2017,2017,18,36,"2017-05-04","00:01:00","2017-09-04","23:59:00",123,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","W-E","Łowicz","Bednary",2017,2018,24,17,"2017-06-17","00:01:00","2018-04-23","23:59:00",310,"All day","track closure",null,"x",null,null,null,null,null,null,"x",null,"Closure track 1,2,101,102,103,104,106,6"]
[null,"PKP PLK",3,"Poznan - Warszawa","E-W","Kutno","Kutno",2017,2017,24,36,"2017-06-12","00:01:00","2017-09-08","23:59:00",180,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"Closure track 122"]
[null,"PKP PLK",3,"Poznan - Warszawa","E-W","Kramsk ","Konin",2017,2017,24,30,"2017-06-12","00:01:00","2017-07-24","23:59:00",42,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","W-E","Żychlin","Żychlin",2017,2018,41,7,"2017-10-15","00:01:00","2018-02-17","23:59:00",125,"All day","track closure",null,"ST",null,null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","W-E","Żychlin","Jackowice",2017,2018,41,7,"2017-10-15","00:01:00","2018-02-17","23:59:00",250,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",3,"Poznan - Warszawa","E-W","Jackowice","Jackowice",2017,2017,24,41,"2017-06-12","00:01:00","2017-10-15","23:59:00",125,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"Closure track 1"]
[null,"PKP PLK",3,"Poznan - Warszawa","W-E","Bednary","Bednary",2017,2017,29,33,"2017-07-17","00:01:00","2017-08-16","23:59:00",30,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"Closure track 2,4"]
[null,"PKP PLK",6,"Warszawa - Terespol","W-E","Łochów ","Sadowne Węgrowskie",2017,2017,13,48,"2017-04-01","00:01:00","2017-11-30","23:59:00",243,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",6,"Warszawa - Terespol","E-W","Sadowne Węgrowskie","Sadowne Węgrowskie",2017,2018,13,9,"2017-04-01","00:01:00","2018-02-28","23:59:00",333,"All day","track closure",null,"ST",null,null,null,null,null,null,"x"]
[null,"PKP PLK",6,"Warszawa - Terespol","W-E, E-W","Sadowne Węgrowskie","Sadowne Węgrowskie",2017,2018,13,9,"2017-04-01","00:01:00","2018-02-28","23:59:00",333,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",6,"Warszawa - Terespol",null,"Prostyń","Małkinia",2017,2018,23,13,"2017-06-11","00:01:00","2018-03-31","23:59:00",293,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",6,"Warszawa - Terespol",null,"Małkinia",null,2017,2018,13,13,"2017-04-01","00:01:00","2018-03-31","23:59:00",364,"All day","track closure",null,"ST",null,null,null,null,null,null,"x"]
[null,"PKP PLK",6,"Warszawa - Terespol","E-W","Małkinia","Czyżew",2017,2018,13,13,"2017-04-01","00:01:00","2018-03-31","23:59:00",364,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",12,"Warszawa - Terespol",null,"Pilawa",null,2017,2017,23,49,"2017-06-11","00:01:00","2017-12-10","23:59:00",162,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"8,10,12,14,16,18,30,32,33,34,35,36"]
[null,"PKP PLK",12,"Warszawa - Terespol",null,"Pilawa","Stoczek Łukowski",2017,2017,37,49,"2017-09-17","00:01:00","2017-12-10","23:59:00",64,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",13,"Warszawa - Terespol","<=>","Pustelnik ","Mińsk Mazowiecki",2017,2017,27,33,"2017-07-03","00:01:00","2017-08-14","23:59:00",42,"All day","track closure","x",null,null,null,null,null,"x"]
[null,"PKP PLK",14,"Poznan - Warszawa",null,"Ostrów Wlkp. Zach","Biadki",2017,2017,31,33,"2017-08-01","00:01:00","2017-08-14","23:59:00",13,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",14,"Poznan - Warszawa",null,"Krotoszyn","Kobylin",2017,2017,23,27,"2017-06-11","00:01:00","2017-07-05","23:59:00",24,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",14,"Poznan - Warszawa",null,"Opatówek","Radliczyce",2017,2017,25,26,"2017-06-19","00:01:00","2017-06-30","23:59:00",11,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK","17\nDeleted","Poznan - Warszawa","<=>","Łódź Widzew","Koluszki",2017,2017,41,50,"2017-10-12","00:01:00","2017-12-13","23:59:00",62,null,"track closure","x",null,null,null,null,null,"x"]
[null,"PKP PLK",19,"Warszawa - Terespol",null,"Warszawa Główna Towarowa ","Józefinów",2017,2017,23,36,"2017-06-11","00:01:00","2017-09-04","23:59:00",85,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",20,"Warszawa - Terespol",null,"Warszawa Zachodnia","Warszawa Gdaska",2017,2018,11,10,"2017-03-13","00:01:00","2018-03-10","23:59:00",362,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",20,"Warszawa - Terespol",null,"Warszawa Gdańska",null,2017,2017,41,49,"2017-10-15","00:01:00","2017-12-09","23:59:00",55,"All day","track closure",null,"ST",null,null,null,null,null,null,"x"]
[null,"PKP PLK",353,"Warszawa - Trakiszki",null,"Ostrowite","Biskupiec Pomorski",2017,2017,24,32,"2017-06-12","00:01:00","2017-08-10","23:59:00",95,"All day","track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK","353\nDeleted","Warszawa - Trakiszki",null,"Stare Jabłonki","Biesal",2017,2017,25,31,"2017-06-23","00:01:00","2017-07-31","23:59:00",38,null,"track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK",353,"Warszawa - Trakiszki",null,"Naterki",null,2017,2017,23,32,"2017-06-11","00:01:00","2017-08-10","23:59:00",19,"All day","track closure",null,"ST",null,null,null,null,null,null,"x",null,"closure track 1,3,5,7"]
[null,"PKP PLK","353\nDeleted","Warszawa - Trakiszki",null,"Ostróda",null,2017,2017,31,51,"2017-08-01","00:01:00","2017-12-22","23:59:00",143,null,"track closure",null,"ST",null,null,null,null,null,null,"x",null,"closure track 1"]
[null,"PKP PLK","353\nDeleted","Warszawa - Trakiszki",null,"Ostróda","Stare Jabłonki",2017,2017,31,51,"2017-08-01","00:01:00","2017-12-22","23:59:00",143,null,"track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK","353\nDeleted","Warszawa - Trakiszki",null,"Stare Jabłonki",null,2017,2017,31,51,"2017-08-01","00:01:00","2017-12-22","23:59:00",143,null,"track closure",null,"ST",null,null,null,null,null,null,"x",null,"closure track 1,3"]
[null,"PKP PLK","353\nDeleted","Warszawa - Trakiszki",null,"Stare Jabłonki","Biesal",2017,2017,42,51,"2017-10-18","00:01:00","2017-12-22","23:59:00",65,null,"track closure",null,"x",null,null,null,null,null,null,"x"]
[null,"PKP PLK","353\nDeleted","Warszawa - Trakiszki",null,"Biesal",null,2017,2017,42,51,"2017-10-18","00:01:00","2017-12-22","23:59:00",65,null,"track closure",null,"ST",null,null,null,null,null,null,"x",null,"closure track 2,4,6"]
[null,"PKP PLK",821,"Frankurt (O) - Poznan","<=>","Jerzmanice ","Rzepin",2017,2017,9,17,"2017-03-01","00:01:00","2017-04-30","23:59:00",60,"All day","track closure","x",null,null,null,null,null,null,null,null,"x","bus service"]
[null,"PKP",10032,"Poznan - Warszawa","<>","Podstolice","Kostrzyn Wielkopolski",2018,2018,15,38,"2018-04-11","00:00:00","2018-09-23","04:00:00",null,"night",null,"x",null,null,null,null,null,null,null,null,null,"4h, column M and O can be changed due to RU's need's"]
[null,"PKP",10033,"Poznan - Warszawa","<>","Kostrzyn Wielkopolski","Swarzędz",2017,2018,47,19,"2017-11-24","00:00:00","2018-05-08","04:00:00",null,"night",null,"x",null,null,null,null,null,null,null,null,null,"4h, column M and O can be changed due to RU's need's"]
[null,"PKP",10034,"Poznan - Warszawa","<>","Kłodawa","Krzewie",2017,2018,41,8,"2017-10-15","00:00:00","2018-02-22","04:00:00",null,"night",null,"x",null,null,null,null,null,null,null,null,null,"4h, column M and O can be changed due to RU's need's"]
[null,"PKP",10035,"Poznan - Warszawa","<>","Żychlin","Jackowice",2017,2018,41,7,"2017-10-15","00:00:00","2018-02-17","04:00:00",null,"night",null,"x",null,null,null,null,null,null,null,null,null,"4h, column M and O can be changed due to RU's need's"]
[null,"PKP",10036,"Poznan - Warszawa","<>","Koło","Kramsk",2017,2018,50,31,"2017-12-11","00:00:00","2018-07-31","04:00:00",null,"Night",null,"x",null,null,null,null,null,null,null,null,null,"4h, column M and O can be changed due to RU's need's"]
[null,"PKP",10037,"Poznan - Warszawa","<>","Łowicz","Łowicz",2018,2018,17,38,"2018-04-23","00:00:00","2018-09-17","23:59:00",null,"All day",null,null,null,null,null,null,null,null,null,null,null,"track no 1 or 2"]
[null,"PKP",10038,"Poznan - Warszawa","<>","Łowicz","Łowicz",2018,2018,17,38,"2018-04-23","00:00:00","2018-09-17","04:00:00",null,"night",null,"x"]
[null,"PKP",10039,"Poznan - Warszawa",null,"Placencja","Bełchów",2018,2018,21,42,"2018-05-24","00:00:00","2018-10-20","23:59:00",null,"All day",null,null,null,null,null,null,null,null,null,null,null,"track no 1 or 2"]
[null,"PKP",10040,"Poznan - Warszawa",null,"Grodzisk Maz.","Warszawa Włochy",2018,2018,36,44,"2018-09-04","00:00:00","2018-11-04","23:59:00",null,"All day",null,null,null,null,null,null,null,null,null,null,null,"track no 1 or 2"]
[null,"PKP",10041,"Poznan - Warszawa","<>","Warszawa Zachodnia","Koluszki",2017,2018,50,1,"2017-12-11","00:00:00","2018-01-02","04:00:00",null,"night",null,null,"x",null,null,null,null,null,null,null,null,"chosen part of line per night/ track no 1 or 2"]
[null,"PKP",10042,"Poznan - Warszawa","<>","Grodzisk Maz.","Koluszki",2018,2018,29,45,"2018-07-20","00:00:00","2018-11-07","04:00:00",null,"night",null,null,"x",null,null,null,null,null,null,null,null,"chosen part of line per night/ track no 1 or 2"]
[null,"PKP",10043,"Poznan - Warszawa","<>","Warszawa Zachodnia","Koluszki",2018,2018,1,13,"2018-01-02","00:00:00","2018-03-30","04:00:00",null,"night",null,"x",null,null,null,null,null,null,null,null,null,"4 h total clousure"]
[null,"PKP",10044,"Poznan - Warszawa","<>","Grodzisk Maz.","Koluszki",2017,2017,41,50,"2017-10-12","00:00:00","2017-12-13","04:00:00",null,"night",null,"x",null,null,null,null,null,null,null,null,null,"4 h total clousure"]
[null,"PKP",10045,"Warszawa - Terespol",null,"Małaszewicze",null,2018,2019,15,10,"2018-04-09","00:00:00","2019-03-07","23:59:00",null,"All day",null,null,"x",null,null,null,null,null,null,null,null,"1,3,3a,5,7,9,11,41,41b,101,405,405b,407"]
[null,"PKP",10046,"Warszawa - Terespol",null,"Terespol",null,2018,2019,10,10,"2018-03-08","00:00:00","2019-03-07","23:59:00",null,"All day",null,null,"x",null,null,null,null,null,null,null,null,"1,3,5,7,51,53,55,47,9,11,13,15,17"]
[null,"PKP",10047,"Warszawa - Terespol","<>","Biała Podlaska","Chotyłów",2018,2019,11,5,"2018-03-15","22:00:00","2019-01-31","04:00:00",null,"Night",null,"x",null,null,null,null,null,null,null,null,null,"hours can be changed due to needs"]
[null,"PKP",10048,"Warszawa - Terespol","<>","Chotyłów","Małaszewicze",2018,2019,15,10,"2018-04-09","22:00:00","2019-03-07","04:00:00",null,"Night",null,"x",null,null,null,null,null,null,null,null,null,"hours can be changed due to needs"]
[null,"PKP",10049,"Warszawa - Terespol",">","Stoczek Łukowski","Pilawa",2017,2017,44,49,"2017-11-01","00:00:00","2017-12-10","23:59:00",null,"All day"]
[null,"PKP",10050,"Poznan - Warszawa",null,"Koluszki","Łódź Fabryczna",2017,2019,41,9,"2017-10-12","00:00:00","2019-02-27","04:00:00",null,"night",null,null,null,null,null,null,null,null,null,null,null,"4h, periodical one path of line, track no 1 or 2"]
[null,"PKP",10051,"Poznan - Warszawa",null,"Warszawa Główna Tow.","Warszawa Praga",2017,2018,41,41,"2017-10-12","00:00:00","2018-10-12","23:59:00",null,"All day",null,null,"x"]
[null,"PKP",10052,"Wroclaw - Katowice",null,"Mysłowicce","Katowice Zawodzie",2018,2018,27,52,"2018-07-05","00:00:00","2018-12-25","23:59:00",null,"All day",null,null,"x",null,null,null,null,null,null,null,null,"track no 1 or 2"]
[null,"PKP",10053,"Wroclaw - Katowice","<>","Kozioł","Sosnowiec Dańdówka",2018,2018,18,42,"2018-05-03","00:00:00","2018-10-15","23:59:00",null,"All day",null,null,"x",null,null,null,null,null,null,null,null,"track no 1 or 2"]
[null,"PKP",10054,"Poznan - Warszawa","<","Bronów","Biniew",2018,2018,29,31,"2018-07-18","00:00:00","2018-08-01","23:59:00",null,"All day",null,null,"x"]
[null,"PKP",10055,null,">","Zielona Góra","Niedoradz",2017,2018,50,22,"2017-12-11","00:00:00","2018-05-30","23:59:00",null,"All day"]
[null,"PKP",10056,null,">","Grębocice","Głogów",2018,2018,12,45,"2018-03-19","00:00:00","2018-11-10","23:59:00",null,"All day",null,null,"x"]
[null,"PKP",10057,null,">","Czerwieńsk","Niełkowice",2018,2018,3,19,"2018-01-15","00:00:00","2018-05-12","23:59:00",null,"All day"]
[null,"PKP",10058,null,"<>","Budachów","Gądków",2018,2018,9,29,"2018-03-01","00:00:00","2018-07-20","23:59:00",null,"All day",null,null,"x",null,null,null,null,null,null,null,null,"track no 1 or 2"]
[null,"PKP",10059,null,"<>","Radnica","Budachów",2018,2018,29,49,"2018-07-21","00:00:00","2018-12-09","23:59:00",null,"All day",null,null,"x",null,null,null,null,null,null,null,null,"track no 1 or 2"]
[null,"PKP",10060,"Wegliniec - Wroclaw",">","Wrocław Muchobór","Legnica",2017,2018,42,23,"2017-10-16","22:00:00","2018-06-05","06:00:00",null,"Night",null,null,null,null,null,null,null,null,null,null,null,"8h for ERTMS, hours can be changed due to needs"]
[null,"PKP",10061,"Warszawa - Terespol",">","Warszawa Praga","Warszaw aWschodnia Tow.",2018,2019,48,5,"2018-12-02","00:00:00","2019-01-31","23:59:00",null,"All day",null,null,"x"]
[null,"PKP",10062,"Wroclaw - Katowice",null,"Sosnowiec Maczki","Długoszyn",2018,2018,17,18,"2018-04-25","22:00:00","2018-04-30","04:00:00",null,"Night",null,"x",null,null,null,null,null,null,null,null,null,"6h, hours can be changed due needs"]
[null,"PKP",10064,null,null,"Naterki","Olsztyn",2017,2018,49,3,"2017-12-04","00:00:00","2018-01-15","23:59:00",null,"All day",null,null,"x"]
[null,"PKP",10065,null,null,"Naterki","Olsztyn",2018,2018,20,28,"2018-05-14","00:00:00","2018-07-12","23:59:00",null,"All day",null,null,"x"]
[null,"PKP",10066,"Poznan - Warszawa","<>","Barłogi","Kłodawa",2018,2019,35,25,"2018-09-01","09:00:00","2019-06-17","18:00:00",null,"All day",null,null,"x",null,null,null,null,null,null,null,null,"track 1 or 2"]
[null,"PKP",10067,"Poznan - Warszawa","<>","Barłogi","Kłodawa",2018,2019,35,25,"2018-09-01","00:00:00","2019-06-17","04:00:00",null,"Night",null,"x",null,null,null,null,null,null,null,null,null,"track 1 or 2"]
[null,"PKP",10068,"Poznan - Warszawa","<>","Barłogi","Koło",2018,2019,29,31,"2018-07-16","09:00:00","2019-07-30","18:00:00",null,"All day",null,"x",null,null,null,null,null,null,null,null,null,"track 1 and 2 - total clousure"]
[null,"PKP",10069,null,">","Dąbrowa Górnicza Tow","Sosnowiec Dańsdówka",2019,2019,26,48,"2019-06-24","18:00:00","2019-11-29","18:00:00",null,"All day",null,null,"x",null,null,null,null,null,null,null,null,"track 2"]
[null,"PKP",10070,"Poznan - Warszawa","<>","Jackowice","Łowicz",2018,2019,46,28,"2018-11-13","09:00:00","2019-07-11","18:00:00",null,"All day",null,null,"x",null,null,null,null,null,null,null,null,"track 1 or 2"]
[null,"PKP",10071,"Poznan - Warszawa","<","Kutno","Stara Wieś",2019,2019,9,30,"2019-02-26","09:00:00","2019-07-24","18:00:00",null,"All day",null,null,"x",null,null,null,null,null,null,null,null,"track 2"]
[null,"PKP",10072,"Poznan - Warszawa","<>","Liblinek","Pabianice",2019,2019,15,46,"2019-04-12","09:00:00","2019-11-15","09:00:00",null,"All day",null,null,"x",null,null,null,null,null,null,null,null,"track 1 or 2"]
[null,"PKP",10073,"Poznan - Warszawa","<>","Łask","Zduńska Wola",2019,2019,15,46,"2019-04-12","09:00:00","2019-11-15","09:00:00",null,"All day",null,null,"x",null,null,null,null,null,null,null,null,"track 1 or 2"]
[null,"PKP",10074,"Warszawa - Trakiszki","<>","Białystok",null,2019,2020,14,37,"2019-04-05","09:00:00","2020-09-13","09:00:00",null,"All day",null,null,"st",null,null,null,null,null,null,null,null,"left part or right part of station"]
[null,"PKP",10075,"Poznan - Warszawa",">","Jackowice",null,2018,2019,46,15,"2018-11-13","09:00:00","2019-04-12","09:00:00",null,"All day",null,null,"st","x",null,null,null,null,null,null,null,"track 1, track 2 speed restriction"]
[null,"PKP",10076,"Poznan - Warszawa",">","Jackowice",null,2018,2019,46,15,"2018-11-13","00:00:00","2019-04-12","04:00:00",null,"Night",null,"x","st",null,null,null,null,null,null,null,null,"track 2"]
[null,"PKP",10077,"Poznan - Warszawa","<>","Kutno",null,2018,2019,30,45,"2018-07-27","09:00:00","2019-11-04","09:00:00",null,"All day",null,null,"st",null,null,null,null,null,null,null,null,"various trakcs"]
[null,"PKP",10078,"Poznan - Warszawa","<>","Łowicz",null,2018,2019,46,28,"2018-11-13","09:00:00","2019-07-11","09:00:00",null,"All day",null,null,"st",null,null,null,null,null,null,null,null,"track 1 or 2"]
[null,"PKP",10079,"Poznan - Warszawa","<>","Łowicz",null,2018,2019,46,28,"2018-11-13","00:00:00","2019-07-11","04:00:00",null,"Night",null,"x","st",null,null,null,null,null,null,null,null,"track 1 or 2"]
[null,"PKP",10080,"Poznan - Warszawa","<>","Jackowice","Łowicz",2018,2019,46,28,"2018-11-13","00:00:00","2019-07-11","04:00:00",null,"Night",null,"x","x",null,null,null,null,null,null,null,null,"track 1 or 2"]
[null,"PKP",10081,"Warszawa - Terespol","<","Małaszewicze",null,2019,2019,11,45,"2019-03-11","00:00:00","2019-11-07","00:00:00",null,"All day",null,null,"st",null,null,null,null,null,null,null,null,"track 2"]
[null,"PKP",10082,"Warszawa - Terespol",null,"Pilawa",null,2019,2019,21,28,"2019-05-23","00:00:00","2019-07-11","00:00:00",null,"All day",null,null,"st",null,null,null,null,null,null,null,null,"tracks 2, 4"]
[null,"PKP",10083,"Poznan - Warszawa","<","Stara Wieś",null,2018,2019,50,26,"2018-12-10","00:00:00","2019-06-28","00:00:00",null,"All day",null,null,"st",null,null,null,null,null,null,null,null,"track 2"]
[null,"PKP",10084,"Poznan - Warszawa","<","Stara Wieś",null,2018,2019,50,26,"2018-12-10","00:00:00","2019-06-28","04:00:00",null,"Night",null,"x","st",null,null,null,null,null,null,null,null,"track 1"]
[null,"PKP",10085,"Warszawa - Terespol","<>","Terespol",null,2019,2020,10,1,"2019-03-08","00:00:00","2020-01-02","00:00:00",null,"All day",null,null,"st",null,null,null,null,null,null,null,null,"track 1 or 2"]
[null,"PKP",10086,"Poznan - Warszawa","<","Żychlin",null,2018,2019,35,5,"2018-08-27","00:00:00","2019-01-31","00:00:00",null,"All day",null,null,"st",null,null,null,null,null,null,null,null,"tracks 1,3,5"]
[null,"PKP",10087,"Poznan - Warszawa","<>","Żychlin",null,2018,2019,35,5,"2018-08-27","00:00:00","2019-01-31","04:00:00",null,"Night",null,"x","st"]
[null,"PKP",10088,"Poznan - Warszawa",">","Stara Wieś","Żychlin",2018,2019,35,5,"2018-08-27","00:00:00","2019-01-31","00:00:00",null,"All day",null,null,"x",null,null,null,null,null,null,null,null,"track 2"]
[null,"PKP",10089,"Poznan - Warszawa","<>","Stara Wieś","Żychlin",2018,2019,35,5,"2018-08-27","00:00:00","2019-01-31","04:00:00",null,"Night",null,"x","x"]
[null,"PKP",10090,"Warszawa - Terespol","<","Chotyłów","Małaszewicze",2019,2020,45,6,"2019-11-08","00:00:00","2020-02-03","00:00:00",null,"All day",null,null,"x",null,null,null,null,null,null,null,null,"track 2"]
[null,"PKP",10091,"Poznan - Warszawa","<>","Krzewie","Kutno",2019,2019,9,33,"2019-02-26","00:00:00","2019-08-17","00:00:00",null,"All day",null,null,"x",null,null,null,null,null,null,null,null,"track 1 or 2"]
[null,"PKP",10092,"Poznan - Warszawa","<>","Krzewie","Kutno",2019,2019,9,33,"2019-02-26","00:00:00","2019-08-17","04:00:00",null,"Night",null,"x","x"]
[null,"PKP",10093,"Warszawa - Terespol","<>","Sokule","Biała Podlaska",2019,2020,5,19,"2019-02-01","00:00:00","2020-05-04","00:00:00",null,"All day",null,null,"x",null,null,null,null,null,null,null,null,"track 1 or 2"]
[null,"PKP",10094,"Poznan - Warszawa",">","Stara Wieś","Żychlin",2019,2019,23,48,"2019-06-03","00:00:00","2019-11-30","00:00:00",null,"All day",null,null,"x",null,null,null,null,null,null,null,null,"track 2"]
[null,"PKP",10095,"Poznan - Warszawa",">","Stara Wieś","Żychlin",2019,2019,23,48,"2019-06-03","00:00:00","2019-11-30","04:00:00",null,"Night",null,"x","x"]
[null,"PKP",10096,"Poznan - Warszawa","<>","Warszawa Główna Tow.","Warszawa Praga",2019,2019,5,31,"2019-02-01","00:00:00","2019-07-31","00:00:00",null,"All day",null,null,"x"]
[null,"SŽDC","V-009493/17","Decin - Praha","<>","Vraňany","Dolní Beřkovice",2018,2018,24,24,"2018-06-14",null,"2018-06-16T23:59:59",null,"3 days","All day","Signal - Road crossing","","LT","","","","","","","","","2. + TV. ","","",""]
[null,"SŽDC","V-009493/17","Decin - Praha","<>","Dolní Beřkovice","",2018,2018,24,24,"2018-06-14",null,"2018-06-16T23:59:59",null,"3 days","All day","Signal - Road crossing","","ST","","","","","","","","","2.,4. jen TV. \nzáhlaví vraňanské 2. traťové koleje","","",""]
[null,"SŽDC","V-009491/17","Decin - Praha","<>","Dolní Beřkovice","Vraňany",2018,2018,24,24,"2018-06-11",null,"2018-06-13T23:59:59",null,"3 days","All day","Signal - Road crossing","","LT","","","","","","","","","1. + TV. ","","",""]
[null,"SŽDC","V-009491/17","Decin - Praha","<>","Dolní Beřkovice","",2018,2018,24,24,"2018-06-11",null,"2018-06-13T23:59:59",null,"3 days","All day","Signal - Road crossing","","ST","","","","","","","","","1.,3.,5. jen TV. \nzáhlaví vraňanské 1. traťové koleje","","",""]
[null,"SŽDC","V-009489/17","Decin - Praha","<>","Dolní Beřkovice","Hněvice",2018,2018,45,45,"2018-11-07",null,"2018-11-08T23:59:59",null,"2 days","All day","Signal - Road crossing","","LT","","","","","","","","","2. + TV. ","","",""]
[null,"SŽDC","V-009488/17","Decin - Praha","<>","Hněvice","Dolní Beřkovice",2018,2018,45,45,"2018-11-05",null,"2018-11-06T23:59:59",null,"2 days","All day","Signal - Road crossing","","LT","","","","","","","","","1. + TV. ","","",""]
[null,"SŽDC","V-009487/17","Decin - Praha","<>","Dolní Beřkovice","Hněvice",2018,2018,20,20,"2018-05-17",null,"2018-05-19T23:59:59",null,"3 days","All day","Signal - Road crossing","","LT","","","","","","","","","2. + TV. ","","",""]
[null,"SŽDC","V-009486/17","Decin - Praha","<>","Hněvice","Dolní Beřkovice",2018,2018,20,20,"2018-05-14",null,"2018-05-16T23:59:59",null,"3 days","All day","Signal - Road crossing","","LT","","","","","","","","","1. + TV. ","","",""]
[null,"SŽDC","V-009474/17","Decin - Praha","<>","Děčín hlavní nádraží","",2018,2018,47,47,"2018-11-19",null,"2018-11-25T23:59:59",null,"7 days","All day","Track & Rail","","ST","","","","","","","","","23.,21. bez TV, 21. jen TV, výh.: č. 42. \nzhlaví střední staničních kolejí č. 21, 23 po návěstidlo Se13.","","",""]
[null,"SŽDC","V-009473/17","Decin - Praha","<>","Děčín hlavní nádraží","",2018,2018,46,46,"2018-11-12",null,"2018-11-18T23:59:59",null,"7 days","All day","Switch","","ST","","","","","","","","","15. bez TV, 15.,27.,29. jen TV, výh.: č. 46, 47. \nzhlaví střední staniční koleje č. 15 po námezník výhybky č. 47.","","",""]
[null,"SŽDC","V-009428/17","Decin - Praha","<>","Lovosice","",2018,2018,19,19,"2018-05-07",null,"2018-05-11T23:59:59",null,"5 days","All day","Switch","","ST","","","","","","","","","5.,7. jen TV. \nzhlaví střední staničních kolejí č. 5,7 od návěstidel L5, L7 po námezník výhybky č. 26.","","",""]
[null,"SŽDC","V-009415/17","Decin - Praha","<>","Lovosice","",2018,2018,39,39,"2018-09-27",null,"2018-09-29T23:59:59",null,"3 days","All day","Track & Rail","","ST","","","","","","","","","15.,17. bez TV, 13.,15.,17. jen TV. ","","",""]
[null,"SŽDC","V-009391/17","Decin - Praha","<>","Lovosice","",2018,2018,40,42,"2018-10-01",null,"2018-10-20T23:59:59",null,"20 days","All day","Track & Rail","","ST","","","","","","","","","113.,115. bez TV, 111.-117. jen TV. ","","",""]
[null,"SŽDC","V-009274/17","Decin - Praha","<>","Děčín hlavní nádraží","Povrly",2018,2018,35,40,"2018-09-01",null,"2018-10-02T23:59:59",null,"12 x 10 hours","Day","Other","","LT","","","","","","","","","1. + TV. redevelopment of rocks","","",""]
[null,"SŽDC","V-009276/17","Decin - Praha","<>","Děčín hlavní nádraží","Povrly",2018,2018,36,41,"2018-09-09",null,"2018-10-13T23:59:59",null,"16 x 10 hours","Day","Other","","LT","","","","","","","","","1. + TV. redevelopment of rocks","","",""]
[null,"SŽDC","V-009285/17","Decin - Praha","<>","Děčín hlavní nádraží","Povrly",2018,2018,38,42,"2018-09-20",null,"2018-10-15T23:59:59",null,"7 x 10 hours","Day","Other","","LT","","","","","","","","","1. + TV. redevelopment of rocks","","",""]
[null,"SŽDC","V-009294/17","Decin - Praha","<>","Děčín hlavní nádraží","Povrly",2018,2018,39,40,"2018-09-29",null,"2018-10-06T23:59:59",null,"6 x 10 hours","Day","Other","","LT","","","","","","","","","1. + TV. redevelopment of rocks","","",""]
[null,"SŽDC","V-009300/17","Decin - Praha","<>","Děčín hlavní nádraží","Povrly",2018,2018,40,42,"2018-10-07",null,"2018-10-18T23:59:59",null,"7 x 10 hours","Day","Other","","LT","","","","","","","","","1. + TV. redevelopment of rocks","","",""]
[null,"SŽDC","V-009313/17","Decin - Praha","<>","Děčín hlavní nádraží","Povrly",2018,2018,42,43,"2018-10-19",null,"2018-10-22T23:59:59",null,"4 x 10 hours","Day","Other","","LT","","","","","","","","","1. + TV. redevelopment of rocks","","",""]
[null,"SŽDC","V-009324/17","Decin - Praha","<>","Děčín hlavní nádraží","Povrly",2018,2018,43,44,"2018-10-23",null,"2018-10-31T23:59:59",null,"9 x 10 hours","Day","Other","","LT","","","","","","","","","1. + TV. redevelopment of rocks","","",""]
[null,"SŽDC","V-009090/17","Decin - Praha","<>","Děčín hl.n. západní nádraží","",2018,2018,45,47,"2018-11-05",null,"2018-11-24T23:59:59",null,"20 days","All day","Switch","","ST","","","","","","","","","203b bez TV, výh.: č. 361, 359, 357, 354, 353, 352, 350, 348, 345, 342, 339, 335. \nzáhlaví ze směru Jílové u Děčína a zhlaví  staničních kolejí č. 203b a 205 - 219","","",""]
[null,"SŽDC","V-009088/17","Decin - Praha","<>","Ústí nad Labem sever","",2018,2018,25,25,"2018-06-18",null,"2018-06-22T23:59:59",null,"5 days","All day","Switch","","ST","","","","","","","","","213. bez TV, 207.,207a,209.,211.,213 jen TV, výh.: č. 230. ","","",""]
[null,"SŽDC","V-009085/17","Decin - Praha","<>","Ústí nad Labem sever","",2018,2018,37,38,"2018-09-10",null,"2018-09-21T23:59:59",null,"12 days","All day","Track & Rail","","ST","","","","","","","","","212. bez TV, 206.,208.,210.,212.,214.,218b jen TV, výh.: č. 227 a část výh. č. 224. \nzhlaví střední staničních kolejí č. 208 a 210 po námezník výhybky č. 221.","","",""]
[null,"SŽDC","V-009083/17","Decin - Praha","<>","Ústí nad Labem sever","",2018,2018,24,24,"2018-06-11",null,"2018-06-15T23:59:59",null,"5 days","All day","Switch","","ST","","","","","","","","","205. + TV, výh.: č. 236. ","","",""]
[null,"SŽDC","V-009079/17","Decin - Praha","<>","Lovosice","",2018,2018,38,39,"2018-09-17",null,"2018-09-26T23:59:59",null,"10 days","All day","Switch","","ST","","","","","","","","","výh.: č. 107, 109, 111. \nzhlaví bohušovické staniční koleje č. 101 od návěstidla S101 po hroty jazyků výhybky č. 107.","","",""]
[null,"SŽDC","V-009071/17","Decin - Praha","<>","Lovosice","",2018,2018,35,37,"2018-09-01",null,"2018-09-14T23:59:59",null,"14 days","All day","Switch","","ST","","","","","","","","","91a,119a bez TV, výh.: č. 105, 108, 110, 112. \nzhlaví střední staniční koleje č. 91 a 119a v úseku od návěstidla Se105 po námezník výhybky č. 201b.","","",""]
[null,"SŽDC","V-009052/17","Decin - Praha","<>","Roudnice nad Labem","Hněvice",2018,2018,42,43,"2018-10-15",null,"2018-10-26T23:59:59",null,"12 days","All day","Track & Rail","","LT","","","","","","","","","1. + TV. ","","",""]
[null,"SŽDC","V-009050/17","Decin - Praha","<>","Hněvice","",2018,2018,41,42,"2018-10-08",null,"2018-10-15T23:59:59",null,"8 days","All day","Switch","","ST","","","","","","","","","316. bez TV, 310.,312.,314. jen TV, výh.: č. 301. \nzáhlaví vlečky Mondi a část zhlaví po námezník výhybky č. 303b","","",""]
[null,"SŽDC","V-009041/17","Decin - Praha","<>","Dolní Beřkovice","",2018,2018,40,40,"2018-10-01",null,"2018-10-05T23:59:59",null,"5 days","All day","Switch","","ST","","","","","","","","","5.,5a bez TV, 1.,3.,5. jen TV. \nzhlaví střední staniční koleje č. 5 - výhybka č. 8.","","",""]
[null,"SŽDC","V-009032/17","Decin - Praha","<>","Roudnice nad Labem","",2018,2018,24,24,"2018-06-11",null,"2018-06-15T23:59:59",null,"5 days","All day","Switch","","ST","","","","","","","","","5 bez TV, 1.,3.,3b,5 jen TV. \nzhlaví střední staniční koleje č. 3 a 5 po námezník výhybky č. 27.","","",""]
[null,"SŽDC","V-009028/17","Decin - Praha","<>","Roudnice nad Labem","",2018,2018,23,23,"2018-06-04",null,"2018-06-08T23:59:59",null,"5 days","All day","Switch","","ST","","","","","","","","","3b bez TV, 1.,3.,3b,5 jen TV. \nzhlaví střední staniční koleje č. 3b po námezník výhybky č. 10.","","",""]
[null,"SŽDC","V-008390/17","Decin - Praha","<>","Děčín východ","Děčín hlavní nádraží",2018,2018,37,37,"2018-09-10",null,"2018-09-14T23:59:59",null,"5 days","All day","Switch","","LT","","","","","","B","","","traťová bez TV. ","","",""]
[null,"SŽDC","V-008203/17","Decin - Praha","<>","Nelahozeves","Vraňany",2018,2018,14,17,"2018-04-04",null,"2018-04-23T23:59:59",null,"20 x 10 hours","Day","Other","","LT","","","","","","","","","2. + TV. ","","",""]
[null,"SŽDC","V-008185/17","Decin - Praha","<>","Vraňany","Nelahozeves",2018,2018,11,13,"2018-03-17",null,"2018-03-28T23:59:59",null,"12 x 10 hours","Day","Other","","LT","","","","","","","","","1. + TV. ","","",""]
[null,"SŽDC","V-008191/17","Decin - Praha","<>","Vraňany","Nelahozeves",2018,2018,13,13,"2018-03-29",null,"2018-04-01T23:59:59",null,"4 x 10 hours","Day","Other","","LT","","","","","","","","","1. + TV. ","","",""]
[null,"SŽDC","V-008201/17","Decin - Praha","<>","Vraňany","Nelahozeves",2018,2018,14,14,"2018-04-02",null,"2018-04-03T23:59:59",null,"2 x 10 hours","Day","Other","","LT","","","","","","","","","1. + TV. ","","",""]
[null,"SŽDC","V-008176/17","Decin - Praha","<>","Lovosice","",2018,2018,39,48,"2018-09-28",null,"2018-11-26T23:59:59",null,"60 days","All day","Other","","ST","","","","","","","","","1.,3. + TV. ","","",""]
[null,"SŽDC","V-008175/17","Decin - Praha","<>","Lovosice","",2018,2018,26,39,"2018-06-30",null,"2018-09-27T23:59:59",null,"90 days","All day","Other","","ST","","","","","","","","","2.,4.,6. + TV. ","","",""]
[null,"SŽDC",null,"Decin - Praha","<>","Libčice n. V.","Roztoky u P.",2019,2019,14,22,"2019-04-01",null,"2017-05-31",null,"12 days","All day","Track & Rail","","LT","","","","","","","","",null,"","",""]
[null,"SŽDC",null,"Decin - Praha","<>","Libčice n. V.","Kralupy n. V.",2019,2019,14,22,"2019-04-01",null,"2017-05-31",null,"6 days","All day","Track & Rail","","LT","","","","","","","","",null,"","",""]
[null,"Prorail","L-004882 1801","Amsterdam - Amersfoort","< >","Keverdijk-","Weesp",2018,2018,2,2,"13-01-2018",null,"15-01-2018",null,2.0833333333333335,null,"Refresh sleepers and (partially) track. Refresh over and over.","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","R-434500 1811","Meteren - Zevenaar","< >","Zevenaar oost","Zevenaar Border",2018,2018,3,3,"20-01-2018",null,"22-01-2018",null,2.125,null,"3rd track work","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","R-434500 1812","Meteren - Zevenaar",">","Zevenaar oost","Zevenaar Border",2018,2018,3,4,"22-01-2018",null,"29-01-2018",null,7,null,"3rd track work",null,"X",null,null,null,null,"X",null,"X"]
[null,"Prorail","M-004514 06","Utrecht - Merten","< >","Utrecht","Geldermalsen",2018,2018,5,5,"2018-02-03",null,"2018-02-05",null,2.1666666666666665,null,"Refresh sleepers and (partially) track. Refresh over and over.","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","R-434500 1813","Meteren - Zevenaar",">","Zevenaar oost","Zevenaar Border",2018,2018,7,8,"19-02-2018",null,"26-02-2018",null,7,null,"3rd track work","X","X",null,null,null,null,"X",null,"X"]
[null,"Prorail","M-004514 06","Utrecht - Merten","< >","Utrecht","Geldermalsen",2018,2018,9,9,"2018-03-03",null,"2018-03-05",null,2.1666666666666665,null,"Refresh sleepers and (partially) track. Refresh over and over.","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","R-434500 1814","Meteren - Zevenaar","< >","Zevenaar oost","Zevenaar Border",2018,2018,11,11,"17-03-2018",null,"19-03-2018",null,2.125,null,"3rd track work","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","R-434500 1815","Meteren - Zevenaar",">","Zevenaar oost","Zevenaar Border",2018,2018,11,12,"19-03-2018",null,"26-03-2018",null,6.958333333333333,null,"3rd track work",null,"X",null,null,null,null,"X",null,"X"]
[null,"Prorail","K-006022 1805","Rotterdam - Meteren","< >","Kijfhoek Local",null,2018,2018,13,13,"31-03-2018",null,"02-04-2018",null,2.1666666666666665,null,"Refresh overhead driving wire","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","L-005010 1809","Amsterdam - Amersfoort","< >","Muiderpoort-","Weesp",2018,2018,14,14,"08-04-2018",null,"08-04-2018",null,"16:00:00",null,"Refresh overhead driving wire","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","L-004877 1837","Amsterdam - Meteren","< >","Amsterdam-","Amsterdam-Bijlmer",2018,2018,16,16,"21-04-2018",null,"23-04-2018",null,2.1666666666666665,null,"Conserve bridges","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","M-004514 11A","Den Bosch - Roosendaal","< >","Tilburg ","Den Bosch",2018,2018,16,16,"21-04-2018",null,"23-04-2018",null,2.1666666666666665,null,"Track and switch renewal","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","R-434500 1816","Meteren - Zevenaar",">","Zevenaar oost","Zevenaar Border",2018,2018,16,17,"23-04-2018",null,"30-04-2018",null,7,null,"3rd track work",null,"X",null,null,null,null,"X",null,"X"]
[null,"Prorail","D-002882 1801","Amersfoort - Bad Bentheim","< >","Barneveld-","Apeldoorn",2018,2018,17,18,"2018-04-28",null,"07-05-2018",null,9.1041666666666661,null,"Refresh track rails, railroadcrsossing and switches","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","V-D00212 ZD02","Den Bosch - Roosendaal","< >","Tilburg ","Den Bosch",2018,2018,17,17,"2018-04-28",null,"2018-04-29",null,28,null,"Track and switch renewal","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","L-004961 1808","Amsterdam - Meteren",">","Muiderpoort","Duivendrecht",2018,2018,17,17,"24-11-2018",null,"26-11-2018",null,2.1666666666666665,null,"Conserve bridges",null,"X",null,null,null,null,"X",null,"X"]
[null,"Prorail","M-004540 03A","Roosendaal - Antwerp","< >","Dordrecht","Essen",null,null,18,18,"2018-05-05",null,"2018-05-07",null,2.1666666666666665,null,"Track and switch renewal","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","R-389700 1801","Amersfoort - Bad Bentheim","< >","Deventer-","Wierden",2018,2018,19,19,"11-05-2018",null,"14-05-2018",null,3.1666666666666665,null,"Replace roofing and building ecoduct","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","R-434500 1817","Meteren - Zevenaar","< >","Zevenaar oost","Zevenaar Border",2018,2018,20,21,"19-05-2018",null,"28-05-2018",null,9.125,null,"3rd track work","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","Z-906006 1805","Amsterdam - Meteren","< >","Muiderpoort","Duivendrecht",2018,2018,21,21,"26-05-2018",null,"28-05-2018",null,2.125,null,"Replace roofing and conserve platform caps","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","D-002882 1815","Amersfoort - Bad Bentheim","< >","Barneveld-","Apeldoorn",2018,2018,22,22,"02-06-2018",null,"04-06-2018",null,2.1041666666666665,null,"Refresh track rails, railroadcrsossing and switches","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","M-004540 03B","Roosendaal - Antwerp","< >","Roosendaal","Essen",null,null,23,23,"09-06-2018",null,"11-06-2018",null,2.1666666666666665,null,"Track renewal","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","R-434500 1818","Meteren - Zevenaar","< >","Zevenaar oost","Zevenaar Border",2018,2018,23,23,"09-06-2018",null,"11-06-2018",null,2.125,null,"3rd track work","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","L-005045 1808","Amsterdam - Meteren","< >","Muiderpoort","Duivendrecht",2018,2018,25,25,"24-06-2018",null,"25-06-2018",null,1.1666666666666667,null,"Refresh overhead driving wire","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","M-004514 12C","Den Bosch - Roosendaal",">","Tilburg ","Den Bosch",2018,2018,26,26,"2018-06-30",null,"2018-07-02",null,2.1666666666666665,null,"Track and switch renewal",null,"X",null,null,null,null,"X",null,"X"]
[null,"Prorail","R-434500 1819","Meteren - Zevenaar","< >","Zevenaar oost","Zevenaar Border",2018,2018,29,30,"18-07-2018",null,"30-07-2018",null,12,null,"3rd track work","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","K-B17018 1807","Rotterdam - Meteren","< >","Barendrecht","Meteren",2018,2018,30,30,"23-07-2018",null,"24-07-2018",null,1,null,"Tunnelinstallations","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","R-434500 1820","Meteren - Zevenaar",">","Zevenaar oost","Zevenaar Border",2018,2018,33,34,"20-08-2018",null,"27-08-2018",null,7,null,"3rd track work",null,"X",null,null,null,null,"X",null,"X"]
[null,"Prorail","M-004514 10A","Den Bosch - Roosendaal","< >","Tilburg ","Den Bosch",2018,2018,33,33,"2018-08-18",null,"20-08-2018",null,2.1666666666666665,null,"Track  renewal","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","M-004514 07","Den Bosch - Roosendaal","< >","Tilburg ","Den Bosch",2018,2018,33,33,"01-09-2018",null,"2018-09-02",null,36,null,"Track  renewal","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","L-004946 1806","Amsterdam - Meteren","< >","Amsterdam","Westhaven",2018,2018,35,35,"01-09-2018",null,"03-09-2018",null,2.1666666666666665,null,"Track and switch renewal","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","D-002882 1816","Amersfoort - Bad Bentheim","< >","Barneveld-","Apeldoorn",2018,2018,36,36,"08-09-2018",null,"10-09-2018",null,2.1041666666666665,null,"Refresh track rails, railroadcrsossing and switches","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","R-434500 1823","Meteren - Zevenaar","< >","Zevenaar oost","Zevenaar Border",2018,2018,37,37,"15-09-2018",null,"17-09-2018",null,2.125,null,"Refresh sleepers and (partially) track. Refresh over and over.","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","L-004946 1807","Amsterdam - Meteren",">","Amsterdam","Westhaven",2018,2018,37,37,"15-09-2018",null,"17-09-2018",null,2.1666666666666665,null,"Track and switch renewal",null,"X",null,null,null,null,"X",null,"X"]
[null,"Prorail","Z-905838 ZD02","Den Bosch - Roosendaal","< >","Tilburg","Den Bosch",2018,2018,39,39,"29-09-2018",null,"01-10-2018",null,2.1666666666666665,null,"Discontinue temporary relief","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","D-002930 1801","Amersfoort - Bad Bentheim","< >","Hengenlo-","Enschede",2018,2018,42,42,"19-10-2018",null,"22-10-2018",null,3.1666666666666665,null,"Refresh track rails, railroadcrsossing and switches","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","R-389700 1802","Amersfoort - Bad Bentheim",">","Deventer-Wierden","Wierden",2018,2018,42,42,"20-10-2018",null,"21-10-2018",null,1.1666666666666667,null,"Replace roofing and conserve platform caps",null,"X",null,null,null,null,"X",null,"X"]
[null,"Prorail","R-434500 1821","Meteren - Zevenaar","< >","Zevenaar oost","Zevenaar Border",2018,2018,42,43,"22-10-2018",null,"29-10-2018",null,7.041666666666667,null,"Noise limitation measures 3rd track works","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","M-004514 02","Den Bosch - Roosendaal",">","Tilburg ","Vught",2018,2018,45,45,"2018-11-10",null,"2018-11-12",null,2.1666666666666665,null,"Track  renewal",null,"X",null,null,null,null,"X",null,"X"]
[null,"Prorail","R-434500 1822","Meteren - Zevenaar","< >","Zevenaar oost","Zevenaar Border",2018,2018,46,46,"17-11-2018",null,"19-11-2018",null,2.125,null,"Adjust rail protection system","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","L-004946 1805","Amsterdam - Meteren","< >","Amsterdam","Westhaven",2018,2018,46,46,"17-11-2018",null,"19-11-2018",null,2.1666666666666665,null,"Switch renewal","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","L-004877 1809","Amsterdam - Amersfoort","< >","Naarden bussem-","Hilversum",2018,2018,47,47,"25-11-2018",null,"26-11-2018",null,1,null,"Conserve bridges","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","R-524500 1804","Amsterdam - Amersfoort","< >","Naarden bussem","Hiversum",2018,2018,47,47,"24-11-2018",null,"26-11-2018",null,2.0833333333333335,null,"Adjust rail protection system","X",null,null,null,null,null,"X",null,"X"]
[null,"Prorail","D-002882 1817","Amersfoort - Bad Bentheim","< >","Barneveld-","Apeldoorn",2018,2018,48,48,"01-12-2018",null,"03-12-2018",null,2.1041666666666665,null,"Refresh track rails, railroadcrsossing and switches","X",null,null,null,null,null,"X",null,"X"]
[null,"Infrabel",11391,"Antwerp - Montzen","<>","Y.NAZARETH","HEIST-OP-DEN-BERG",2018,2019,7,8,"2018-02-17","01:00:00","2019-02-19","04:00:00","2 days","All day",null,"x",null,null,null,null,null,"x",null,null,null,"Netekanaal - Montzenroute via lijn 35-53/1-53-27B-27"]
[null,"Infrabel",11393,"Antwerp - Montzen","<>","Y.NAZARETH","HEIST-OP-DEN-BERG",2018,2018,8,9,"2018-02-24","01:00:00","2018-02-26","04:00:00","2 days","All day",null,"x",null,null,null,null,null,"x",null,null,null,"Netekanaal - Montzenroute via lijn 35-53/1-53-27B-27"]
[null,"Infrabel",11395,"Antwerp - Montzen","<>","Y.NAZARETH","HEIST-OP-DEN-BERG",2018,2018,9,10,"2018-03-03","01:00:00","2018-03-05","04:00:00","2 days","All day",null,"x",null,null,null,null,null,"x",null,null,null,"Netekanaal - Montzenroute via lijn 35-53/1-53-27B-27"]
[null,"Infrabel",13247,"Antwerp - Montzen","<","Bassenge","Visé",2018,2018,10,10,"2018-03-05","05:00:00","2018-03-08","05:59:00","4 days","All day","Bridge work",null,"x",null,null,null,null,null,null,null,null,"Viaduc des Allemands"]
[null,"Infrabel",13248,"Antwerp - Montzen","<>","Bassenge","Visé",2018,2018,10,11,"2018-03-09","06:00:00","2018-03-15",1.2493055555555601,"7 days","All day","Bridge work","x",null,null,null,null,null,"x",null,null,null,"Viaduc des Allemands\nRe routing via L40-Kinkempois-L36A-L36"]
[null,"Infrabel",13249,"Antwerp - Montzen",">","Bassenge","Visé",2018,2018,11,13,"2018-03-16","06:00:00","2018-03-30","16:00:00","15 days","All day","Bridge work",null,"x",null,null,null,null,null,null,null,null,"Viaduc des Allemands"]
[null,"Infrabel",13251,"Antwerp - Montzen",">","Y.Visé-Haut","Fouron",2018,2018,20,24,"2018-05-14","06:00:00","2018-06-10","16:00:00","28 days","All day","Platforms work",null,"x",null,null,null,null,null,null,null,null,"Assainissement Y.Visé-Haut-Fouron"]
[null,"Infrabel",11859,"Antwerp - Montzen","<>","Ant. Luchtbal","Y.Schijn",2018,2018,36,36,"2018-09-02","00:00:00","2018-09-02","17:40:00","17:40:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"Vernieuwing Ballast\nRe routing via L10"]
[null,"Infrabel",11860,"Antwerp - Montzen","<>","Ant. Luchtbal","Y.Schijn",2018,2018,37,37,"2018-09-09","00:00:00","2018-09-09","17:40:00","17:40:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"Vernieuwing Ballast\nRe routing via L10"]
[null,"Infrabel",13256,"Antwerp - Montzen",">","Y. Berneau","Fouron",2018,2018,37,42,"2018-09-10","06:00:00","2018-10-14","16:00:00","69 days","All day","Platforms work",null,"x",null,null,null,null,null,null,null,null,"Assainissement Y.Berneau-Fouron"]
[null,"Infrabel",11862,"Antwerp - Montzen","<>","Ant. Luchtbal","Y.Schijn",2018,2018,38,38,"2018-09-16","00:00:00","2018-09-16","17:40:00","17:40:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"Vernieuwing Ballast\nRe routing via L10"]
[null,"Infrabel","8810020\nDeleted","Antwerp - Montzen","<","Bassenge","Visé",2018,2018,38,40,"2018-09-20",1,"2018-10-01",1.9993055555555601,"11 days","All day","Bridge work",null,"x",null,null,null,null,null,null,null,null,"Pont sur Canal"]
[null,"Infrabel",11863,"Antwerp - Montzen","<>","Ant. Luchtbal","Y.Schijn",2018,2018,39,39,"2018-09-23","00:00:00","2018-09-23","17:40:00","17:40:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"Vernieuwing Ballast\nRe routing via L10"]
[null,"Infrabel",11865,"Antwerp - Montzen","<>","Ant. Luchtbal","Y.Schijn",2018,2018,40,40,"2018-09-30","00:00:00","2018-09-30","17:40:00","17:40:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"Vernieuwing Ballast\nRe routing via L10"]
[null,"Infrabel",11867,"Antwerp - Montzen","<>","Ant. Luchtbal","Y.Schijn",2018,2018,41,41,"2018-10-07","00:00:00","2018-10-07","17:40:00","17:40:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"Vernieuwing Ballast\nRe routing via L10"]
[null,"Infrabel",11870,"Antwerp - Montzen","<>","Ant. Luchtbal","Y.Schijn",2018,2018,42,42,"2018-10-14","00:00:00","2018-10-14","17:40:00","17:40:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"Vernieuwing Ballast\nRe routing via L10"]
[null,"Infrabel",11872,"Antwerp - Montzen","<>","Ant. Luchtbal","Y.Schijn",2018,2018,43,43,"2018-10-21","00:00:00","2018-10-21","17:40:00","17:40:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"Vernieuwing Ballast\nRe routing via L10"]
[null,"Infrabel",13259,"Antwerp - Montzen","<","Fouron","Remersdael",2018,2018,43,53,"2018-10-22","06:00:00","2018-12-31","23:59:00","71 days","All day","Tunnel work",null,"x",null,null,null,null,null,null,null,null,"Tunnel de Veurs"]
[null,"Infrabel",11875,"Antwerp - Montzen","<>","Ant. Luchtbal","Y.Schijn",2018,2018,45,45,"2018-11-04","00:00:00","2018-11-04","17:40:00","17:40:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"Vernieuwing Ballast\nRe routing via L10"]
[null,"Infrabel",13259,"Antwerp - Montzen",">","Fouron","Remersdael",2019,2019,1,14,"2019-01-01","00:00:00","2019-03-31","16:00:00","90 days","All day","Tunnel work",null,"x",null,null,null,null,null,null,null,null,"Tunnel de Veurs"]
[null,"Infrabel",11315,"Antwerp - Montzen","<>","LIER","Y.AUBRY",2019,2019,13,14,"2019-03-30",null,"2019-03-31",null,"3 days","All day","Track work","x",null,null,null,null,null,"x",null,null,null,"Spoorstaven - Rerouting via lijn 35-53-27B-27"]
[null,"Infrabel",11973,"Antwerp - Montzen","<>","Y.GLONS","TONGEREN",2019,2019,14,14,"2019-03-31","00:00:00","2019-03-31","16:00:00","16:00:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"C75 - omleiden via 24/1 - 40 - 36A - 36"]
[null,"Infrabel",11303,"Antwerp - Montzen","<>","LIER","Y.AUBRY",2019,2019,14,15,"2019-04-06",null,"2019-04-07",null,"3 days","All day","Track work","x",null,null,null,null,null,"x",null,null,null,"Spoorstaven - Rerouting via lijn 35-53-27B-27"]
[null,"Infrabel",11974,"Antwerp - Montzen","<>","Y.GLONS","TONGEREN",2019,2019,15,15,"2019-04-07","00:00:00","2019-04-07","16:00:00","16:00:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"C75 - omleiden via 24/1 - 40 - 36A - 36"]
[null,"Infrabel",11305,"Antwerp - Montzen","<>","LIER","Y.AUBRY",2019,2019,15,16,"2019-04-13",null,"2019-04-14",null,"3 days","All day","Track work","x",null,null,null,null,null,"x",null,null,null,"Spoorstaven - Rerouting via lijn 35-53-27B-27"]
[null,"Infrabel",11975,"Antwerp - Montzen","<>","Y.GLONS","TONGEREN",2019,2019,16,16,"2019-04-14","00:00:00","2019-04-14","16:00:00","16:00:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"C75 - omleiden via 24/1 - 40 - 36A - 36"]
[null,"Infrabel",11307,"Antwerp - Montzen","<>","LIER","Y.AUBRY",2019,2019,16,17,"2019-04-20",null,"2019-04-21",null,"3 days","All day","Track work","x",null,null,null,null,null,"x",null,null,null,"Spoorstaven - Rerouting via lijn 35-53-27B-27"]
[null,"Infrabel",11310,"Antwerp - Montzen","<>","LIER","Y.AUBRY",2019,2019,17,18,"2019-04-27",null,"2019-04-28",null,"3 days","All day","Track work","x",null,null,null,null,null,"x",null,null,null,"Spoorstaven - Rerouting via lijn 35-53-27B-27"]
[null,"Infrabel",11311,"Antwerp - Montzen","<>","LIER","Y.AUBRY",2019,2019,18,19,"2019-05-04",null,"2019-05-05",null,"3 days","All day","Track work","x",null,null,null,null,null,"x",null,null,null,"Spoorstaven - Rerouting via lijn 35-53-27B-27"]
[null,"Infrabel",11312,"Antwerp - Montzen","<>","LIER","Y.AUBRY",2019,2019,19,20,"2019-05-11",null,"2019-05-12",null,"3 days","All day","Track work","x",null,null,null,null,null,"x",null,null,null,"Spoorstaven - Rerouting via lijn 35-53-27B-27"]
[null,"Infrabel",11976,"Antwerp - Montzen","<>","Y.GLONS","TONGEREN",2019,2019,20,20,"2019-05-12","00:00:00","2019-05-12","16:00:00","16:00:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"C75 - omleiden via 24/1 - 40 - 36A - 36"]
[null,"Infrabel",11313,"Antwerp - Montzen","<>","LIER","Y.AUBRY",2019,2019,20,21,"2019-05-18",null,"2019-05-19",null,"3 days","All day","Track work","x",null,null,null,null,null,"x",null,null,null,"Spoorstaven - Rerouting via lijn 35-53-27B-27"]
[null,"Infrabel",11977,"Antwerp - Montzen","<>","Y.GLONS","TONGEREN",2019,2019,21,21,"2019-05-19","00:00:00","2019-05-19","16:00:00","16:00:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"C75 - omleiden via 24/1 - 40 - 36A - 36"]
[null,"Infrabel",11314,"Antwerp - Montzen","<>","LIER","Y.AUBRY",2019,2019,21,22,"2019-05-25",null,"2019-05-26",null,"3 days","All day","Track work","x",null,null,null,null,null,"x",null,null,null,"Spoorstaven - Rerouting via lijn 35-53-27B-27"]
[null,"Infrabel",11978,"Antwerp - Montzen","<>","Y.GLONS","TONGEREN",2019,2019,22,22,"2019-05-26","00:00:00","2019-05-26","16:00:00","16:00:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"C75 - omleiden via 24/1 - 40 - 36A - 36"]
[null,"Infrabel",11980,"Antwerp - Montzen","<>","Y.GLONS","TONGEREN",2019,2019,23,23,"2019-06-02","00:00:00","2019-06-02","16:00:00","16:00:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"C75 - omleiden via 24/1 - 40 - 36A - 36"]
[null,"Infrabel",11981,"Antwerp - Montzen","<>","Y.GLONS","TONGEREN",2019,2019,24,24,"2019-06-09","00:00:00","2019-06-09","16:00:00","16:00:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"C75 - omleiden via 24/1 - 40 - 36A - 36"]
[null,"Infrabel",11982,"Antwerp - Montzen","<>","Y.GLONS","TONGEREN",2019,2019,25,25,"2019-06-16","00:00:00","2019-06-16","16:00:00","16:00:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"C75 - omleiden via 24/1 - 40 - 36A - 36"]
[null,"Infrabel",11983,"Antwerp - Montzen","<>","Y.GLONS","TONGEREN",2019,2019,26,26,"2019-06-23","00:00:00","2019-06-23","16:00:00","16:00:00","Day","Track work","x",null,null,null,null,null,"x",null,null,null,"C75 - omleiden via 24/1 - 40 - 36A - 36"]
[null,"Infrabel",11415,"Antwerp - Montzen","<>","Heist OdB","Y.O.Dr.Aarschot",2019,2019,27,28,"2019-07-01",1.0416666666666701,"2019-07-07",2.0409722222222202,"11 days","All day","Track work","x",null,null,null,null,null,"x",null,null,null,"re routing via L35-53"]
[null,"Infrabel",13250,"Antwerp - Montzen",">","Bassenge","Visé",2019,2019,32,41,"2019-08-05","06:00:00","2019-10-06",1.95763888888889,"63 days","All day","Bridge work",null,"x",null,null,null,null,null,null,null,null,"Pont sur Canal"]

{"sheet":"Graphic Overview","index":2,"n_rows":4,"n_cols":368,"rows_kept":4,"cut":false,"hidden":false,"merged":[[3,332,3,338],[3,339,3,345],[3,346,3,352],[3,115,3,121],[3,122,3,128],[3,129,3,135],[3,136,3,142],[3,143,3,149],[3,150,3,156],[3,157,3,163],[3,164,3,170],[3,171,3,177],[3,248,3,254],[3,255,3,261],[3,262,3,268],[3,269,3,275],[2,343,2,373],[2,160,2,189],[2,190,2,220],[2,221,2,251],[2,252,2,281],[2,282,2,312],[2,313,2,342],[0,1,1,7],[2,9,2,39],[2,40,2,67],[2,68,2,98],[2,99,2,128],[2,129,2,159],[3,10,3,16],[3,17,3,23],[3,24,3,30],[3,31,3,37],[3,38,3,44],[3,45,3,51],[3,52,3,58],[3,59,3,65],[3,66,3,72],[3,73,3,79],[3,80,3,86],[3,87,3,93],[3,94,3,100],[3,101,3,107],[3,108,3,114],[3,178,3,184],[3,185,3,191],[3,192,3,198],[3,199,3,205],[3,206,3,212],[3,353,3,359],[3,360,3,366],[3,367,3,373],[3,213,3,219],[3,220,3,226],[3,227,3,233],[3,234,3,240],[3,241,3,247],[3,276,3,282],[3,283,3,289],[3,290,3,296],[3,297,3,303],[3,304,3,310],[3,311,3,317],[3,318,3,324],[3,325,3,331]]}
[null,"C01 Overview"]
[]
[null,null,null,null,null,null,2017,null,null,"January",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"February",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"March",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"April",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"May",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"June",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"July",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"August",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"September",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"October",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"November",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"December"]
[null,"Possession","Type","Date from","Date to","Duration","IM",null,null,null,1,null,null,null,null,null,null,2,null,null,null,null,null,null,3,null,null,null,null,null,null,4,null,null,null,null,null,null,5,null,null,null,null,null,null,6,null,null,null,null,null,null,7,null,null,null,null,null,null,8,null,null,null,null,null,null,9,null,null,null,null,null,null,10,null,null,null,null,null,null,11,null,null,null,null,null,null,12,null,null,null,null,null,null,13,null,null,null,null,null,null,14,null,null,null,null,null,null,15,null,null,null,null,null,null,16,null,null,null,null,null,null,17,null,null,null,null,null,null,18,null,null,null,null,null,null,19,null,null,null,null,null,null,20,null,null,null,null,null,null,21,null,null,null,null,null,null,22,null,null,null,null,null,null,23,null,null,null,null,null,null,24,null,null,null,null,null,null,25,null,null,null,null,null,null,26,null,null,null,null,null,null,27,null,null,null,null,null,null,28,null,null,null,null,null,null,29,null,null,null,null,null,null,30,null,null,null,null,null,null,31,null,null,null,null,null,null,32,null,null,null,null,null,null,33,null,null,null,null,null,null,34,null,null,null,null,null,null,35,null,null,null,null,null,null,36,null,null,null,null,null,null,37,null,null,null,null,null,null,38,null,null,null,null,null,null,39,null,null,null,null,null,null,40,null,null,null,null,null,null,41,null,null,null,null,null,null,42,null,null,null,null,null,null,43,null,null,null,null,null,null,44,null,null,null,null,null,null,45,null,null,null,null,null,null,46,null,null,null,null,null,null,47,null,null,null,null,null,null,48,null,null,null,null,null,null,49,null,null,null,null,null,null,50,null,null,null,null,null,null,51,null,null,null,null,null,null,52]

{"sheet":"Help","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Data","index":4,"n_rows":42,"n_cols":7,"rows_kept":42,"cut":false,"hidden":true,"merged":[]}
["IM",null,"Section",null,"Duration","ID value","Reason for restriction"]
["Infrabel",88,"Gent - Mechelen",1,"All day",10002,"Signal work"]
["Pro Rail",84,"Mechelen - Montzen",2,"Day",null,"Switch work"]
["DB Netz",80,"Antwerp - Montzen",3,"Night",null,"Catenary work"]
["PKP",null,"Montzen - Aachen",4,null,null,"Track work"]
["SZDC",54,"Aachen - Oberhausen",5,null,null,"Rail work"]
["LG",24,"Rotterdam - Meteren",6,null,null,"Tunnel work"]
[null,null,"Roosendaal - Antwerp",7,null,null,"Bridge work"]
[null,null,"Meteren - Zevenaar",8,null,null,"Misc. Work"]
[null,null,"Zeevenaar - Emmerich",9,null,null,"Maintanance"]
[null,null,"Emmerich - Oberhausen",10]
[null,null,"Oberhausen - Hannover",11]
[null,null,"Wilhelmshaven - Bremen",12]
[null,null,"Bremerhaven - Bremen",13]
[null,null,"Bremen - Hannover",14]
[null,null,"Hannover - Magdeburg",15]
[null,null,"Magdeburg - Berlin",16]
[null,null,"Berlin - Frankurt (O)",17]
[null,null,"Magdeburg - Falkenberg",18]
[null,null,"Falkenberg - Bad Schandau",19]
[null,null,"Falkenberg - Horka",20]
[null,null,"Bad Schandau  - Decin",21]
[null,null,"Decin - Praha",22]
[null,null," Horka - Wegliniec",23]
[null,null,"Wegliniec - Wroclaw",24]
[null,null,"Wroclaw - Katowice",25]
[null,null,"Frankurt (O) - Poznan",26]
[null,null,"Poznan - Warszawa",27]
[null,null,"Warszawa - Terespol",28]
[null,null,"Warszawa - Trakiszki",29]
[null,null,"Trakiszki-Šeštokai",30]
[null,null,"Šeštokai-Kaunas",31]
[null,null,"Hamburg - Magdeburg",32]
[null,null,"Löhne - Bad Bentheim",33]
[null,null,"Amersfoort - Bad Bentheim",34]
[null,null,"Löhne - Hannover",35]
[null,null,"Oberhausen - Löhne",36]
[null,null,"Amsterdam - Amersfoort",37]
[null,null,"Amersfoort - Utrecht",38]
[null,null,"Utrecht - Merten",39]
[null,null,"Merten - Den Bosch",40]
[null,null,"Den Bosch - Roosendaal",41]